**FIPS Steering Group – Meeting # 8 – Minutes**

Meeting Date: 21st November 2024

Meeting Venue: MS Teams

Meeting Agenda:

|  |
| --- |
|  |
| **Agenda Item** |
| Welcome and agreement of minutes of meeting no 7 |
| Review of action points from previous meeting  |
| FIP update  |
| Social Risk Assessment update  |
| Bord Bia Standard  |
| Next Steps & Action List |
| AOB & Next Meeting Date |

**Minutes**

* **Welcome and agreement of minutes of meeting no 7**
	+ Members agreed on minutes from meeting 7
* **FIPs update**
	+ Verifact presented a draft FIP newsletter, and it was discussed by the group
	+ Suggestion that the newsletter could cover clarification and provide awareness of important social issues such as contracts
	+ It was agreed that the newsletter would issue twice per year
	+ Haddock and Coley FIPS upgraded on Fishery Progress to a B rating
	+ Annual report for Prawn FIP due to be submitted at the end of December
	+ 1st Whiting FIP report due also at end of December
	+ Update on brown crab working group was provided by Rory Campbell
		- 2 workshops have been carried out, Sept and Oct 2024
		- Proposals will be submitted to the Minister by the end of the year
		- Continued work into a fisheries management plan which will be incorporated into the Brown Crab FIP workplan
	+ Key actions for the Q1 and Q2 of 2025 were presented
	+ Constructive discussion on ghost gear. Industry rep noted the FIP vessels participate in the Clean Oceans initiatives which includes the bringing ashore of ghost gear.
	+ BIM have figures on quantities of ghost gear taken out of the marine environment.
	+ Action: Newsletter to be developed and sent to FIP members
	+ Action: BIM to bring figures of ghost gear to next meeting for further discussion
* **Social Update**
	+ One page summary developed on the role of FIPs in social issues and presented to the group. This was adopted by the meeting members.
	+ 1st social risk assessment update due at end of December to Fishery Progress
	+ Social sub-group has been set up and meeting held. Focus of meeting was to work with the fleet to facilitate the risk assessment.
	+ An issue arising from the meeting was a lack of consistent knowledge across stakeholder groups on contracts. This is an area that can be addressed under the social workplan.
	+ First tranche of interviews with fishers and vessel owners have been carried out
	+ 14 interviews were conducted in Castletownbere and Kinsale
	+ Suggestion from an industry rep of an annual social survey/review to ensure the results reflect conditions within the fleet. The group agreed that this is a good approach.
	+ Action: Labour force study to be circulated to group
	+ Action: The draft social workplan should be reviewed annually based on social survey updates
* **AOB & Next Meeting Date**
	+ Action: Doodle poll to be circulated for next meeting in January 2025