## Workshop Logistics
Item | Total | Responsible | Status | Notes
Venue | 300 | CADS | Completed |  | https://drive.google.com/file/d/1mZZ8mtojiABscZa4vlTWbv7xlzQtOCqg/view?usp=drive_link | https://drive.google.com/file/d/1VlwVGnqCIK8d-LQd1ojRXENSjjcrmRGF/view?usp=drive_link | https://drive.google.com/file/d/1vO7sXllQ3CHX2EA6D0FVW3ruEPnyWscb/view?usp=drive_link
Catering | 1697.5 | CADS | Completed
Save-the-Date Notification |  | CADS | Completed |  | meet.google.com/wrc-tycv-ozh
Budget (Preparation and Facilitation, Venue and Food) |  | TNC | Completed
Agenda |  | CADS | Completed
Supplies |  | TNC |  | What supplies are necessary? Quotations will be necessary here. Jane, to purchase supplies and have available at workshop | https://drive.google.com/file/d/1xmEyaN0M5caic6zJcsY9TadVgEmScycJ/view?usp=drive_link
Workshop Equipment |  | CADS/TNC | Completed
Rapporteur |  | CADS | In-progress
Evaluation Sheet |  | CADS | In-progress
Communication - Tshirt |  | TNC | Completed | Unavailable.
Social Media Post |  | CADS | In-progress
FIP+ FDM Banner | 227.81 | CADS | In-progress |  | https://drive.google.com/file/d/1vO7sXllQ3CHX2EA6D0FVW3ruEPnyWscb/view?usp=drive_link | https://drive.google.com/file/d/1227c9gc6neaf-9L4r9hd7nI4cIOakAJt/view?usp=drive_link
Workplan Revision Workshop
Attendees
1 Elmer Rodriguez | 2
2 Jason Arnold | 1
3 Jeronimo Tzul | 3
4 Robert Usher | 1
5 Gregory Lambey | 2
6 Issac Lambey | 3
7 Roberto Bautista | 1
8 Jaime Velasquez | 2
9 Estevan Solis | 3
10 Julio Maaz | 1
11 Peter Battisti
12 Hugo Miranda | 2
13 Jane Salazar Mcloughlin
14 Dr. Jay Coombs
15 N Martinez UB | 3
16 Virginia Burns | 1
17 Sydney Fuller | 2
18 Kenneth Esquivel | 3
19 Mauro Gongora | 1
20 Demois Williams
21 Amani Coombs
22 Aretha Mortis
Note on B1: @aretha.mortis@cadsbelize.com please insert the costs for the items highlighted in yellow. _Assigned to Aretha Mortis_ -Jay Coombs

## Workshop Agenda - Facilitator N
Agenda Item | Objectives | Time | Activity | Facilitator/Session Lead
Arrival - Registration - Coffee |  | 8:30
Welcome - Workshop Introduction | This session will bring the participants' attention to the main reasons for the conduct of the workshop. The TNC Fisheries Specialist will do this by providing a brief overview of the scorecard report for the Belize FIP+FDM and its current rating. The TNC Fisheries Specialist will additionally explain the order of the workshop day to the participants. | 9:00 - 9:30 | Presentation | Mrs. Jane Salazar McLoughin Fisheries Specialist, TNC
SUSTAINABLE FISH STOCKS
Work Session 1: Review of Indicators for Sustainable Fish Stocks Stock status outcome (1.1.1) Stock rebuilding outcome (1.1.2) Harvest strategy (1.2.1) Assessment of stock status (1.2.4) | This session re-introduces the workshop participants to the indicators for fishery progress under this action. Participants will review two(2) of the four(4) indicators and prioritise the actions they will be progressing either to October 2023, December 2023 or to January 2024. | 9:30 - 10:30 am | In groups, participants will assess the tasks for each of the four(4) actions required to complete this Indicator. In particular, they will review and prioritise the following actions: Stock status outcome (1.1.1) Stock rebuilding outcome (1.1.2) Harvest strategy (1.2.1) Assessment of stock status (1.2.4) | FIP+ Coordinator
Session Summary | Participants will provide summary feedback on the discussions and decisions reached in their groups. The facilitator will close this session ensuring that the final decisions are endorsed and agreed by all. | 10:30 -10:45 am | The small groups will provide feedback to the plenary regarding the decisions on each action supporting the completion of this task. The facilitator will guide the workshop to consensus based on group feedback to the plenary. | FIP+ Coordinator
Break - 10:30 -10:45 am
Work Session 2: Review of Indicators for Sustainable Fish Stocks cont. Indicators: Harvest control rules & tools (1.2.2) Harvest strategy information & monitoring (1.2.3) | Participants will repeat the activity for session 1, but this time they will focus on: Harvest control rules & tools (1.2.2) Harvest strategy information & monitoring (1.2.3) | 11:00 -12:15 pm | The small groups will provide feedback to the plenary regarding the decisions on each action supporting the completion of this overall task. The facilitator will guide the workshop to consensus based on group feedback to the plenary. | FIP+Coordinaor
Session Summary | Participants will provide summary feedback on the discussions and decisions reached in their groups. The facilitator will close this session ensuring that the final decisions are endorsed and agreed by all. | 12:15 - 12:30 pm | The small groups will provide feedback to the plenary regarding the decisions on each action supporting the completion of this task. The facilitator will guide the workshop to consensus based on group feedback to the plenary. | FIP+Coordinaor Steering Committee small group representative
Lunch |  | 12:30
EFFECTIVE MANAGEMENT
Work Session 3: Review of Indicators for Effective Management Indicators: Fishery-specific objectives(3.2.1) | This session re-introduces the workshop participants to the indicators for fishery progress under this action. Participants will review two(2) of the indicators that were rated negatively in the last Fisheryprogress.com scoring. After reviewing in small groups, participants willprioritise the actions they will be progressing either to October 2023, December 2023 or to January 2024. | 1:15 - 2:00 pm | The small groups will provide feedback to the plenary regarding the decisions on each action supporting the completion of this overall task. The facilitator will guide the workshop to consensus based on group feedback to the plenary. | FIP+ Coordinator
Session Summary | Participants will provide summary feedback on the discussions and decisions reached in their groups. The facilitator will close this session ensuring that the final decisions are endorsed and agreed by all. | 2:00- 2:15 pm | The small groups will provide feedback to the plenary regarding the decisions on each action supporting the completion of this task. The facilitator will guide the workshop to consensus based on group feedback to the plenary. | FIP+Coordinaor Steering Committee small group representative
Work Session 4: "Work Session 3: Review of Indicators for Effective Management Indicators: Monitoring and Management Performance Evaluation (3.2.4) | This session re-introduces the workshop participants to the indicators for fishery progress under this action. Participants will review two(2) of the indicators that were rated negatively in the last Fisheryprogress.com scoring. After reviewing in small groups, participants willprioritise the actions they will be progressing either to October 2023, December 2023 or to January 2024. | 2:15- 3:00 pm | The small groups will provide feedback to the plenary regarding the decisions on each action supporting the completion of this overall task. The facilitator will guide the workshop to consensus based on group feedback to the plenary. | FIP+ Coordinator
Session Summary | Participants will provide summary feedback on the discussions and decisions reached in their groups. The facilitator will close this session ensuring that the final decisions are endorsed and agreed by all. | 3:00 -3:15 pm | The small groups will provide feedback to the plenary regarding the decisions on each action supporting the completion of this task. The facilitator will guide the workshop to consensus based on group feedback to the plenary. | FIP+Coordinaor Steering Committee small group representative
Break (Ice-breaker) 3:15 pm - 3:30 pm
Recommitment to Workplan | - Introduction to FIP Social Policy Statement - Endorsement of the Revised Workplan | 3:30 - 4:15 pm | This session is to introduce the participants to the FIP Social Policy Statement so that they can approve formulation for approval at the August 2023 SC meeting. Participants will also endorse presentation of the revised workplan for approval at the August 2023 SC Meeting | FIP+ Coordinator Fisheries Specialist
Workshop Evaluation | Participants complete workshop evaluation form online | 4:15 - 4:30 pm |  | FIP+ Coordinator
Close: 4:30 pm

## Workshop Agenda
Fishery Improvement Project (FIP) & Fishery Development Model (FDM) Workplan Revision Workshop Black Orchid Resort 27 July 2023
No. | Item | Time | Facilitator/Session Lead
1 | Arrival - Registration - Coffee | 8:30:00 a.m.
2 | Welcome - Workshop Introduction | 9:00 am - 9:10 am | Mrs. Jane Salazar McLoughlin Fisheries Specialist, TNC
3 | Participants' Introductions Order of the Day | 9:10 am - 9:30 am | FIP+ Coordinator
4 | SUSTAINABLE FISH STOCKS
4.1 | Work Session 1: Review of Indicators for Sustainable Fish Stocks Stock status outcome (1.1.1) Stock rebuilding outcome (1.1.2) Harvest strategy (1.2.1) Assessment of stock status (1.2.4) | 9:30 am - 10:30 am | FIP+ Coordinator
4.2 | Session Summary | 10:30 am - 10:45 am | FIP+ Coordinator
4.3 | Break - 10:30 am -10:45 am
4.4 | Work Session 2: Review of Indicators for Sustainable Fish Stocks cont. Indicators: Harvest control rules & tools (1.2.2) Harvest strategy information & monitoring (1.2.3) | 11:00 am -12:15 pm | FIP+Coordinator
4.5 | Session Summary | 12:15 pm - 12:30 pm | FIP+Coordinator Steering Committee small group representative
4.6 | Lunch- 12:30 pm - 1:15 pm
5 | EFFECTIVE MANAGEMENT
5.1 | Work Session 3: Review of Indicators for Effective Management Indicator: Fishery-specific objectives (3.2.1) | 1:15 pm - 2:00 pm | FIP+ Coordinator
5.2 | Session Summary | 2:00 pm - 2:15 pm | FIP+Coordinator Steering Committee small group representative
5.3 | Work Session 4: "Work Session 3: Review of Indicators for Effective Management Indicators: Monitoring and Management Performance Evaluation (3.2.4) | 2:15 pm - 3:00 pm | FIP+ Coordinator
5.4 | Session Summary | 3:00 pm -3:15 pm | FIP+Coordinator Steering Committee small group representative
6 | Break (Ice-breaker) 3:15 pm - 3:30 pm
7 | Recommitment to Workplan | 3:30 pm - 4:15 pm | FIP+ Coordinator Fishery Specialist
8 | Recap of the Day | 4:15 pm - 4:30 pm | FIP+ Coordinator
Close: 4:30 pm

## Complete Robust Stock Assessmen
Action 1: Complete Robust Stock Assessment | TASKS | OUTSTANDING MATTER(S) | Expected Completion Date | PRIORITIZED | JUSTIFICATION | PROJECTED RESULTS TIMELINE | Primary/ Lead FIP+ Entity | Supporting FIP+ Entity | Progress Updates
| Allocate funds and capacity to repeat every year |  | 2024-11-01 | Yes | This task is relevant but will require resources and capacities beyond the FIP+FDM Project. | Completion by OCtober 2023 | BFD |  | 2023-10-01
| Institutionalization of stock assessment | Assessment of fisheries level by the registered fishers and non-fishers. Cooperatives will need to play a role in providing data. | 2024-11-01 | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | This task remains relevant, the resources and the cpacities exist to implement it. | BFD | National Coop, Northern Coop | 2024-03-01 | 2023-10-01 | 2023-12-01
| Share assessment results | Technical capacity deficit, technical report | 2021-05-01 | Yes | This task is relevant but will require resources and capacities beyond the FIP+FDM Project. | Completion by December 2023 | BFD | TNC | 2023-10-01 | 2023-12-01
| Submit assessment to Peer Review | Local Peers | 2021-04-01 | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | Completion by March 2024 | BFD | FIP SC | 2023-10-01 | 2023-12-01 | 2024-03-01
| Working Group conducts Stock Assessment |  | 2021-01-01 | No | This task is no longer relevant to the FIP+FDM Project. | Terminate
| Working Group makes methods public | Official and original assessment completed by BFD w/support from TNC | 2020-11-01 | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | Completion by March 2024 | BFD | TNC | 2023-10-01 | 2023-12-01
| Create communication platform to share methodology (model and data) | Management Plan, existing assesment includes the Methodology | 2020-05-01 | No | This task is no longer relevant to the FIP+FDM Project. | Terminate
| Working Group selects best-fit model | Completed - Evidence is that Belize is a party to OSPESCA | 2020-06-01 | No |  | Terminate
| Working Group (WG) conducts global review | Completed as Belize is part of OSPESCA | 2020-07-01 | No | This task remains relevant, the resources and the cpacities exist to implement it. | Terminate
| Review existing and on-going data collection (local) | Signing of Data Sharing Agreement by Cooperatives - this is part of the Fisheries Act - Tally also exists along with Vericatch - National's sign on to TAlly - TNC to support a focal point from Northern to share the request - and BFD to request the information from TNC |  | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | Completion by October 2023 |  |  | 2023-10-01

## Identify Rebuilding Strategy
Indicator 1.1.2: Stock Rebuilding Outcome
Action: Identify a Suitable Rebuilding Strategy | TASKS | OUTSTANDING MATTER(S) | Expected Completion Date | PRIORITIZED | JUSTIFICATION | PROJECTED RESULTS | Primary/ Lead FIP+ Entity | Supporting FIP+ Entity | Progress Updates
| Continuously improve co-op data collection processes as a means of being able to evaluate changes in production and changes in CPUE | With the completion of stock assessment, the FIP stakeholder groups have agreed to investigate what a rebuilding strategy should look like, in the event that production does decrease or a significant change in the catch per unit of effort is noted. The investigation will include reasearch into successful rebuilding strategies in regional lobster fisheries, as well to push the direct and immediate need for an updated and regular stock assessment. | 2022-12-01 | Yes | This task is relevant but will require resources and capacities beyond the FIP+FDM Project. | Completion by March 2024 | Belize Fisheries Dept | Cooperatives, TNC, TASA | 2023-10-01 | 2024-12-01
| Support the strategy for moving forward a stock assessment for Belizean Spiny Lobster |  | 2021-12-01 | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | Completion by October 2023 | BFD | TNC | 2023-10-01 | 2024-12-01 | 2024-03-01
| Conduct global analysis on lobster fisheries identifying rebuilding strategies and specifying recommendations for the Belizean Spiny Lobster Fishery Rebuilding Strategy |  | 2020-12-01 | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | Completion by October 2023 | BFD | TNC | 2023-10-01 | 2024-12-01

## Incorporate AMF for Harvest Con
Indicator 1.2.1: Harvest Strategy
Action: Incorporate AMF to Guide Decision-making Regarding Harvest Control Strategy | TASKS | OUTSTANDING MATTER(S) | Expected Completion Date | PRIORITIZED | JUSTIFICATION | PROJECTED RESULTS | Primary/ Lead FIP+ Entity | Supporting FIP+ Entity | Progress Updates
| Pilot electronic data transfer between traceability systems in Coops and AMF |  | 2020-07-01 | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | This task remains relevant, the resources and the cpacities exist to implement it. | TNC | BFD, Cooperatives | 2023-10-01 | Decmber 2023 | 2024-03-01
| Independent reviews of Harvest Strategy are conducted and recommendations for improvement are made public | Include considerations from Trap Data, Inventory data, close season, size limit, and certain limitations | 2024-11-01 | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | Completion by December 2023 | BFD | TNC | 2023-10-01 | Decmber 2023
| Ongoing training and education on the AMF purpose, functions, etc., conducted for participating government, NGOs, and Coops | Data provision and submission from coops,and co-managers the lobster announcement contributes to this as well | 2024-11-01 | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | Completion by March 2024 |  |  | 2023-10-01 | Decmber 2023 | 2024-03-01
| Create a multi stakeholder collaboration to define Harvest Control Rules, including setting a quota for lobster - | This the role of the Belize Fisheries Council - legally mandated | 2024-11-01 | No | This task is no longer relevant to the FIP+FDM Project. | Terminate
| Technology for AMF is built and continuously refined and updated to incorporate additional data and data needs for the future (including social and economic considerations) | Vessel monitoring system, Tracebility Technology, | 2023-01-01 | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | Completion by March 2024 | TNC | National and Northern Coops | 2023-10-01 | Decmber 2023 | 2024-03-01
| Develop system to incorporate external data into government database |  | Completed
| Incorporate National data sets into the AMF via the Traceability system to the Fisheries Visualisation Tool - Repeat for Northern | National | Completed
| Incorporate Northern data into the AMF | Northern's Data sharing Agreement - to be prepared and presented to the Management committee meeting | 2020-12-01 | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | Completion by October 2023 | Northern | TNC | 2023-10-01
| Determine protocols for data quality, sharing, and KDEs- including setting of target and limit reference points | Data management workshop report | 2020-06-01 | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | Completion by October 2023 | BFD | TNC, Northern, National | 2023-10-01
| Create Scientific Committee for Harvest Control Rules and Strategy | Fisheries Council roles - The Government of Belize will appoint a Scientific Advisory Group - BFD to provide draft TOR | 2020-02-01 | Yes | 2023-10-01 |  | BFD |  | 2023-10-01

## Harvest Control and Rules
Indicator 1.2.2: Harvest Control Rules and Tools
Action: Turneffe Casita Inventory Pilot | TASKS | OUTSTANDING MATTER(S) | Expected Completion Date | PRIORITIZED | JUSTIFICATION | PROJECTED RESULTS | Primary/ Lead FIP+ Entity | Supporting FIP+ Entity | Progress Updates
| Develop scaling strategy including outreach and expansion of incentive program to other coop members | CApture Fisheries workplan BFD to assess available lobster traps and shades ; data collection required + resources needed +TASA to provide data on 2021 by October 2023 | 2022-01-01 | Yes | This task is relevant but will require resources and capacities beyond the FIP+FDM Project. | Completion by November 2024 | BFD | WCS - Southwater Caye +TASA at Turneffe | 2023-10-01 | 2023-10-01 | 2024-03-01 | 2024-11-01
| Link into AM Plan, Use effort data to inform stock assessment and HCRs |  | Completed | No
| Carry out a verification process, Develop long-term verification process for registry and effort data - reference four steps on verification process |  | 2022-02-01 | Yes | This task is relevant but will require resources and capacities beyond the FIP+FDM Project. | Completion by November 2024 | BFD | TNC | 2023-10-01 | 2023-12-01 | 2024-03-01
| Carry out a verification (physical survey) |  | Completed
| Align with OSPESCA legal requirements and legal aspects |  | Completed
| Deploy tagging system and verify inventory data through cross-reference with VMS pilot - Assessing the presence of fishers on the sea but a suitable technology has not been found as yet. Subscription data for system could prove challenging for long term sustainabilty | Fisheries Specialist to provide evidence to support this for enforcement and fishing effort - effort is a pilot ( WCS to send the report on pilot) | 2021-09-01 | Yes | This task is relevant but will require resources and capacities beyond the FIP+FDM Project. | Completion by October 2023 |  |  | 2023-10-01
| Record Bycatch- through interview surveys | By-catch in the lobster fishery is minimal based on the type of gear. Traps may vary but they can be returned to sea. The by-catch does occur. The impact study can provide feedback on by-catch but specifically to the Turneffe | 2020-09-01 | No | There are no resources available to progress this action. | Terminate
| Identify materials and design of gear and dimensions |  | Completed
| Design and implement tagging and registry system, determine tag type, calculate level of effort |  | Completed
| Determine and map the location of fishing camps, quantify number of traps and shades used in each fishing area |  | Completed

## Harvest Strategy Info and Monit
Indicator 1.2.3: Harvest Strategy Information and Monitoring
Action: Coordinate Campaign to Pass Aquatic Resource Act | TASKS | Expected Completion Date | PRIORITIZED | JUSTIFICATION | PROJECTED RESULTS | Primary/ Lead FIP+ Entity | Supporting FIP+ Entity | Progress Updates
Management Plan | Develop Lobster Fisheries management plan under passed Act | Completed | No | This task is no longer relevant to the FIP+FDM Project. | Terminate
Need evidence - first meeting of Fisheries Council | Activate Fisheries Advisory Council | Completed | No | This task is no longer relevant to the FIP+FDM Project. | Terminate
WCS - provide communication data | Develop PR campaign, including social media | Completed | No | This task is no longer relevant to the FIP+FDM Project. | Terminate
WCS - provide communication data + Mr Fuller from Belize Fishermen Cooperative Association (BFCA) | Direct Lobbying to key government officials in House committee and Cabinet Sub-committee | Completed | No | This task is no longer relevant to the FIP+FDM Project. | Terminate
FB posts - WCS - Julio to send committee members | Create Task Force (TF) to coordinate interested stakeholders to implement campaign | Completed | No | This task is no longer relevant to the FIP+FDM Project. | Terminate

## Conduct long-term Fisheries Dep
Fishery Specific Objectives
Coordinate Campaign to Pass Aquatic Resources Act | TASKS | Expected Completion Date | PRIORITIZED | JUSTIFICATION | PROJECTED RESULTS | Primary/ Lead FIP+ Entity | Supporting FIP+ Entity | Progress Updates
| Develop Lobster Fisheries management plan under passed Act | Completed | No | This task is no longer relevant to the FIP+FDM Project.
| Activate Fisheries Advisory Council | 2021-09-01 | No | This task is relevant but will require resources and capacities beyond the FIP+FDM Project.
| Develop PR campaign, including social media | Completed | No | This task is no longer relevant to the FIP+FDM Project.
| Direct Lobbying to key government officials in House committee and Cabinet Sub-committee | Completed | No | This task is no longer relevant to the FIP+FDM Project.
| Create Task Force (TF) to coordinate interested stakeholders to implement campaign | Completed |  | This task is no longer relevant to the FIP+FDM Project.
Note on A2: The tasks listed here do not coincide with the tasks listed on FisheryProgress/the workplan. They include: - Share analysis with FIP participants - Analyze data - Share data with AMF - Conduct interviews - Monitoring vessels and port-side -jane.salazar@tnc.org @jane.salazar@tnc.org the Action has been replaced. -Jay Coombs

## Improve Coop Staffing and Hirin
Monitoring and Management Performance Evaluation
Action: Improve Coop Staffing and Hiring Policies | TASKS | OUTSTANDING MATTER(S) | Expected Completion Date | PRIORITIZED | JUSTIFICATION | PROJECTED RESULTS | Primary/ Lead FIP+ Entity | Supporting FIP+ Entity | Progress Updates
| Update hiring policies to reflect more equitable and efficient strategies |  | 2024-11-01 | Yes | This task remains relevant, the resources and the capacities exist to implement it. | Completion by December 2023 | Northern and National Cooperatives | TNC | 2023-10-01 | 2024-12-01
| Review data after 6 months (on-going) (need to verify) |  | 2024-11-01
| Implement strategies (including gender equity considerations) | Women in fisheries forum | 2021-02-01 | Yes | This task remains relevant, and the resources and capacities exist to implement it. | Completion by October 2023 | WCS | BFD | 2023-10-01 | 2023-12-01 | 2024-03-01
| Engage co-op management on strategies to improve | Tally Reporting - link | 2020-09-01 | Yes | This task remains relevant, the resources and the cpacities exist to implement it. | Completion by October 2023 | TNC | Northern and National Cooperatives | 2023-10-01 | 2023-12-01
| Conduct analysis of staff and plan workflows |  | Completed

## Implement Long-term VMS Monitor
Monitoring and Management Performance Evaluation
Action: Implement Long-term VMS Monitoring Program | TASKS | OUTSTANDING MATTER(S) | Expected Completion Date | PRIORITIZED | JUSTIFICATION | PROJECTED RESULTS | Primary/ Lead FIP+ Entity | Supporting FIP+ Entity | Progress Updates
| Government traning on analysis |  | 2024-11-01
| Share data with Global Fishing fleet |  | 2024-11-01
| Roll-out(scale) to fishing fleet |  | 2021-02-01
| Develop scaling strategy to entire fishing fleet |  | 2020-09-01
Cost-effectiveness analysis of system
Develop and deploy e-logbook and training program
Scope out technology requirements and linking with VMS and Tally
Deploy 85 units of VMs
Recruit volunteer for Pilot
Completed

## Recap
Useful | Challenges | Commitment | Expectations

## Copy of Implement Long-term VMS
Monitoring and Management Performance Evaluation
Action: Implement Long-term VMS Monitoring Program | TASKS | OUTSTANDING MATTER(S) | Expected Completion Date | PRIORITIZED | JUSTIFICATION | PROJECTED RESULTS | Primary/ Lead FIP+ Entity | Supporting FIP+ Entity | Progress Updates
| Update hiring policies to reflect more equitable and efficient strategies |  | 2024-11-01 | View
| Review data after 6 months (on-going) |  | 2024-11-01
| Implement strategies (including gender equity considerations) |  | 2021-02-01 | View
| Engage co-op management on strategies to improve |  | 2020-09-01 | View
| Conduct analysis of staff and plan workflows |  | Completed | View