# Northern Brazil Caribbean red snapper - pot/trap

## Fishery Improvement Project (FIP) Workplan

Table 1: Workplan Overview

| Workplan Version and Date | 08/01/2025 |
| --- | --- |
| Start date (expected) | End date (anticipated month/year) |
| 04/01/2016 | 12/31/2026 |
| FIP Lead (organization/individual responsible for Action Plan) | Improvements recommended by (meeting/group that supported the development) |
| IABS | IABS / UFPA / OCEANA / MPA / MMA & Stakeholders |
| FIP Coordinator (organization/individual responsible for reporting on FisheryProgress) | Workplan organized by (consultant or person) |
| IABS | Andre M. Brugger, Oc. MSc |

Table 2. Unit(s) of Assessment (UoA)

| UoA 1 | Description |
| --- | --- |
| Target species (common and scientific name) | Example: Caribbean Red Snapper (Lutjanus purpureus) |
| Stock | Example: Western Atlantic Ocean |
| Geographical area | Example: The exclusive economic zone (EEZ) of Brazil |
| Fishing method or gear type | Example: pot/traps |
| Fishing fleet or group of vessels, or individuals fishing operators pursuing stock | Example: Semi industrial fleet |

## FIP Actions

Table 3. Performance Indicator Action Plan Table for Action Environmental Impact

| Action Number and Name | 1. Stock Assessment and Environmental Impact |
| --- | --- |
| Action Goal | Develop studies to assess fisheries environmental impacts on species and substrates, stock assessment and technical support for management improvements. |
| Action Description | Develop a study to identify the existence of one or more snapper species on the North and Northeast coasts. |
| Expected Completion Date | July 2026 |
| Priority | High |
| Estimated Cost | 5.000,00 BRL |
| Responsible Parties | NETUNO USA, GPESCA, OCEANA, MPA |
| MSC PI(s) Addressed by the Action | 1.1.2, 2.5.3, 2.4.3, 2.1.3, 2.1.1 |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Stock Assessment and Environmental Impact | Identify the existence of one or more snapper stocks on the North and Northeast coasts | IABS | NETUNO USA, GPESCA, OCEANA, MPA | Apr 2016 | July 2026 | Technical Reports |

Table 3. Performance Indicator Action Plan Table for Action Fisheries data collection

| Action Number and Name | 2. Fisheries data collection |
| --- | --- |
| Action Goal | Start a continuous fisheries data collection Program (catch, effort, fishing areas, by-catch, ghost fisheries) |
| Action Description | Use new adopted Trace Register TR5 software to segregate data from official catch certificates (landing composition, effort, areas, by-catch/by-products, gears, bait used). |
| Expected Completion Date | July 2026 |
| Priority | High |
| Estimated Cost | 10.000,00 BRL |
| Responsible Parties | NETUNO USA, GPESCA, UFPA, MPA |
| MSC PI(s) Addressed by the Action | 1.2.3, 1.1.2, 1.1.1, 2.3.3, 2.5.3, 2.4.3, 2.1.3, 2.2.3, 2.2.2, 2.2.1 |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Fisheries data collection | Use new adopted Trace Register TR5 software to segregate data from official catch certificates (landing composition, effort, areas, by-catch/by-products, gears, bait used). | IABS | NETUNO USA, UFPA, GPESCA, MPA | February 2024 | July 2026 | Technical Reports |

Table 3. Performance Indicator Action Plan Table for Action Management and Monitoring System

| Action Number and Name | 3. Management and Monitoring System |
| --- | --- |
| Action Goal | Develop and implement a Management and Monitoring System |
| Action Description | Ensure that management plan designed by the FIP stakeholders will be discussed and adopted by the management fisheries management committee (CPGs). |
| Expected Completion Date | December 2026 |
| Priority | Medium |
| Estimated Cost | 5.000,00 BRL |
| Responsible Parties | NETUNO USA, IABS, GPESCA, UFPA, OCEANA, MPA |
| MSC PI(s) Addressed by the Action | 1.2.2, 1.2.1, 1.2.3, 1.1.2, 3.2.3, 3.1.2, 3.2.2, 3.2.1, 3.1.1, 3.2.4 |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Management and Monitoring System | Ensure that management plan designed by the FIP stakeholders will be discussed and adopted by the management fisheries management committee (CPGs). | IABS | NETUNO USA, UFPA, GPESCA, OCEANA, MPA | March 2024 | December 2026 | CPG minutes |

Table 3. Performance Indicator Action Plan Table for Action Management Plan

| Action Number and Name | 4. Management Plan |
| --- | --- |
| Action Goal | Develop and implement a management plan for the fishery/stock. |
| Action Description | Develop and implement a management plan for the fishery/stock based on defining clear objectives for management, as an export quota, defining a stock assessment method and verifying the current status of the stock in relation to reference points, designing a strategy to monitor the stock and a mechanism of feed-back that allows decision-makers to rapidly change fishing intensity when adverse situations are identified. |
| Expected Completion Date | December 2026 |
| Priority | Medium |
| Estimated Cost | 30,000.00 BRL |
| Responsible Parties | NETUNO USA, UFPA, OCEANA, MPA |
| MSC PI(s) Addressed by the Action | 1.2.4, 1.1.2, 1.1.1, 3.1.2, 3.2.2, 3.2.1, 3.1.3, 3.1.1 |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Management Plan | Implement a plan for the fishery defining clear objectives for management, defining a stock assessment method and verifying the current status of the stock in relation to reference points. | IABS | NETUNO USA, UFPA, GPESCA, OCEANA, MPA | Apr 2016 | December 2026 | Export quota proposal accepted and adopted by Government |

## Additional Impacts

Additional Impacts: Federal Government Recovery Plan Emergency Action 3

| Action Number and Name | Adopt a preventive capture limit (quota) until other recovery measures are adopted |
| --- | --- |
| Action Goal | Quota proposed and tested |
| Action Description | During CPG (Permanent Management Committee) meeting in March 2025, members/participants approved a landing quota and a minimum size for the fishery. A 3.300 ton/yr (7,000,000 Lbs) quota and a 33 cm (13 inches) minimum furcal size were approved. To put in place this new HCR/HS an alert trigger point was proposed when landings achieve 80% and 90% of the quota. There was an expectation that the HCR/HS will become enforced for the next season May-Dec 2026 |
| Expected Completion Date | Dec 2026 |
| Priority | High |
| Estimated Cost | Government budget |
| Responsible Parties | MPA |
| Status Summary | Quota approved |
| Improvement Recommendation | Integrate with FIP Action 4 |

Additional Impacts: Federal Government Recovery Plan Emergency Action 4

| Action Number and Name | Resume activities of the North/Northeast Management Committee Demersal Resources (CPGs) |
| --- | --- |
| Action Goal | Management Committee reactivated |
| Action Description | Re-establish the Shared Management System for the Sustainable Use of Fisheries Resources, to provide input to the MMA and the MPA in the decision-making process on the sustainable use of fisheries resources and the conservation of biodiversity. |
| Expected Completion Date | March 2025 |
| Priority | High |
| Estimated Cost | Government budget |
| Responsible Parties | MPA |
| Status Summary | Discussions started but CPGs Committee meetings not resumed yet |
| Improvement Recommendation | Integrate with FIP Actions 3 and 4 |