Mexico upper Gulf of California corvina - hook & line

Fishery Improvement Project (FIP) Work Plan

Context:

In general, the main actions to improve the performance of the fishery in the Upper Gulf of California (1) are to establish a monitoring program, and (2) to define and formalize the objectives within the fishery management system.

Table 1: General description of the work plan

| Version and date of the work plan | April 2025 |  |
| --- | --- | --- |
| Start date (expected) | Completion date (expected month/year) |  |
| March 2025 | March 2027 |  |
| FIP Leader (organization/individual responsible for the Action Plan) | Improvements recommended by (meeting/group that supported the development) |  |
| Pronatura noroeste Noroeste AC | MRAG of the Americas |  |
| FIP Coordinator (organization/individual responsible for reporting on FisheryProgress) | Work plan developed by (consultant or individual) |  |
| Pronatura noroeste Noroeste AC | IFP Working Group |  |

Acronyms

| PNO | Pronatura Noroeste |
| --- | --- |
| CEDO | Intercultural Center for Desert and Ocean Studies. |
| ABC Fishing | Alternative Fishing of Baja California. A.C |
| IMIPAS | Regional Fisheries Research Center |
| SEPESCA | Secretariat of Fisheries and Aquaculture |
| IMIPAS | Mexican Institute of Fisheries and Aquaculture Research |
| UABC | Autonomous University of Baja California |
| IIO | Oceanological Research Institute |

Unit(s) of evaluation

Table 2. Unit(s) of Assessment (UoA)

| UoA 1 | Description |
| --- | --- |
| Target species (common and scientific name) | Silver croaker (Cynoscion parvipinnis) |
| Stocks | Upper Gulf of California, Mexico. |
| Geographical area | Area 77 (Pacific, East Central) |
| Fishing method or gear type | Line and hook |
| Fishing fleet or group of vessels, or individual fishery operators targeting stocks | Artisanal Fishing Vessels |

Table 3. Unit(s) of Assessment (UoA)

| UoA 2 | Description |
| --- | --- |
| Target species (common and scientific name) | Yellowfin croaker (Cynoscion xanthulus) |
| Stocks | Upper Gulf of California, Mexico. |
| Geographical area | Area 77 (Pacific, East Central) |
| Fishing method or gear type | Line and hook |
| Fishing fleet or group of vessels, or individual fishery operators targeting stocks | Artisanal Fishing Vessels |

Table 4. Unit(s) of Assessment (UoA)

| UoA 3 | Description |
| --- | --- |
| Target species (common and scientific name) | Northern white seabass (Micropogonias megalops) |
| Stocks | Upper Gulf of California, Mexico. |
| Geographical area | Area 77 (Pacific, East Central) |
| Fishing method or gear type | Line and hook |
| Fishing fleet or group of vessels, or individual fishery operators targeting stocks | Artisanal Fishing Vessels |

FIP Actions

Action Plan for Performance Indicators Action Table 5. Generate baseline information to develop an harvest strategy

| Number and name of share (One sentence description) | 1.-Generate baseline information to develop a harvest strategy. |
| --- | --- |
| Action objective (A sentence describing the result of the action) | Identify and implement an appropriate harvest strategy based on the best available information. |
| Action Description | The pre-assessment indicates that there is no harvest strategy for the three UoA. Also, Mexican fisheries legislation leads to the implementation of harvest strategies that can be included in a management plan and that should be linked to the reference points derived from the stock assessment for each indicator species. Therefore, the tasks of this action aim to fill this gap in the fishery according to the structure proposed by the MSC for the harvest strategy that will be harmonized with the elements of a management plan. To this end, an information and monitoring system will be developed to support the harvest strategy. |
| Planned completion date | March 2027 |
| Priority (Based on implementers' criteria: e.g., problems with the lowest score are high priority or actions that need to be completed before starting other actions are high priority). | High |
| Estimated cost (An estimate of the budget necessary to complete the action) | $ 30 000 USD |
| Responsible parties (List of participants) | IMIPAS, Pronatura noroeste Noroeste |
| MSC performance indicator(s) addressed by the action (MSC performance indicators that are directly affected by the action. Completion of the action is likely to result in an improved score change for these performance indicators). | 1.2.1 Harvest strategy. According to the vocabulary of the MSC standard "harvest strategy" corresponds to the "combination of monitoring, stock assessment, control rules and management actions". |

| Score issue a) Harvest strategy design | The harvest strategy is expected to achieve stock management objectives reflected in PI 1.1.1 SG80. The harvest strategy is responsive to the state of the stock and the elements of the harvest strategy work together towards achieving stock management objectives reflected in PI 1.1.1 SG80. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Score issue b) Harvest strategy evaluation | SG 60. The harvest strategy is likely to work based on prior experience or plausible argument. SG 80. The harvest strategy may not have been fully tested but evidence exists that it is achieving its objectives. |  |  |  |  |  |
| Score issue c) Harvest strategy monitoring | SG 60. Monitoring is in place that is expected to determine whether the harvest strategy is working. |  |  |  |  |  |
| Action | Tasks/Milestones | Responsible (leader) | Responsible (support function) | Start date | Planned completion date | Completion tests/results |
| 1. Develop exploitation strategy | 1.1 Develop the fishery monitoring system (see Table 4, which corresponds to indicator 1.2.3). | Pronatura Noroeste IMIPAS SEPESCA UABC IIO | ABC Fishing CEDO | April 2025 | March 2027 | Database |

Design and implement a standardized monitoring program with trained monitors to determine the population status of target species and identify the general trend of other species in the fishery.

| Number and name of share (One sentence description) | 2. Design and implement a standardized monitoring program with trained monitors to determine the population status of target species and identify the general trend of other non-target species in the fishery. |
| --- | --- |
| Action objective (A sentence describing the result of the action) | To have a monitoring program to follow and evaluate the permanence of the stocks of target species. |
| Action Description (Brief summary of the steps involved in the action and the importance of the action in achieving the objectives of the FIP) | Implement standardized monitoring program with trained monitors to determine the population status of indicator species and identify the general trend of other species in the fishery. |
| Planned completion date | March 2027 |
| Priority (Based on implementers' criteria: e.g., problems with the lowest score are high priority or actions that need to be completed before starting other actions are high priority). | - High |
| Estimated cost (An estimate of the budget necessary to complete the action) | $ 30 000 |
| Responsible parties (List of participants) | Pronatura noroeste, CEDO, Pesca ABC, IMIPAS |
| MSC performance indicator(s) addressed by the action (MSC performance indicators that are directly affected by the action. Completion of the action is likely to result in an improved score change for these performance indicators). | 1.2.3 - Information and monitoring 2.1.3 - Primary Species Information 2.2.3 - Secondary Species Information 2.4.3 - Habitat Information 2.5.3 - Ecosystem information |

| Indicator 1.2.3 | Score issue (a) Range of information | SG 60. Some relevant information related to stock structure, stock productivity and fleet composition is available to support the harvest strategy. SG 80. Sufficient relevant information related to stock structure, stock productivity, fleet composition and other data are available to support the harvest strategy. |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Score issue (b) Monitoring | Stock abundance and UoA removals are monitored and at least one indicator is available and monitored with sufficient frequency to support the harvest control rule. SG 80. Stock abundance and UoA removals are regularly monitored at a level of accuracy and coverage consistent with the harvest control rule, and one or more indicators are available and monitored with sufficient frequency to support the harvest |  |  |  |  |
|  | Score issue (c) Comprehensiveness of information | SG 80. There is good information on all other fishery removals from the stock. |  |  |  |  |
| Indicator 2.1.3 | Score issue (a) Information adequacy for assessment of impact on main primary species. | SG 60. If RBF is used to score PI 2.1.1 for the UoA: Qualitative information is adequate to estimate productivity and susceptibility attributes for main primary species. If RBF is used to score PI 2.1.1 for the UoA: Some quantitative information is adequate to assess productivity and susceptibility attributes for main primary species. |  |  |  |  |
|  | Score issue (c) Information adequacy for management strategy. | SG 60. Information is adequate to support measures to manage main primary species. SG 80 Information is adequate to support a strategy to manage all primary species and evaluate with a high degree of certainty whether the strategy is achieving its objective. |  |  |  |  |
| Indicator 2.2.3 | Score issue (a) Information adequacy for assessment of impact on main secondary species. | SG 60. If RBF is used to score PI 2.2.1 for the UoA: Qualitative information is adequate to estimate productivity and susceptibility attributes for main secondary species. If RBF is used to score PI 2.2.1 for the UoA: Some quantitative information is adequate to assess productivity and susceptibility attributes for main secondary species. |  |  |  |  |
|  | Score issue (c) Information adequacy for management strategy. | SG 60. Information is adequate to support measures to manage main secondary species. SG 80. Information is adequate to support a partial strategy to manage main secondary species. |  |  |  |  |
| Indicator 2.3.3 | Score issue (a) Information adequacy for assessment of impacts. | SG 60. If RBF is used to score PI 2.3.1 for the UoA: Qualitative information is adequate to estimate productivity and susceptibility attributes for ETP species. SG 80. If RBF is used to score PI 2.3.1 for the UoA: Some quantitative information is adequate to assess productivity and susceptibility attributes for ETP species. |  |  |  |  |
|  | Score issue (b) Information adequacy for management strategy. | SG 60. Information is adequate to support measures to manage the impacts on ETP species SG 80. Information is adequate to measure trends and support a strategy to manage impacts on ETP species. |  |  |  |  |
| Action | Tasks/Milestones | Responsible (leader) | Responsible (support function) | Start date | Planned completion date | Completion tests/results |
| 2. Design and implement a standardized monitoring program with trained monitors to determine the population status of the target species and identify the general trend of the other species in the fishery. | 2.1. Design a monitoring program to evaluate the composition of the fishing fleet. | Northwest Pronatura IMIPAS SEPESCA UABC IIO | Fishermen, CEDO, ABC Fisheries, MAREM | April 2025 | March 2027 | Standardized and updated follow-up program |
|  | 2.2. Improve information on fishing effort (in number and types of hooks, baits and effective fishing time). | Northwest Pronatura IMIPAS SEPESCA UABC IIO | Fishermen, CEDO, ABC Fisheries, MAREM | April 2025 | March 2027 | Analysis of fishing effort |
|  | 2.3. Record interactions and/or capture of non-target species in the monitoring program logbooks. | Northwest Pronatura IMIPAS SEPESCA UABC IIO | Fishermen, CEDO, ABC Fisheries, MAREM | April 2025 | March 2027 | Logbook with information section on ETP species; Communication Materials |

Establish a sound, transparent and permanent decision-making process in the multispecies fish fishery.

| Number and name of share (One sentence description) | 3. Establish a solid, transparent and permanent decision-making process in the multispecies fish fishery based on the precautionary principle. |
| --- | --- |
| Action objective (A sentence describing the result of the action) | To have decision-making processes in the development of measures and strategies aimed at meeting the objectives of the fishery, in a transparent manner and based on the precautionary principle. |
| Action Description (Brief summary of the steps involved in the action and importance of the action in achieving the objectives of the FIP) | As indicated in the pre-assessment report for indicator 3.2.1, there is no established management strategy and, therefore, no formal decision-making process. It is therefore intended to strengthen the Management Advisory Committee, in the case of this action, particularly in the decision-making process. |
| Planned completion date | March 2027 |
| Priority (Based on implementers' criteria: e.g., problems with the lowest score are high priority or actions that need to be completed before starting other actions are high priority). | High |
| Estimated cost (An estimate of the budget necessary to complete the action) | $ 3,000 USD |
| Responsible parties (List of participants) | Pronatura noroeste noroeste, CEDO, Pesca ABC |
| MSC performance indicator(s) addressed by the action (MSC performance indicators that are directly affected by the action. Completion of the action is likely to result in an improved score change for these performance indicators). | 3.2.2 Decision-making processes |

|  | Score issue (a) Decision-making processes |  | SG 60. There are some decision-making processes in place that result in measures and strategies to achieve the fishery-specific objectives. SG 80. There are established decision-making processes that result in measures and strategies to achieve the fishery-specific objectives. |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Score issue (b) Responsive-ness of decision-making processes |  | Decision-making processes respond to serious issues identified in relevant research, monitoring, evaluation and consultation, in a transparent, timely and adaptive manner and take some account of the wider implications of decisions. Decision-making processes respond to serious and other important issues identified in relevant research, monitoring, evaluation and consultation, in a transparent, timely and adaptive manner and take account of the wider implications of decisions. |  |  |  |  |  |
|  | Score issue (c) Use of precaution-ary approach |  | SG 80. Decision-making processes use the precautionary approach and are based on best available information. |  |  |  |  |  |
|  | Score issue (d) Account-ability and transparency of management system and decision-making process |  | SG 60. Some information on the fishery's performance and management action is generally available on request to stakeholders Information on the fishery's performance and management action is available on request, and explanations are provided for any actions or lack of action associated with findings and relevant recommendations emerging from research, monitoring evaluation and review activity. |  |  |  |  |  |
|  | Score issue (e) Approach to disputes |  | SG 60. Although the management authority or fishery may be subject to continuing court challenges, it is not indicating a disrespect or defiance of the law by repeatedly violating the same law or regulation necessary for the sustainability for the fishery. SG 80. The management system or fishery is attempting to comply in a timely fashion with judicial decisions arising from any legal challenges. |  |  |  |  |  |
| Action |  |  | Tasks/Milestones | Responsible (leader) | Responsible (support function) | Start date | Planned completion date | Completion tests/results |
|  | 3. Establish a fishery committee |  | 3.1 Identify the species comprising the fishery | IMIPAS SEPESCA Northwest Pronatura | Fishermen, CEDO, ABC Fisheries, MAREM | April 2025 | March 2027 | List of species of flake caught in the region |
|  | 3. Establish a fishery committee |  | 3.2 Determine and define the roles of the actors within the committee. | IMIPAS SEPESCA Northwest Pronatura | Fishermen, CEDO, ABC Fisheries, MAREM | April 2025 | March 2027 | Act of description of roles and responsibilities |
|  |  |  | 3.3 Define the committee's responsibilities and actions. | IMIPAS SEPESCA Northwest Pronatura | Fishermen, CEDO, ABC Fisheries, MAREM | April 2025 | March 2027 | Act of description of roles and responsibilities |
|  |  |  | 3.4 Train/inform the fishing sector on the responsibilities, benefits of the committee. | IMIPAS SEPESCA Northwest Pronatura | Fishermen, CEDO, ABC Fisheries, MAREM | April 2025 | March 2027 | Minutes of meetings in which the sector is trained |
|  |  |  | 3.5 Formalize the committee | IMIPAS SEPESCA Northwest Pronatura | Fishermen, CEDO, ABC Fisheries, MAREM | April 2025 | March 2027 | Formalize a regional fishery committee. |

Additional impacts

Some FIPs include objectives that go beyond the MSC IPs. Provide additional details below on additional impacts that FIP stakeholders are working to address.

| Social impact |  |
| --- | --- |
| Status summary |  |
| Recommendation for improvement |  |

| Supply Chain Roundtable | This FIP seeks to engage new buyers. |
| --- | --- |
| Status summary |  |
| Recommendation for improvement |  |

| Traceability |  |
| --- | --- |
| Status summary |  |
| Recommendation for improvement |  |

| Another |  |
| --- | --- |
| Status summary |  |
| Recommendation for improvement |  |