## India unicorn leatherjacket filefish - Trawl

## Fishery Improvement Project (FIP) Workplan

Table 1: Workplan Overview

| Workplan Version and Date |  |
| --- | --- |
| Start date (expected) | End date (anticipated month/year) |
| 11/15/2025 | 12/15/2027 |
| FIP Lead (organization/individual responsible for Action Plan) | Improvements recommended by (meeting/group that supported the development) |
| Netuno USA, Inc | IABS |
| FIP Coordinator (organization/individual responsible for reporting on FisheryProgress) | Workplan developed by (consultant or person) |
| Andre M. Brugger | Vineetha Aravind and Jo Gascoigne |

#### Acronyms

| FAO | Food and Agriculture Organization of the United Nations |
| --- | --- |
| NETFISH | Network for Fish Quality & Sustainable Fishing / MPEDA |
| MPEDA | Ministry of Commerce & Industry |
| CMFRI | Central Marine Fisheries Research Institute |
| FSI | Fishery Survey at India |
| SSNI | Sustainable Seafood Network of India |
| SEAI | Seafood Exporter Association of India |
| MSC | Marine Stewardship Council |
| DoFs | Department of Fisheries |
| CIFT | Central Institute of Fishery Technology |

#### Unit of Assessment(s)

Fill in the following table, which will be considered the scope against which the fishery is assessed against the MSC Fisheries Standard.

Table 2. Unit(s) of Assessment (UoA)

| UoA 1 | Description |
| --- | --- |
| Target species (common and scientific name) | Unicorn leatherjacket Aluterus monoceros |
| Stock | Southwestern India |
| Geographical area | The exclusive economic zone (EEZ) of India – Kerala State |
| Fishing method or gear type | Trawler |
| Fishing fleet or group of vessels, or individuals fishing operators pursuing stock | Multispecies mid water trawler |

Table 2. Unit(s) of Assessment (UoA)

| UoA 2 | Description |
| --- | --- |
| Target species (common and scientific name) | Unicorn leatherjacket Aluterus monoceros |
| Stock | Southwestern India |
| Geographical area | The exclusive economic zone (EEZ) of India – Karnataka State |
| Fishing method or gear type | Trawler |
| Fishing fleet or group of vessels, or individuals fishing operators pursuing stock | Multispecies mid water trawler |

## FIP Actions

Table 3. Performance Indicator Action Plan Table for Action 1. Stock structure and biology for unicorn leatherjacket

| Action Number and Name (One sentence description) | Stock structure and biology for unicorn leatherjacket |
| --- | --- |
| Action Goal (One sentence that describe the result of the action) | Understand the stock structure and biology for unicorn leatherjacket population |
| Action Description (Brief summary of the steps involved in the action and importance of the action in achieving the FIP objectives) | Obtain the data on A. monoceros biology, life history and stock structure which is needed for a basic but robust stock assessment |
| Expected Completion Date | December 2027 |
| Priority (Based on the implementers criteria: e.g., lowest scoring issues are high priority or actions that are necessary to complete before beginning other actions are high priority) | High |
| Estimated Cost (An estimate of the budget needed to complete the action) | $ 12,000 |
| Responsible Parties (List of participants) | IABS / Netuno USA / Neptune / Baraka and Indofisheries |
| MSC PI(s) Addressed by the Action | 1.2.3; pre-requisite for 1.2.4 and 1.1.1 |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Stock structure and biology for unicorn leatherjacket | Collate existing information about unicorn biology and life history, and evaluate gaps based on data required for data-deficient stock assessment options (Cmsy, SPiCT, LCA or others) | IABS / Netuno USA / Neptune / Baraka and Indofisheries | CMFRI/ Fisheries University / Relevant NGOs | November 2025 | December 2027 | Gap analysis of unicorn data in relation to different stock assessment techniques |
|  | Establish research project to fill gaps in knowledge about age and growth, mortality, reproduction, habitat etc. | CMFRI/ Fisheries University / IABS / Neptune / Baraka | Netuno USA, Indo Fisheries and Relevant NGOs | November 2025 | December 2027 | Contract with researcher(s), publications |
|  | Map likely distribution of unicorn in Kerala and Karnataka from habitat and fisher information | FSI/CMFRI/ Fisheries University / IABS / Neptune / Baraka | Netuno USA, Indo Fisheries and Relevant NGOs | November 2025 | December 2027 | Fisher interviews, maps |
|  | Test hypotheses about stock structure in Kerala and Karnataka using genetic or other information | CMFRI/ Fisheries University / IABS / Neptune / Baraka | Netuno USA, Indo Fisheries and Relevant NGOs | November 2025 | December 2027 | Recommendation for management unit(s) in Kerala and Karnataka |

Table 3. Performance Indicator Action Plan Table for Action 2. Risk assessment for main bycatch species

| Action Number and Name (One sentence description) | Risk assessment for main bycatch species |
| --- | --- |
| Action Goal (One sentence that describe the result of the action) | Assess the risk of endangered bycatch in the trawler fleet, especially sharks and marine mammals |
| Action Description (Brief summary of the steps involved in the action and importance of the action in achieving the FIP objectives) | Main bycatch species identified and risk to the populations from the fishery evaluated; measures identified to reduce risk where required |
| Expected Completion Date | December 2027 |
| Priority (Based on the implementers criteria: e.g., lowest scoring issues are high priority or actions that are necessary to complete before beginning other actions are high priority) | Medium |
| Estimated Cost (An estimate of the budget needed to complete the action) | $ 9,000 |
| Responsible Parties (List of participants) | IABS / Netuno USA / Neptune / Baraka and Indofisheries |
| MSC PI(s) Addressed by the Action | 2.2.1, 2.2.2, 2.2.3, 2.5.1, 2.5.2, 2.5.3 |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Risk assessment for main bycatch species | From catch profile data (above) generate a list of main bycatch species for the fishery | IABS / Netuno USA / Neptune / Baraka and Indofisheries | CMFRI / Fisheries University / CIFT, DoFs and Relevant NGOs | June 2026 | December 2027 | Catch profile and species list |
|  | Conduct risk assessments (PSAs) for the main bycatch species | FIPs / consultant | Netuno USA, Indo Fisheries and Relevant NGOs | June 2026 | December 2027 | PSA reports |
|  | For any species considered to be at ‘high risk’ from the fishery, evaluate options for management measures to reduce risk | CIFT / DoFs / CMFRI/ Fisheries University / IABS / Neptune / Baraka | Netuno USA, Indo Fisheries and Relevant NGOs | June 2026 | December 2027 | Research publications, workshops |
|  | Test and implement the measures, initially in the model fleet | CIFT / DoFs / CMFRI/ Fisheries University / IABS / Neptune / Baraka | Netuno USA, Indo Fisheries and Relevant NGOs | June 2026 | December 2027 | Measures being used on board |

## Additional Impacts

Some FIPs include objectives that go beyond the MSC PIs. Please provide additional detail below on additional impacts that FIP stakeholders are working to address.

### Example: Traceability improvements

Describe the problems, goals and actions that will be implemented to ensure FIP traceability.

| Addition Impact Title | Additional Impact Description |
| --- | --- |
| Status Summary |  |
| Improvement Recommendation |  |

[Copy and paste table as appropriate]