MSC Improvement Program

Marine Stewardship Council

# MSC Fishery Improvement Action Plan

Lake Winnipeg North Basin Walleye (Sander vitreus) & Lake Whitefish (Coregonus clupeaformis) Fisheries

Table of Contents

1	Improvement Action Plan Overview	3

1.1	Improvement Action Plan overview by Performance Indicator	6

2	Improvement actions and tasks at Performance Indicator and / or Scoring Issue level	8

3	Progress verification schedule	24

4	Performance Indicator draft score changes (Benchmarking and Tracking Tool)	25

5	Template information and copyright	31

Improvement Action Plan Overview

Table 1. Improvement Action Plan overview

| Fishery name or Unit/s of Assessment (UoA/s): | UoA 1: Walleye (Sander vitreus), North Basin _ UoA 2: Lake Whitefish (Coregonus clupeaformis), Grand Rapids UoA 3: Lake Whitefish (Coregonus clupeaformis), Mossy Bay UoA 4: Lake Whitefish (Coregonus clupeaformis), Poplar River UoA 5: Lake Whitefish (Coregonus clupeaformis), Dauphin River / Lake St. Martin | Fishery location: | UoA 1: North Basin of Lake Winnipeg, Manitoba, Canada UoA 2: Grand Rapids whitefish area of Lake Winnipeg, Manitoba, Canada UoA 3: Mossy Bay / Playgreen Lake whitefish area of Lake Winnipeg, Manitoba, Canada UoA 4: Poplar River whitefish area of Lake Winnipeg, Manitoba, Canada UoA 5: Dauphin River/Lake St. Martin whitefish area of Lake Winnipeg, Manitoba, Canada |
| --- | --- | --- | --- |
| Fishing gear type(s): | Set gillnets | Fishery in MSC Improvement Program? (Applicant/Yes/No): | Applicant |
| Does the fishery client intend to enter the UoA(s) into MSC full assessment (or in the case of a suspended MSC certificate enter the reinstatement process)? |  | Yes |  |
| If yes, please indicate which version of the MSC Fisheries Standard will be used for Full Assessment. |  | v3.1 |  |
| IAP Start date (expected): |  | MSC Improvement Program Completion Date (The expected date on which an Improvement Action Plan is completed, whereby the UoA(s) has/have achieved a draft scoring range equivalent to an MSC pass and a CAB has uploaded either an ACDR or a Surveillance Report to the MSC database as a means to ‘complete’ the MSC Improvement Program process) |  |
| 31/01/2026 |  | 31/01/2031 |  |
| Project leaders (organisation/individual responsible for IAP): |  | IAP and improvements supported by (stakeholder groups, organisations, or meetings that supported the development of the IAP): |  |
| Lake Winnipeg North Basin FIP Working Group |  | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Lake Winnipeg North Basin Community Licensing Areas 6, 7, 8, 9 - Manitoba Fisheries Branch - Indigenous Services Canada |  |
| FIP Coordinator / Improvement Program Project Manager (name, affiliation, and position if applicable): |  | Improvement Program Project Manager commits to: - Serve as the key contact between the CAB and the Applicant Fishery. - Coordinate the implementation of the Improvement Action Plan. - Collate all information necessary for Progress Verification, including compiling the Progress Reports and updating the IAP and BMT as relevant |  |
| Lake Winnipeg Indigenous Commercial Fishers Inc. plans to hire a FIP Coordinator in spring 2026. Interim coordination is managed collaboratively by: - Sam Murdock, Director of Operation, Fisher River Cree Nation - Erin Dunbar, Director, Manitoba Fisheries Branch - Bill Galbraith, Senior Resources Management Officer, Indigenous Services Canada - Suzanne Chiupka, Fisheries Certification Manager, Manitoba Fisheries Branch |  | These commitments will be assigned to the FIP Coordinator after April 1, 2026. In the interim, Suzanne Chiupka of Manitoba Fisheries Branch will coordinate the tasks listed above, in partnership with Lake Winnipeg Indigenous Commercial Fishers Inc, and Indigenous Services Canada. |  |
| Improvement Action Plan developed by (entity, consultant, or person): |  | Date when this Improvement Action Plan was created: |  |
| Developed by: Lake Winnipeg North Basin FIP Working Group Reviewed and approved by: LRQA |  | 12/12/2025 |  |
| Summary of the Improvement Action Plan: |  |  |  |
| Principle 1 – Coordinate stock rebuilding plans, develop harvest strategy, and introduce fisher logbooks. Principle 2 – Develop a fisheries management plan that addresses in-scope species, ETP/OOS species, and the ecosystem. Principle 3 – Develop a fisheries management plan that establishes processes for dispute resolution, transparent information-sharing and decision-making, internal and external review, and effective enforcement. |  |  |  |
| Stakeholder inputs into the Improvement Action Plan (Optional). If the IAP has been updated, include stakeholder updates if relevant. |  |  |  |
| - All Community Licensing Areas (6, 7, 8, 9) on Lake Winnipeg’s North Basin provided support to move from a Prospective FIP into a Comprehensive FIP by way of resolution submitted by the Lake Winnipeg Indigenous Commercial Fishers Inc. Board (2024) - Lake Winnipeg North Basin FIP Working Group (with representation from fishers, provincial government, and federal government) collaborated on the development of a five-year action plan, a two-year budget and compiled all information required to register a Comprehensive FIP (2025) |  |  |  |
| References: |  |  |  |
| - Lake Winnipeg Walleye (Sander vitreus), Sauger (Sander canadensis), and Lake Whitefish (Coregonus clupeaformis) Gillnet Fisheries Pre-Assessment Report (2024) - Lake Winnipeg North Basin FIP Action Plan (2025) - Lake Winnipeg North Basin MSC Benchmarking and Tracking Tool (2025) |  |  |  |
| Date/s of updated versions of this Improvement Action Plan: |  | n/a |  |

Improvement Action Plan overview by Performance Indicator

Table 2. Improvement Action Plan Overview by Performance Indicator – MSC Fisheries Standard v3.1

| Performance Indicator (PI) | Action ID and Name |  | Deadline |
| --- | --- | --- | --- |
| 1.1.1 - Stock status | 1.1.1 | Stock Status Improvement Plans | Complete |
| 1.1.2 - Stock rebuilding | 1.1.2 | Stock Rebuilding Plans | 31/01/2031 |
| 1.2.1 - Harvest Strategy | 1.2.1 | Harvest Strategy Evaluation | 31/01/2031 |
| 1.2.2 - Harvest control rules and tools | 1.2.2 | Harvest Control Rules and Tools | 31/01/2031 |
| 1.2.3 - Information and monitoring | 1.2.3 | Fisher Logbooks | 31/01/2031 |
| 2.1.2 - In-scope species management strategy | 2.1.2 | In-Scope Species Management Strategy | 31/01/2031 |
| 2.2.1 - ETP/OOS species outcome | 2.2.1 | ETP/OOS Species Outcome | 31/03/2030 |
| 2.2.2 - ETP/OOS species management strategy | 2.2.2 | ETP/OOS Species Strategy | 31/01/2031 |
| 2.2.3 - ETP/OOS species information | 2.2.3 | ETP/OOS Species Information | 31/01/2031 |
| 2.3.2 - Habitats management strategy | 2.3.2 | Report Lost Gear - Fishers | 31/03/2029 |
| 2.3.3 - Habitats information | 2.3.3 | Report Lost Gear - Fisheries Branch | 31/01/2031 |
| 2.4.2 - Ecosystem management strategy | 2.4.2 | Harvest Strategy Ecosystem Objectives | 31/03/2030 |
| 2.4.3 - Ecosystem information | 2.4.3 | Document Ecosystem Changes | 31/03/2029 |
| 3.1.1 - Legal and/or customary framework | 3.1.1 | Document Dispute Resolution | 31/03/2030 |
| 3.1.2 - Consultation, roles & responsibilities | 3.1.2 | Document Meeting Summaries | 31/03/2030 |
| 3.2.1 - Fishery-specific objectives | 3.2.1 | Fisheries Management Plan - Fishery-Specific Objectives | 31/03/2029 |
| 3.2.2 - Decision-making processes | 3.2.2 | Fisheries Management Plan - Decision-Making Framework | 31/01/2031 |
| 3.2.3 - Compliance & enforcement | 3.2.3 | Enforcement Strategy | 31/01/2031 |
| 3.2.4 - Monitoring and management performance evaluation | 3.2.4 | Evaluation Process | 31/01/2031 |

Improvement actions and tasks at Performance Indicator and / or Scoring Issue level

Table 3. Performance Indicator Action Plan Table for Action 1.1.1 - Stock Status Improvement Plans - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 1.1.1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Stock Status Improvement Plans |  |  |  |  |  |
| Action summary | Implement stock status improvement plans to maintain sustainable production and population recovery |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 1.1.1 Stock status (a) Stock status relative to recruitment impairment (b) Stock status in relation to achievement of maximum sustainable yield (MSY) |  |  |  |  |  |
| Deadline | Complete |  |  |  |  |  |
| Task No. | Responsible – Action Lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 1.1.1.i - Implement voluntary quota buy-back program | Manitoba Fisheries | - Manitoba Fisheries - Fishers | Not applicable | Not applicable | Complete | Complete |
| 1.1.1.ii - Implement a maximum mesh size | Manitoba Fisheries | - Manitoba Fisheries - Fishers | Not applicable | Not applicable | Complete | Complete |
| 1.1.1.iii - Pause the Lake Whitefish Optimization Program | Manitoba Fisheries | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Fishers | In-kind | Not applicable | Ongoing | Milestone 1 - Program is paused for five years (2024- 2029) |

Table 4. Performance Indicator Action Plan Table for Action 1.1.2 - Stock Rebuilding Plans - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 1.1.2 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Stock Rebuilding Plans |  |  |  |  |  |
| Action summary | Discuss, develop, implement and evaluate stock rebuilding plans for UoAs scoring below 80 |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 1.1.2 Stock Rebuilding (a) Rebuilding timeframes (b) Rebuilding evaluation |  |  |  |  |  |
| Deadline | 31/01/2031 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 1.1.2.i - Facilitate workshops with fisher representatives to discuss and develop options for stock rebuilding plans | Manitoba Fisheries | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Manitoba Fisheries - Fishers - Fish Buyers - Fisher Cooperatives - Indigenous Services Canada | $190,000 CAD Resources budgeted for workshops are also related to the following tasks: 1.2.2.i, 1.2.3.i, 2.1.2.i, 2.2.2.i, 2.2.2.ii, 2.2.2.iii, 2.2.3.i, 2.2.3.iii, 2.4.2.i, 3.2.2.i | 2026-2028 | 31/03/2029 | Milestone 1 – Year 1 - 3: Stock rebuilding plans are developed (2026-2028) |
| 1.1.2.ii - Implement stock rebuilding plan including fisheries management changes if required as per the plan | Manitoba Fisheries | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Manitoba Fisheries - Fishers - Fish Buyers - Fisher Cooperatives - Indigenous Services Canada | In-kind | 2029 | 31/03/2030 | Milestone 2 – Year 4: Stock rebuilding plans are implemented (2029) |
| 1.1.2.iii - Use performance measures to evaluate stock rebuilding plans | Manitoba Fisheries | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Manitoba Fisheries - Fishers - Fish Buyers - Fisher Cooperatives - Indigenous Services Canada | In-kind | 2030 | 31/01/2031 | Milestone 3 – Year 5: Stock rebuilding plans are evaluated (2030) |

Table 5. Performance Indicator Action Plan Table for Action 1.2.1 - Harvest Strategy Evaluation - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 1.2.1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Harvest Strategy Evaluation |  |  |  |  |  |
| Action summary | Evaluate harvest strategy to ensure it is robust and precautionary |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 1.2.1 Harvest Strategy (a) Harvest strategy design (b) Harvest strategy evaluation (d) Harvest strategy review |  |  |  |  |  |
| Deadline | 31/01/2031 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 1.2.1.i - Analyze stock assessment data against performance measures to evaluate effectiveness of the harvest strategy | Manitoba Fisheries | - Manitoba Fisheries - Fishers - Collaborative Stock Monitoring Program | In-kind | 2030 | 31/01/2031 | Milestone 1 – Year 5: Harvest strategy is evaluated (2030) |

Table 6. Performance Indicator Action Plan Table for Action 1.2.2 - Harvest Control Rules and Tools - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 1.2.2 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Harvest Control Rules and Tools |  |  |  |  |  |
| Action summary | Discuss, develop, implement and evaluate a harvest strategy that includes well-defined and effective harvest control rules (HCRs) |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 1.2.2 Harvest Control Rules and Tools (a) Harvest control rules design and application (b) Harvest control rules robustness to uncertainty (c) Harvest control rules evaluation |  |  |  |  |  |
| Deadline | 31/01/2031 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 1.2.2.i - Facilitate workshops with fisher representatives to discuss and develop harvest strategy options (HCRs - harvest control rules) | Manitoba Fisheries | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Manitoba Fisheries - Fishers - Fish Buyers - Fisher Cooperatives - Indigenous Services Canada | Resources for this task are listed under 1.1.2.i | 2026-2028 | 31/03/2029 | Milestone 1 – Year 1 - 3: A harvest strategy is developed (2026-2028) |
| 1.2.2.ii - Continue to collect stock assessment data to inform the implementation of the harvest control strategy | Manitoba Fisheries | - Manitoba Fisheries - Indigenous Services Canada - Collaborative Stock Monitoring Program | In-kind | 2026-2030 | 31/01/2031 | Milestone 2 – Year 1-5: Stock assessment data is collected (2025-2028) |
| 1.2.2.iii - Implement harvest control rules based on stock status | Manitoba Fisheries | - Manitoba Fisheries - Fishers | In-kind | 2029 | 31/03/2030 | Milestone 3 – Year 4: Harvest control rules as implemented as per the harvest strategy (2029) |

Table 7. Performance Indicator Action Plan Table for Action 1.2.3 - Fisher Logbooks - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 1.2.3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Fisher Logbooks |  |  |  |  |  |
| Action summary | Develop, implement and evaluate fisher logbooks to collect relevant information to support the harvest strategy |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 1.2.3 Information and Monitoring (c) Comprehensiveness of information |  |  |  |  |  |
| Deadline | 31/01/2031 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 1.2.3.i - Discuss and develop a process and template for fisher logbooks through facilitated meetings | Lake Winnipeg Indigenous Commercial Fishers Inc. | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Manitoba Fisheries - Fishers - Fish Buyers - Fisher Cooperatives - Indigenous Services Canada | Resources for this task are listed under 1.1.2.i | 2026-2027 | 31/03/2028 | Milestone 1 – Year 1 - 2: A template for logbooks is developed (2026-2027) |
| 1.2.3.ii - Implement pilot project for logbook implementation and update template based on feedback gathered | Lake Winnipeg Indigenous Commercial Fishers Inc. | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Fishers - Fisher Cooperatives | In-kind | 2028 | 31/03/2029 | Milestone 2 – Year 3: Logbooks are tested through a pilot project (2028) |
| 1.2.3.iii - Implement the use of fisher logbooks | Lake Winnipeg Indigenous Commercial Fishers Inc. | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Fishers - Fisher Cooperatives | In-kind | 2029 | 31/03/2030 | Milestone 3 – Year 4: Logbooks are implemented (2029) |
| 1.2.3.iv - Evaluate if fisher logbooks are effective at supplying information required to assess the harvest strategy | Manitoba Fisheries | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Manitoba Fisheries | In-kind | 2030 | 31/01/2031 | Milestone 4 – Year 5: Logbooks are evaluated (2030) |

Table 8. Performance Indicator Action Plan Table for Action 2.1.2 - In-Scope Species Management Strategy - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 2.1.2 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | In-Scope Species Management Strategy |  |  |  |  |  |
| Action summary | Develop, implement and evaluate a management strategy to maintain or not hinder rebuilding of in-scope species (northern pike, freshwater drum, white suckers, shorthead red horse) |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 2.1.2 Primary Species Management Strategy (a) Management strategy in place (b) Management strategy effectiveness (c) Review of alternative measures |  |  |  |  |  |
| Deadline | 31/01/2031 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 2.1.2.i - Discuss and develop an in-scope species management strategy | Manitoba Fisheries | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Manitoba Fisheries - Indigenous Services Canada | Resources for this task are listed under 1.1.2.i | 2026-2028 | 31/03/2029 | Milestone 1 – Year 1 - 3: An in-scope species management strategy is developed (2026-2028) |
| 2.1.2.ii - Implement the in-scope species management strategy | Manitoba Fisheries | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Manitoba Fisheries - Fishers | In-kind | 2029 | 31/03/2030 | Milestone 2 – Year 4: The in-scope species management strategy is implemented (2029) |
| 2.1.2.iii - Evaluate the effectiveness of the in-scope species strategy | Manitoba Fisheries | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Manitoba Fisheries - Academia | In-kind | 2030 | 31/01/2031 | Milestone 3 – Year 5: The in-scope species management strategy is evaluated (2030) |

Table 9. Performance Indicator Action Plan Table for Action 2.2.1 - ETP/OOS Species Outcome - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 2.2.1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | ETP/OOS Species Outcome |  |  |  |  |  |
| Action summary | Discuss and develop a process to collect information on ETP/OOS species to ensure the direct effects of the UoA do not hinder recovery of ETP/OOS species |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 2.2.1 ETP/OOS Species Outcome (a) Direct effects |  |  |  |  |  |
| Deadline | 31/03/2030 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 2.2.1.i - Incorporate information on ETP/OOS species in fisher logbooks | Lake Winnipeg Indigenous Commercial Fishers Inc. | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Manitoba Fisheries - Fishers | In-kind | 2028-2029 | 31/03/2030 | Milestone 1 – Year 3 - 4: Information on ETP/OOS species is included on fisher logbooks (2028-2029) |

Table 10. Performance Indicator Action Plan Table for Action 2.2.2 - ETP/OOS Species Strategy - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 2.2.2 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | ETP/OOS Species Strategy |  |  |  |  |  |
| Action summary | Develop, implement and evaluate a precautionary UoA management strategy to minimize and/or eliminate incidental catch of ETP/OOS species and ensure UoA does not hinder recovery of ETP/OOS species |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 2.2.2 ETP/OOS Species Management Strategy (a) Management strategy in place (b) Management strategy effectiveness (c) Review of alternative measures to minimise mortality of the ETP/OOS unit (e) Ghost gear management strategy |  |  |  |  |  |
| Deadline | 31/01/2031 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 2.2.2.i - Discuss and develop an ETP/OOS species strategy | Manitoba Fisheries | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Fisher Cooperatives - Fishers | Resources for this task are listed under 1.1.2.i | 2026-2028 | 31/03/2029 | Milestone 1 – Year 1 - 3: ETP/OOS species strategy is developed (2026-2028) |
| 2.2.2.ii - Implement the ETP/OOS species strategy | Manitoba Fisheries | - Manitoba Fisheries Lake Winnipeg Indigenous Commercial Fishers Inc. - Fishers | Resources for this task are listed under 1.1.2.i | 2029 | 31/03/2030 | Milestone 2 – Year 4: ETP/OOS species strategy is implemented (2029) |
| 2.2.2.iii - Evaluate the effectiveness of the ETP/OOS species strategy | Manitoba Fisheries | - Manitoba Fisheries - Academia - Indigenous Services Canada | Resources for this task are listed under 1.1.2.i | 2030 | 31/01/2031 | Milestone 3 – Year 5: ETP/OOS species strategy is evaluated (2030) |

Table 11. Performance Indicator Action Plan Table for Action 2.2.3 - ETP/OOS Species Information - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 2.2.3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | ETP/OOS Species Information |  |  |  |  |  |
| Action summary | Discuss and develop a process to collect information to determine the impact of the UoA of the ETP/OOS species and assess the effectiveness of management measures |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 2.2.3 ETP/OOS Species Information (b) Information adequacy for management strategy |  |  |  |  |  |
| Deadline | 31/01/2031 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 2.2.3.i - Incorporate information on ETP/OOS species in fisher logbooks | Lake Winnipeg Indigenous Commercial Fishers Inc. | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Fishers | Resources for this task are listed under 1.1.2.i | 2026-2027 | 31/03/2028 | Milestone 1 – Year 1 and 2: Template for fisher logbooks is developed (2026-2027) |
| 2.2.3.ii - Gather information on ETP/OOS species | Lake Winnipeg Indigenous Commercial Fishers Inc. | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Fishers | In-kind | 2028-2029 | 31/03/2030 | Milestone 2 – Years 3 and 4: Logbooks include information on ETP/OOS species (2028 - 2029) |
| 2.2.3.iii - Gather traditional knowledge on ETP/OOS species | Lake Winnipeg Indigenous Commercial Fishers Inc. | - Lake Winnipeg Indigenous Commercial Fishers Inc. - Fishers - Indigenous Services Canada | Resources for this task are listed under 1.1.2.i | 2030 | 31/01/2031 | Milestone 3 – Years 5: Information on ETP/OOS species from fishers and elders is gathered and documented (2030) |

Table 12. Performance Indicator Action Plan Table for Action 2.3.2 - Report Lost Gear - Fishers - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 2.3.2 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Report Lost Gear - Fishers |  |  |  |  |  |
| Action summary | Establish a process for fishers to report lost gear to ensure the UoA does not pose a risk of serious or irreversible harm to habitat |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 2.3.2 Habitats management strategy (d) Ghost gear management strategy |  |  |  |  |  |
| Deadline | 31/03/2029 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 2.3.2.i - Develop a process for fishers to report lost gear | Lake Winnipeg Indigenous Commercial Fishers Inc. | - Fishers - Manitoba Conservation Officer Service - Manitoba Fisheries - Indigenous Services Canada | $15,000 CAD | 2027-2028 | 31/03/2029 | Milestone 1 – Year 2 and 3: A process to report lost gear is established |

Table 13. Performance Indicator Action Plan Table for Action 2.3.3 - Report Lost Gear - Fisheries Branch - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 2.3.3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Report Lost Gear - Fisheries Branch |  |  |  |  |  |
| Action summary | Discuss and develop a process to collect and report information on ghost gear to determine the impact of the UoA on habitat, including changes over time |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 2.3.3 Habitats Information (b) Information adequacy for assessment of impacts |  |  |  |  |  |
| Deadline | 31/01/2031 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 2.3.3.i - Compile information on ghost gear through on-water patrols, public reports, programs, and reporting from fishers | Manitoba Fisheries | - Manitoba Fisheries - Manitoba Conservation Officer Service | In-kind | 2029-2030 | 31/01/2031 | Milestone 1 – Year 4 and 5: Information on ghost gear is compiled and documented (2029-2030) |

Table 14. Performance Indicator Action Plan Table for Action 2.4.2 - Harvest Strategy Ecosystem Objectives - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 2.4.2 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Harvest Strategy Ecosystem Objectives |  |  |  |  |  |
| Action summary | Document connections between the harvest strategy and ecosystems to ensure the UoA does not pose a risk of serious or irreversible harm to ecosystem structure and function |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 2.4.2 Ecosystem Management Strategy (a) Management strategy in place (b) Management strategy effectiveness |  |  |  |  |  |
| Deadline | 31/01/2031 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 2.4.2.i - Develop ecosystem objectives for the fishery and describe them in a written document (e.g. in the fisheries management plan) | Manitoba Fisheries | Manitoba Fisheries | Resources for this task are listed under 1.1.2.i | 2026-2028 | 31/03/2029 | Milestone 1 – Year 1 - 3: Ecosystem objectives are developed and documented (2026-2028) |
| 2.4.2.ii - Outline a process on how ecosystem indicators will be considered when making fisheries management decisions | Manitoba Fisheries | Manitoba Fisheries | In-kind | 2029-2030 | 31/01/2031 | Milestone 2 – Year 4 and 5: A process is documented on how ecosystem indicators will be considered when making fisheries management decisions (2029-2030) |

Table 15. Performance Indicator Action Plan Table for Action 2.4.3 - Document Ecosystem Changes - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 2.4.3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Document Ecosystem Changes |  |  |  |  |  |
| Action summary | Document history of ecosystem changes over time to build knowledge of the ecosystem and the main impacts of the UoAs on key ecosystem elements |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 2.4.3 Ecosystem information (b) Investigation of UoA impacts |  |  |  |  |  |
| Deadline | 31/03/2029 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 2.4.3.i - Compile information on the history of ecosystem changes and describe them in a written document, e.g. in a management plan | Manitoba Fisheries | Manitoba Fisheries | In-kind | 2026-2028 | 31/03/2029 | Milestone 1 – Years 1 - 3: A history of ecosystem changed is included in the fisheries management plan (2026-2028) |

Table 16. Performance Indicator Action Plan Table for Action 3.1.1 - Document Dispute Resolution - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 3.1.1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Document Dispute Resolution |  |  |  |  |  |
| Action summary | Document dispute resolution to demonstrate the management system incorporates an appropriate dispute resolution framework |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 3.1.1 Legal and/or Customary Framework (b) Resolution of disputes |  |  |  |  |  |
| Deadline | 31/03/2030 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 3.1.1.i - Compile a summary of processes related to disputes such as suspension appeals, licensing disputes, etc. | Manitoba Fisheries | Manitoba Fisheries | In-kind | 2028-2029 | 31/03/2030 | Milestone 1 – Years 3-4: A summary of disputes is documented (2028-2029) |

Table 17. Performance Indicator Action Plan Table for Action 3.1.2 - Document Meeting Summaries - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 3.1.2 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Document Meeting Summaries |  |  |  |  |  |
| Action summary | Document meetings between management agency and fishers to demonstrate open, effective and transparent consultation processes |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 3.1.2 Consultation, Roles and Responsibilities (a) Roles and responsibilities (b) Consultation process |  |  |  |  |  |
| Deadline | 31/03/2030 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 3.1.2.i - Compile and publicly post meeting summaries / minutes from meetings between fishers and Manitoba Fisheries | Manitoba Fisheries | - Manitoba Fisheries - Lake Winnipeg Indigenous Commercial Fishers Inc. | $4,000 CAD | 2028-2029 | 31/03/2030 | Milestone 1 – Years 3-4: Meeting summaries / minutes are documented and posted online (2028-2029) |

Table 18. Performance Indicator Action Plan Table for Action 3.2.1 - Fisheries Management Plan - Fishery-Specific Objectives - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 3.2.1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Fisheries Management Plan - Fishery-Specific Objectives |  |  |  |  |  |
| Action summary | Develop and document fisheries-specific objectives in a fisheries management plan to achieve outcomes expressed by MSC Principles 1 and 2 |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 3.2.1 Fishery-specific objectives (a) Objectives |  |  |  |  |  |
| Deadline | 31/03/2029 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 3.2.1.i - Incorporate fisheries specific objectives within the fisheries management plan | Manitoba Fisheries | - Manitoba Fisheries - Lake Winnipeg Indigenous Commercial Fishers Inc. | $55,000 CAD | 2028 | 31/03/2029 | Milestone 1 – Years 3: Fisheries specific objectives are documented within the fisheries management plan (2028) |

Table 19. Performance Indicator Action Plan Table for Action 3.2.2 - Fisheries Management Plan - Decision-Making Framework - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 3.2.2 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Fisheries Management Plan - Decision-Making Framework |  |  |  |  |  |
| Action summary | Develop a responsive and transparent decision-making framework to achieve fishery-specific objectives and resolve disputes in a timely manner |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 3.2.2 - Decision-making processes (a) Decision-making processes (b) Responsiveness of decision-making processes (c) Use of precautionary approach (d) Accountability and transparency of management system and decision-making process (e) Approach to disputes |  |  |  |  |  |
| Deadline | 31/01/2031 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 3.2.2.i - Document how fisheries specific objectives are considered when making fisheries management decisions | Manitoba Fisheries | - Manitoba Fisheries - Lake Winnipeg Indigenous Commercial Fishers Inc. | Resources for this task are listed under 1.1.2.i | 2029-2030 | 31/01/2031 | Milestone 1 – Year 4 and 5: A process is documented on how fisheries specific objectives will be considered when making fisheries management decisions (2029-2030) |

Table 20. Performance Indicator Action Plan Table for Action 3.2.3 - Enforcement Strategy - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 3.2.3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Enforcement Strategy |  |  |  |  |  |
| Action summary | Develop and implement an enforcement strategy to ensure the UoAs comply with management measures |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 3.2.3 Compliance and Enforcement (c) Compliance (information) (d) Compliance (outcome) |  |  |  |  |  |
| Deadline | 31/01/2031 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 3.2.3.i - Discuss and develop an enforcement strategy | Manitoba Conservation Officer Service | - Manitoba Conservation Officer Service - Manitoba Fisheries | $4,000 CAD | 2026-2027 | 31/03/2028 | Milestone 1 – Year 1 and 2: An enforcement strategy is developed (2026-2027) |
| 3.2.3.ii - Implement enforcement strategy and document patrols | Manitoba Conservation Officer Service | - Manitoba Conservation Officer Service - Manitoba Fisheries | In-kind | 2028 | 31/03/2029 | Milestone 2 – Year 3 (2028) |
| 3.2.3.iii - Evaluate effectiveness of the enforcement strategy | Manitoba Conservation Officer Service | - Manitoba Conservation Officer Service - Manitoba Fisheries | In-kind | 2029-2030 | 31/01/2031 | Milestone 3 – Year 4 and 5 (2029-2030) |

Table 21. Performance Indicator Action Plan Table for Action 3.2.4 - Evaluation Process - UoA1 (North Basin Walleye), UoA2 (Grand Rapids Lake Whitefish), UoA3 (Mossy Bay Lake Whitefish), UoA4 (Poplar River Lake Whitefish), UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Action ID no | 3.2.4 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Evaluation Process |  |  |  |  |  |
| Action summary | Establish regular internal and external evaluation processes to ensure effective and timely review of the management system |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | 3.2.4 Monitoring and Management Performance Evaluation (a) Evaluation coverage (b) Internal and/or external review |  |  |  |  |  |
| Deadline | 31/01/2031 |  |  |  |  |  |
| Task No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources – Time | Deadline | Evidence of implementation |
| 3.2.4.i - Develop a process for reviewing the management system and its objectives | Manitoba Fisheries | Manitoba Fisheries | $6,000 CAD | 2026-2027 | 31/03/2028 | Milestone 1 – Years 1 and 2: Develop a process for internal and external reviews (2026 - 2027) |
| 3.2.4.ii - Implement internal review process | Manitoba Fisheries | Manitoba Fisheries | In-kind | 2028-2029 | 31/03/2030 | Milestone 2 – Year 3 and 4: Conduct internal review of stock assessments and fisheries management plan (2028-2029) |
| 3.2.4.iii - Implement external review process | Manitoba Fisheries | Manitoba Fisheries | In-kind | 2030 | 31/01/2031 | Milestone 3 – Year 5: Conduct external review of stock assessments and fisheries management plan (2030) |

Progress verification schedule

Table 23. Progress Verification Schedule

| Progress verification | Proposed date | Onsite or offsite | Improvement actions to be verified | Performance Indicators with improved draft scoring range |
| --- | --- | --- | --- | --- |
| Year 1 | 31/03/2027 | Offsite | 1.1.2 - Stock Rebuilding Plans - UoA1, UoA2, UoA3, UoA5 | The fishery will verify progress on actions that start in Year One (2026), but PI scores are not anticipated to improve in Year One. |
|  |  |  | 1.2.2 - Harvest Control Rules and Tools - UoA1, UoA2, UoA3, UoA4, UoA5 |  |
|  |  |  | 1.2.3 - Fisher Logbooks - UoA1, UoA2, UoA3, UoA4, UoA5 |  |
|  |  |  | 2.1.2 - In-Scope Species Management Strategy - UoA1, UoA2, UoA3, UoA4, UoA5 |  |
|  |  |  | 2.2.2 - ETP/OOS Species Strategy - UoA1, UoA2, UoA3, UoA4, UoA5 |  |
|  |  |  | 2.2.3 - ETP/OOS Species Information - UoA1, UoA2, UoA3, UoA4, UoA5 |  |
|  |  |  | 2.4.2 - Harvest Strategy Ecosystem Objectives - UoA1, UoA2, UoA3, UoA4, UoA5 |  |
|  |  |  | 2.4.3 - Document Ecosystem Changes - UoA1, UoA2, UoA3, UoA4, UoA5 |  |
|  |  |  | 3.2.3 - Enforcement Strategy - UoA1, UoA2, UoA3, UoA4, UoA5 |  |
|  |  |  | 3.2.4 - Evaluation Process - UoA1, UoA2, UoA3, UoA4, UoA5 |  |
| Year 2 | 31/03/2028 | Offsite | 3.2.4 - Evaluation Process - UoA1, UoA2, UoA3, UoA4, UoA5 | 3.2.4 Monitoring and Management Performance Evaluation |
| Year 3 | 31/03/2029 | Onsite | 1.1.2 - Stock Rebuilding Plans - UoA1, UoA2, UoA3, UoA5 | 1.2.2 Harvest Control Rules and Tools |
|  |  |  | 1.2.1 - Harvest Strategy Evaluation - UoA1, UoA2, UoA3, UoA4, UoA5 | 2.2.1 ETP/OOS Species Outcome |
|  |  |  | 2.2.3 - ETP/OOS Species Information - UoA1, UoA2, UoA3, UoA4, UoA5 | 2.2.3 ETP/OOS Species Information |
|  |  |  | 2.4.3 - Document Ecosystem Changes - UoA1, UoA2, UoA3, UoA4, UoA5 | 2.4.3 Ecosystem information |
|  |  |  | 3.2.1 - Fisheries Management Plan - Fishery-Specific Objectives - UoA1, UoA2, UoA3, UoA4, UoA5 | 3.2.1 Fishery-specific objectives |
| Year 4 | 31/03/2030 | Offsite | 1.2.2 - Harvest Control Rules and Tools - UoA1, UoA2, UoA3, UoA4, UoA5 | 1.2.2 Harvest Control Rules and Tools |
|  |  |  | 2.1.2 - In-Scope Species Management Strategy - UoA1, UoA2, UoA3, UoA4, UoA5 | 2.1.2 Primary Species Management Strategy |
|  |  |  | 2.2.1 - ETP/OOS Species Outcome - UoA1, UoA2, UoA3, UoA4, UoA5 | 2.2.1 ETP/OOS Species Outcome |
|  |  |  | 3.1.1 - Document Dispute Resolution - UoA1, UoA2, UoA3, UoA4, UoA5 | 3.1.1 Legal and/or Customary Framework |
|  |  |  | 3.1.2 - Document Meeting Summaries - UoA1, UoA2, UoA3, UoA4, UoA5 | 3.1.2 Consultation, Roles and Responsibilities |
| Year 5 | 31/01/2031 | Offsite | 1.1.1 - Stock Status Improvement Plans - UoA1, UoA2, UoA3, UoA5 | 1.1.1 Stock status |
|  |  |  | 1.1.2 - Stock Rebuilding Plans - UoA1, UoA2, UoA3, UoA5 | 1.1.2 Stock Rebuilding |
|  |  |  | 1.2.1 - Harvest Strategy Evaluation - UoA1, UoA2, UoA3, UoA4, UoA5 | 1.2.1 Harvest Strategy |
|  |  |  | 1.2.3 - Fisher Logbooks - UoA1, UoA2, UoA3, UoA4, UoA5 | 1.2.3 Information and Monitoring |
|  |  |  | 2.1.2 - In-Scope Species Management Strategy - UoA1, UoA2, UoA3, UoA4, UoA5 | 2.1.2 Primary Species Management Strategy |
|  |  |  | 2.2.2 - ETP/OOS Species Strategy - UoA1, UoA2, UoA3, UoA4, UoA5 | 2.2.2 ETP/OOS Species Management Strategy |
|  |  |  | 2.2.3 - ETP/OOS Species Information - UoA1, UoA2, UoA3, UoA4, UoA5 | 2.2.3 ETP/OOS Species Information |
|  |  |  | 2.3.3 - Report Lost Gear - Fisheries Branch - UoA1, UoA2, UoA3, UoA4, UoA5 | 2.3.3 Habitats Information |
|  |  |  | 2.4.2 - Harvest Strategy Ecosystem Objectives - UoA1, UoA2, UoA3, UoA4, UoA5 | 2.4.2 Ecosystem Management Strategy |
|  |  |  | 3.2.2 - Fisheries Management Plan - Decision-Making Framework - UoA1, UoA2, UoA3, UoA4, UoA5 | 3.2.2 - Decision-making processes |
|  |  |  | 3.2.3 - Enforcement Strategy - UoA1, UoA2, UoA3, UoA4, UoA5 | 3.2.3 Compliance and Enforcement |
|  |  |  | 3.2.4 - Evaluation Process - UoA1, UoA2, UoA3, UoA4, UoA5 | 3.2.4 Monitoring and Management Performance Evaluation |

Performance Indicator draft score changes (Benchmarking and Tracking Tool)

Table 24. Benchmarking and Tracking Tool (BMT) – UoA1 (North Basin Walleye)

| Principle | Component |  | Performance Indicator (PI) |  |  | Pre-Assessment Year 0 | Actual Year 1 | Actual Year 2 | Actual Year 3 | Actual Year 4 | Actual Year 5 |  | Expected Year 1 | Expected Year 2 | Expected Year 3 | Expected Year 4 | Expected Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Outcome |  | 1.1.1 Stock status |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  |  | 1.1.2 Stock rebuilding |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  | Management |  | 1.2.1 Harvest Strategy |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  |  |  | 1.2.2 Harvest control rules and tools |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | <60 | ≥80 | ≥80 |
|  |  |  | 1.2.3 Information / monitoring |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  |  | 1.2.4 Assessment of stock status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
| 2 | In-scope species |  | 2.1.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  |  | 2.1.2 Management strategy |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | <60 | 60-79 | ≥80 |
|  |  |  | 2.1.3 Information |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  | ETP/OOS species |  | 2.2.1 Outcome status |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  |  | 2.2.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  |  | 2.2.3 Information |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  | Habitats |  | 2.3.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  |  | 2.3.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
|  |  |  | 2.3.3 Information |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  | Ecosystem |  | 2.4.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  |  | 2.4.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  |  | 2.4.3 Information |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
| 3 | Governance and Policy |  | 3.1.1 Legal and/or customary framework |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  |  | 3.1.2 Consultation, roles and responsibilities |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  |  | 3.1.3 Long term objectives |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  | Fishery-specific management system |  | 3.2.1 Fishery-specific objectives |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
|  |  |  | 3.2.2 Decision-making processes |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  |  | 3.2.3 Compliance and enforcement |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  |  | 3.2.4 Monitoring and management performance evaluation |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | 60-79 | 60-79 | 60-79 | ≥80 |
| Total number of PIs equal to or greater than 80 |  |  |  |  |  | 6 |  |  |  |  |  |  | 6 | 6 | 9 | 13 | 25 |
| Total number of PIs 60-79 |  |  |  |  |  | 13 |  |  |  |  |  |  | 13 | 14 | 14 | 12 | 0 |
| Total number of PIs less than 60 |  |  |  |  |  | 6 |  |  |  |  |  |  | 6 | 5 | 2 |  |  |
| Overall BMT Index |  |  |  |  |  | 0.50 |  |  |  |  |  |  | 0.50 | 0.52 | 0.64 | 0.76 | 1.00 |

Table 25. Benchmarking and Tracking Tool (BMT) – UoA2 (Grand Rapids Lake Whitefish)

| Principle | Component | Performance Indicator (PI) |  |  | Pre-Assessment Year 0 | Actual Year 1 | Actual Year 2 | Actual Year 3 | Actual Year 4 | Actual Year 5 |  | Expected Year 1 | Expected Year 2 | Expected Year 3 | Expected Year 4 | Expected Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Outcome | 1.1.1 Stock status |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 1.1.2 Stock rebuilding |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  | Management | 1.2.1 Harvest Strategy |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  |  | 1.2.2 Harvest control rules and tools |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | <60 | ≥80 | ≥80 |
|  |  | 1.2.3 Information / monitoring |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 1.2.4 Assessment of stock status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
| 2 | In-scope species | 2.1.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 2.1.2 Management strategy |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | <60 | 60-79 | ≥80 |
|  |  | 2.1.3 Information |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  | ETP/OOS species | 2.2.1 Outcome status |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  | 2.2.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 2.2.3 Information |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  | Habitats | 2.3.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 2.3.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
|  |  | 2.3.3 Information |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  | Ecosystem | 2.4.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 2.4.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 2.4.3 Information |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
| 3 | Governance and Policy | 3.1.1 Legal and/or customary framework |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  | 3.1.2 Consultation, roles and responsibilities |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  | 3.1.3 Long term objectives |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  | Fishery-specific management system | 3.2.1 Fishery-specific objectives |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
|  |  | 3.2.2 Decision-making processes |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 3.2.3 Compliance and enforcement |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 3.2.4 Monitoring and management performance evaluation |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | 60-79 | 60-79 | 60-79 | ≥80 |
| Total number of PIs equal to or greater than 80 |  |  |  |  | 6 |  |  |  |  |  |  | 6 | 6 | 9 | 13 | 25 |
| Total number of PIs 60-79 |  |  |  |  | 13 |  |  |  |  |  |  | 13 | 14 | 14 | 12 | 0 |
| Total number of PIs less than 60 |  |  |  |  | 6 |  |  |  |  |  |  | 6 | 5 | 2 |  |  |
| Overall BMT Index |  |  |  |  | 0.50 |  |  |  |  |  |  | 0.50 | 0.52 | 0.64 | 0.76 | 1.00 |

Table 26. Benchmarking and Tracking Tool (BMT) – UoA3 (Mossy Bay Lake Whitefish)

| Principle | Component | Performance Indicator (PI) |  |  | Pre-Assessment Year 0 | Actual Year 1 | Actual Year 2 | Actual Year 3 | Actual Year 4 | Actual Year 5 |  | Expected Year 1 | Expected Year 2 | Expected Year 3 | Expected Year 4 | Expected Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Outcome | 1.1.1 Stock status |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 1.1.2 Stock rebuilding |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  | Management | 1.2.1 Harvest Strategy |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  |  | 1.2.2 Harvest control rules and tools |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | <60 | ≥80 | ≥80 |
|  |  | 1.2.3 Information / monitoring |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 1.2.4 Assessment of stock status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
| 2 | In-scope species | 2.1.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 2.1.2 Management strategy |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | <60 | 60-79 | ≥80 |
|  |  | 2.1.3 Information |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  | ETP/OOS species | 2.2.1 Outcome status |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  | 2.2.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 2.2.3 Information |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  | Habitats | 2.3.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 2.3.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
|  |  | 2.3.3 Information |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  | Ecosystem | 2.4.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 2.4.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 2.4.3 Information |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
| 3 | Governance and Policy | 3.1.1 Legal and/or customary framework |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  | 3.1.2 Consultation, roles and responsibilities |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  | 3.1.3 Long term objectives |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  | Fishery-specific management system | 3.2.1 Fishery-specific objectives |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
|  |  | 3.2.2 Decision-making processes |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 3.2.3 Compliance and enforcement |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 3.2.4 Monitoring and management performance evaluation |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | 60-79 | 60-79 | 60-79 | ≥80 |
| Total number of PIs equal to or greater than 80 |  |  |  |  | 6 |  |  |  |  |  |  | 6 | 6 | 9 | 13 | 25 |
| Total number of PIs 60-79 |  |  |  |  | 13 |  |  |  |  |  |  | 13 | 14 | 14 | 12 | 0 |
| Total number of PIs less than 60 |  |  |  |  | 6 |  |  |  |  |  |  | 6 | 5 | 2 |  |  |
| Overall BMT Index |  |  |  |  | 0.50 |  |  |  |  |  |  | 0.50 | 0.52 | 0.64 | 0.76 | 1.00 |

Table 27. Benchmarking and Tracking Tool (BMT) – UoA4 (Poplar River Lake Whitefish)

| Principle | Component | Performance Indicator (PI) |  |  | Pre-Assessment Year 0 | Actual Year 1 | Actual Year 2 | Actual Year 3 | Actual Year 4 | Actual Year 5 |  | Expected Year 1 | Expected Year 2 | Expected Year 3 | Expected Year 4 | Expected Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Outcome | 1.1.1 Stock status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 1.1.2 Stock rebuilding |  |  | --- | --- | --- | --- | --- | --- |  | --- | --- | --- | --- | --- |
|  | Management | 1.2.1 Harvest Strategy |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  |  | 1.2.2 Harvest control rules and tools |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | <60 | ≥80 | ≥80 |
|  |  | 1.2.3 Information / monitoring |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 1.2.4 Assessment of stock status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
| 2 | In-scope species | 2.1.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 2.1.2 Management strategy |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | <60 | 60-79 | ≥80 |
|  |  | 2.1.3 Information |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  | ETP/OOS species | 2.2.1 Outcome status |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  | 2.2.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 2.2.3 Information |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  | Habitats | 2.3.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 2.3.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
|  |  | 2.3.3 Information |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  | Ecosystem | 2.4.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 2.4.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 2.4.3 Information |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
| 3 | Governance and Policy | 3.1.1 Legal and/or customary framework |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  | 3.1.2 Consultation, roles and responsibilities |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  | 3.1.3 Long term objectives |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  | Fishery-specific management system | 3.2.1 Fishery-specific objectives |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
|  |  | 3.2.2 Decision-making processes |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 3.2.3 Compliance and enforcement |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 3.2.4 Monitoring and management performance evaluation |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | 60-79 | 60-79 | 60-79 | ≥80 |
| Total number of PIs equal to or greater than 80 |  |  |  |  | 7 |  |  |  |  |  |  | 7 | 7 | 10 | 14 | 24 |
| Total number of PIs 60-79 |  |  |  |  | 12 |  |  |  |  |  |  | 12 | 13 | 12 | 10 | 0 |
| Total number of PIs less than 60 |  |  |  |  | 5 |  |  |  |  |  |  | 5 | 4 | 2 |  |  |
| Overall BMT Index |  |  |  |  | 0.54 |  |  |  |  |  |  | 0.54 | 0.56 | 0.67 | 0.79 | 1.00 |

Table 28. Benchmarking and Tracking Tool (BMT) – UoA5 (Dauphin River / Lake St. Martin Lake Whitefish)

| Principle | Component | Performance Indicator (PI) |  |  | Pre-Assessment Year 0 | Actual Year 1 | Actual Year 2 | Actual Year 3 | Actual Year 4 | Actual Year 5 |  | Expected Year 1 | Expected Year 2 | Expected Year 3 | Expected Year 4 | Expected Year 5 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Outcome | 1.1.1 Stock status |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 1.1.2 Stock rebuilding |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  | Management | 1.2.1 Harvest Strategy |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  |  | 1.2.2 Harvest control rules and tools |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | <60 | ≥80 | ≥80 |
|  |  | 1.2.3 Information / monitoring |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 1.2.4 Assessment of stock status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
| 2 | In-scope species | 2.1.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 2.1.2 Management strategy |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | <60 | 60-79 | ≥80 |
|  |  | 2.1.3 Information |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  | ETP/OOS species | 2.2.1 Outcome status |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  | 2.2.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 2.2.3 Information |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | <60 | 60-79 | 60-79 | ≥80 |
|  | Habitats | 2.3.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 2.3.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
|  |  | 2.3.3 Information |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  | Ecosystem | 2.4.1 Outcome status |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  |  | 2.4.2 Management strategy |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 2.4.3 Information |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
| 3 | Governance and Policy | 3.1.1 Legal and/or customary framework |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  | 3.1.2 Consultation, roles and responsibilities |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | ≥80 | ≥80 |
|  |  | 3.1.3 Long term objectives |  |  | ≥80 | --- | --- | --- | --- | --- |  | ≥80 | ≥80 | ≥80 | ≥80 | ≥80 |
|  | Fishery-specific management system | 3.2.1 Fishery-specific objectives |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | ≥80 | ≥80 | ≥80 |
|  |  | 3.2.2 Decision-making processes |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 3.2.3 Compliance and enforcement |  |  | 60-79 | --- | --- | --- | --- | --- |  | 60-79 | 60-79 | 60-79 | 60-79 | ≥80 |
|  |  | 3.2.4 Monitoring and management performance evaluation |  |  | <60 | --- | --- | --- | --- | --- |  | <60 | 60-79 | 60-79 | 60-79 | ≥80 |
| Total number of PIs equal to or greater than 80 |  |  |  |  | 6 |  |  |  |  |  |  | 6 | 6 | 9 | 13 | 25 |
| Total number of PIs 60-79 |  |  |  |  | 13 |  |  |  |  |  |  | 13 | 14 | 14 | 12 | 0 |
| Total number of PIs less than 60 |  |  |  |  | 6 |  |  |  |  |  |  | 6 | 5 | 2 |  |  |
| Overall BMT Index |  |  |  |  | 0.50 |  |  |  |  |  |  | 0.50 | 0.52 | 0.64 | 0.76 | 1.00 |

Template information and copyright

The Marine Stewardship Council “MSC Fishery Improvement Action Plan Reporting Template v4.0” and its content is copyright of “Marine Stewardship Council” - © “Marine Stewardship Council” 2024. All rights reserved.

Delete the table below.

Table 32. Template Version Control

| Version | Date of publication | Document name | Description of amendment |
| --- | --- | --- | --- |
| 1.0 | 07/10/2009 | msc-fishery-improvement-action-plan-template.xlsx | - N/A – new document |
| 1.0 | 2013 | msc-fishery-improvement-action-plan-overview-template.docx | - N/A – new document |
| 1.0 | 22/11/2013 | Fisheries Improvement Action Plan Template.docx | - N/A – new document |
| 2.0 | 30/09/2019 | ITM Fisheries Improvement Action Plan Template.docx | - Combination of v1.0 overview and reporting templates in single document, specifically for ITM |
| 2.1 | 23/07/2020 | MSC Fisheries Improvement Action Plan Template.docx | - Template updated to be applicable to all FIPs not just ITM. - Contact email changed from standards@msc.org to fisheries@msc.org - BMT hyperlink updated. - Introduction and Overview updated - Version tracker added. - Added additional scheme document table. |
| 2.2 | 25/02/2021 | msc-fishery-improvement-action-plan-template-v2.2-2021.docx | - Some edits to Introduction and modified guidance below. - Added fields for Date of Action Plan creation and updates. - Moved version tracker and scheme document table to end of document. - Edit to note in Table 2 relating to PI 1.1.1(a) - Added example draft scoring ranges with coloured fill to tables 4a, b, c. - Other minor edits to stakeholder action plan section - Added Traceability action plan section. |
| 3.0 | 01/05/2023 | MSC Fishery Improvement Action Plan Reporting Template v3.0.docx | - Updated to align with MSC ITM Program Requirements and Guidance – Pilot v2.0 and Fisheries Certification Process 2.3/3.0. Performance indicators for MSC Fisheries Standard v3.0 added. |
| 4.0 | 29/10/2024 | MSC Fishery Improvement Action Plan Reporting Template v4.0.docx | - Updated to align with MSC Improvement Program Requirements and Guidance v3.0, Fisheries Standard v3.1 and traceability has been added. |

Marine Stewardship Council

Marine House

1 Snow Hill

London EC1A 2DH

United Kingdom

Phone: + 44 (0) 20 7246 8900

Fax: + 44 (0) 20 7246 8901

Email:   fisheries@msc.org