Mexico Gulf of Mexico finfish - vertical and bottom longline.

## Fishery Improvement Project (FIP)

## Workplan

Table 1: Workplan Overview

| Workplan Version and Date | Version 1.0 (based on PA Results) |
| --- | --- |
| Start date (expected) | End date (anticipated month/year) |
| August 2024 | December 2027 |
| FIP Lead (organization/individual responsible for Action Plan) | Improvements recommended by (meeting/group that supported the development) |
| Comunidad y Biodiversidad, A.C. (COBI) | Ocean outocomes (O2) |
| FIP Coordinator (organization/individual responsible for reporting on FisheryProgress) | Workplan developed by (consultant or person) |
| Lorena Rocha | Ocean outocomes (O2) |

#### Unit of Assessment(s)

Table 2. Unit(s) of Assessment (UoA)

| UoA 1 | Description |
| --- | --- |
| Target species | Lutjanus campechanus, Bagre marinus, Rhomboplites aurorubens, and Lutjanus synagris |
| Stock | Campeche Bank, in the southeast region of the Gulf of Mexico. |
| Geographical area | Gulf of Mexico |
| Fishing method or gear type | Vertical longline (ristra or rosario) |
| Fishing fleet | Cooperativa de Producción de Bienes y Servicios, Pescadores de Nuevo Campechito SC de RL de CV |
| UoA 2 | Description |
| Target species | Lutjanus campechanus, Bagre marinus, Rhomboplites aurorubens, and Lutjanus synagris |
| Stock | Campeche Bank, in the southeast region of the Gulf of Mexico. |
| Geographical area | Gulf of Mexico |
| Fishing method or gear type | Bottom longline (palangre huachinanguero) |
| Fishing fleet | Cooperativa de Producción de Bienes y Servicios, Pescadores de Nuevo Campechito SC de RL de CV |

## FIP Actions

Table 3. Action 1: Complete a Stock status evaluation for all target species

| Action 1 | Action 1. Complete a Stock status evaluation for all target species |
| --- | --- |
| Action Goal | Confirm the status of the target species in order to validate the need for more robust strategies. |
| Action Description (Brief summary of the steps involved in the action and importance of the action in achieving the FIP objectives) | The last (available) stock assessment was carried out in 2000, and current stock status is not known. Based on the recommendation provide in the pre-assessment, is necessary to do a robust stock assessment of the red snapper fishery with references points established, developing a dynamic analysis of biomass and a Montecarlo model to define catch quotas and strengthen the harvest strategy. This methodology will be have external peer review. The expected is to create evidence of the currrent status of the stock and help to strengthen the current management strategy and develop specific regulations. Currently, stock evaluations for red snapper (current FIP) and Bagre marinus (National Fisheries Chart 2023) are available. Although the Gafftopsail catfish (B. marinus) status (above the MSY) was only presented as a result on the technical section for the species, details about the methodology implemented were not included. The evaluation of the stock was assessed in 2017. Based on the recommendation provide in the pre-assessment for this fishery and scoping document, it is necessary to complete a robust stock assessment of the vermilion and lane snappers as well as to confirm the status for Gafftopsail catfish. The results will provide input to identify if the current management strategy / measures, are effective, or if there is a need for stronger measures or even a rebuilding strategy. |
| Expected Completion Date | December 2027 |
| Priority | High |
| Estimated Cost | $11,000 USD |
| Responsible Parties (List of participants) | Fishing cooperative, COBI, IMIPAS, and academic researchers. |
| MSC Performance Indicator(s) Addressed by the Action | 1.2.4, 1.2.1, 1.2.3, 1.1.2, and 1.1.1 |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Complete a Stock status evaluation for all target species | 1. Review of the stock assessment methodology for the vermilion and lane snappers as well as to confirm status for Gafftopsail catfish | COBI, academic researchers | Consultant, academic researchers, COBI | November 2024 | December 2026 | Document where the consultants propose the methodology to be used. |
|  | 2. Define the status of these fisheries with reference to its MSY, and peer review it | COBI, academic researchers | Consultant, IMIPAS, CONAPESCA, COBI, fishing cooperative | February 2025 | December 2026 | Manuscript submitted and published to a scientific journal |
|  | 3. Design and propose a specific harvest strategy for the vermilion, lane snappers and Gafftopsail catfish. | COBI, academic researchers | Consultant, IMIPAS, CONAPESCA, COBI, fishing cooperative | July 2026 | December 2027 | Manuscript with results and workshop documentation |

Table 4. Action 2: Design and promote management measures for the fishery

| Action 2 | Action 2. Design and promote management measures for the fishery |
| --- | --- |
| Action Goal | To define a series of measures, strategy or partial strategy that provides evidence of the fisheries' sustainability. |
| Action Description | Through stakeholders collaboration, modify the legal guidelines in a clear, specific and transparent way on the indicators and management standards of the red snapper fishery, to obtain a Fisheries Management Plan for red snapper in the Gulf of Mexico and apply the regulations through legal framework, with periodical revisions, always taking into account the transparency and clarity during the processes of management of the same, allowing that the management indicators to be adaptable for changes in the fishery. Status of the species will play a direct role in this action. Currently, there is no evidence that all target species are above the >80 scoring for P1.1.1. For this reason, the creation of a more formal management scheme is needed, either in the form of a Fisheries Management Plan, a Mexican Official Norm (NOM) or even through more specific measures that will be included within the fisheries National Fisheries Chart profile of the species. |
| Expected Completion Date | December 2027 |
| Priority | Medium |
| Estimated Cost | $4,600 USD |
| Responsible Parties | Fishing cooperative, COBI, IMIPAS, CONAPESCA, academic researchers, and consultants. |
| MSC Performance Indicator(s) Addressed by the Action | 1.2.1, 1.2.2, 3.2.1, and 3.2.4 |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 2. Design and promote management measures for the fishery | 1. Diagnosis of the current official and informal specific objectives and rules to the management of the fisheries. | COBI | COBI, fishing cooperative | August 2024 | August 2025 | Report of diagnosis. |
|  | 2. Define and establish management strategies with an ecosystem approach. | COBI | IMIPAS, CONAPESCA, fishing cooperative, academic researchers, COBI | July 2026 | December 2027 | Collaborative report based on quotas by fleets related for the fisheries, |
|  | 3. Plan to implement and evaluate harvest control tools based on legal document management indicators. | COBI | fishing cooperative, IMIPAS, CONAPESCA, COBI | July 2026 | December 2027 | Workshop and report with results - with short and long term objectives that allows to follow up effective actions of handling in order to maintain the health of the stocks. |
|  | 4. Clarify and apply the long-term objectives of the National Fisheries Chart and to share the management processes of the vermilion and lane snappers, and gafftopsail catfish, in a transparent way. | COBI | fishing cooperative, IMIPAS, CONAPESCA, COBI | July 2026 | December 2027 | Report of compliance |
|  | 5. Continue the modification process of the fishing permit: replace gillnets with vertical and bottom longline, and handline. | COBI, INPESCA | INPESCA, fishing cooperative, IMIPAS, CONAPESCA, COBI | August 2024 | December 2027 | Report of the meetings, improvements, and the agreements |

Table 5. Action 3: Improve and expand the monitoring program

| Action 3 | Action 3. Improve and expand the monitoring program |
| --- | --- |
| Action Goal | The monitoring program continues generating evidence of the impacts on habitats, species (in-scope and ETP) and create a baseline for an ecosystem analysis. |
| Action Description | The pre-assessment concluded the there are no enough data to identify specific interactions among primary, secondary and ETP species with the red snapper bottom and vertical longline fishery. The fishery monitoring program will be evaluate the red snapper current caught strategy will be reviewed and the modification of fishing gear will be implemented to know the biomass level catched, fishing areas, selectivity of fishing gears, bycatch and fishing mortality. Also, will be register and reported results obtained to other species in this fishery (primary, secondary and ETP species) with the goal of generate information to determinate it status and create suitable fishing regulations. The current FIP has successfully started a monitoring program that has allowed to generate information on the target species (mostly red snapper). The expansion to three new target species should follow a similar approach and generate enough information to effectively confirm levels of interactions with the rest of the species, habitats, and ecosystems. |
| Expected Completion Date | December 2027 |
| Priority | High |
| Estimated Cost | $13,700 USD |
| Responsible Parties | Fishing cooperative, COBI |
| MSC Performance Indicator(s) Addressed by the Action | 1.2.3, 2.1.3, 2.2.3 , 2.3.3, and 2.4.3 |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 3. Improve and expand the monitoring program | 1. Training to new fishers/cooperatives who will carry on fishing logbooks | COBI | Fishing cooperatives, COBI | March 2025 | March 2026 | Meetings logs of trainings and first fishing logbooks registered by fishers. |
|  | 2. Fishing logbooks information analysis (Semi-Annual) | COBI | Fishing cooperatives, COBI | August 2024 | December 2027 | Monitoring reports |

Table 6.    Action 4: Evaluate impacts on habitat and ecosystem

| Action 4 | Action 4. Evaluate impacts on habitat and ecosystem |
| --- | --- |
| Action Goal | Confirm the impacts on the ecosystem. |
| Action Description | Evidence taken from similar fisheries, to suggest that the fishery may damage habitat by removing priority species, and to generate damage on the habitat by the fishing gears action. It is necessary to generate information through continuous monitoring about the habitat and ecosystem impacts caused by the use of bottom and vertical longline on the Red snapper fishery in the Campeche Bank, and to develop management measures, if these are negative. In general, the previous work developed by the “Red Snapper FIP” allowed to have a better understanding of the impacts of the fishery in both habitat and ecosystem. However, the inclusion of more target species requires to develop more specific evidence of these impacts. This and the fact that the MSC standard version 3.0 was used this time, are the major drivers to generate more specific evidence of the current status of these elements, and based on this, to assess the need for an improvement management measures/strategy. |
| Expected Completion Date | December 2026 |
| Priority | Medium |
| Estimated Cost | $11,000 USD |
| Responsible Parties | Fishing cooperative, COBI, IMIPAS, CONAPESCA, academic researchers |
| MSC Performance Indicator(s) Addressed by the Action | 2.1.1, 2.1.2, 2.2.1, 2.2.2, 2.3.1, 2.3.2, 2.4.1 and 2.4.2 |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 4. Evaluate impacts on habitat and ecosystem | 1. Ecopath analysis | Academic researchers, COBI | COBI, academic researchers, IMIPAS | January 2025 | December 2026 | Manuscript submitted to a peer-review journal.30 |
|  | 2. Diagnose whether an improvement in management measures/strategy is necessary | COBI | COBI, academic researchers, fishing cooperative, IMIPAS | April 2026 | December 2026 | Workshop and report with results |

Table 7. Action 5: Update decision-making progress

| Action 5 | Action 5. Update decision-making progress |
| --- | --- |
| Action Goal | Define and robustness management tools to the red snapper fishery and associated species fishery, and regulate the legal status of fishers. |
| Action Description | Collaborate with government groups and stakeholders to the development of strategies for the implementation and enforcement of fisheries policies and the assignment of roles in decision-making process. |
| Expected Completion Date | December 2026 |
| Priority | Medium |
| Estimated Cost | $2,300 USD |
| Responsible Parties | Fishing cooperative, COBI, IMIPAS, CONAPESCA, academic researchers |
| MSC Performance Indicator(s) Addressed by the Action | 3.1.1, 3.2.2, 3.1.2, and 3.2.3 |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 5. Update decision-making progress | Development of a technical advisory committee for the snappers fishery in the Campeche Bank region | COBI | IMIPAS, CONAPESCA, INPESCA, academic researchers, fishing cooperative, COBI | October 2024 | December 2026 | Constitutive act of the group - will allow the development of specific control guidelines, aimed at the red snapper and associated species fishery |