# KIEN GIANG BLUE SWIMMING CRAB

# FISHERIES IMPROVEMENT PROJECT

# (Kien Giang BSC FIP)

PLAN OF ACTIONS

Originally developed by: RICHARD BANKS and TRAN VAN HAO

Prepared for the VASEP CRAB COUNCIL (VCC)

Updated August 2025 by JOCELYN DRUGAN and VU VIET HA

KIEN GIANG - VIETNAM

LIST OF ACRONYMS

| Vietnamese Institutions Acronyms |  |
| --- | --- |
| DARD | Department of Agriculture and Resource Development |
| DFISH | Vietnam Directorate of Fisheries |
| DECAFIREP | Department of Capture Fisheries & Resource Exploitation and Protection |
| MARD | The Ministry of Agriculture and Resource Development |
| NIO | Nha Trang Institute of Oceanography |
| NTU | Nha Trang University |
| PPC | Provincial People’s Committees |
| RIMF | Research Institute for Marine Fisheries |
| Sub-DFISH | Provincial Directorate of Fisheries |
| TFMC | Tuna Fisheries Management Council |
| VASEP | Vietnam Association of Seafood Exporters and Producers |
| VCC | VASEP Crab Council |
| WWF | World Wildlife Fund (Vietnam) |
| Fisheries Management Acronyms |  |
| EEZ | Exclusive Economic Zone |
| CAC | Crab Advisory Council |
| CMC | Crab Management Council |
| CMP | Crab Management Plan |
| IUU | Illegal, Unreported and Unregulated |
| MoU | Memorandum of Understanding |
| MSE | Management Strategy Evaluation |
| NTMP | National Tuna Management Plan |
| UNFSA | United Nations Fish Stocks Agreement |
| MSC Acronyms |  |
| BMT | MSC FIP Benchmarking and Monitoring Tool |
| CSA | Consequence Susceptibility Analysis |
| EAFM | Ecosystem Approach to Fisheries Management |
| ETP | Endangered, Threatened and Protected |
| FCR | Fisheries Certification Requirements |
| FIP | Fishery Improvement Project |
| MSC | Marine Stewardship Council |
| PRA | Participatory Rural Appraisal |
| PSA | Productivity Susceptibility Analysis |
| RBF | Risk Based Framework |
| RRA | Rapid Rural Appraisal |
| SICA | Scale Intensity Consequence Analysis |

## INTRODUCTION

This FIP was originally launched in 2010 and subsequently re-activated in 2024 following a few years of inactivity starting in 2020. The Units of Assessment (UoAs) are:

- Blue swimming crab caught by gill net, Kien Giang Province, Vietnam;

- Blue swimming crab, caught by trap, Kien Giang Province, Vietnam.

This document identifies the activities and range of activities required in the Action Plan for the fisheries to meet the Marine Stewardship Council (MSC) standard, version 2.01. The most important feature to this is that all target species (Principle 1), must focus on the stock status and management activities throughout the range of the stock, whilst ecosystem interactions (for secondary species, and Endangered, Threatened, and Protected (ETP) species) relate specifically to the fishery under assessment.

Prior to 2020, WWF-Vietnam and the Vietnam Association of Seafood Exporters and Producers (VASEP) Crab Council supported implementation of the FIP. The overarching management issues fall to DARD. Research functions are supported by the Research Institute for Marine Fisheries (RIMF).

In 2019, the Poseidon consultant determined that the main challenges for this fishery to achieve MSC status in the near or medium term (over the next 5 years) are as follows.

- The stock biomass is quite variable responding to changing environmental conditions, but in 2017 there was a catastrophic event with resulting high levels of mortality and a significant reduction in stock biomass.

- Over the years, there is no evidence that DARD is willing to implement the required changes to gear restrictions to rebuild the stock and to prevent a hindering of recovery, or once rebuilt, to regulate effort. Measures were set in 2015 aimed at reducing the catch of pre adult crabs.

- Policing of the fishery is heavily under-resourced, which has resulted in some systematic noncompliance in areas such as the minimum landing size. A large proportion of the fleet (vessels under 20 CV) are largely unregulated.

- The stock is also fished by Cambodian fishers. The consultant had raised the need to allow for uncertainties created as a result of Cambodian fishing effort, but no assessment has been made despite anecdotal effort that there is significant presence of Cambodian activity on the target stock.

- DARD has other management priorities and has been unable to dedicate sufficient time to support the FIP and Local District government have limited powers to implement controls.

- District fisheries are subject to lower levels of enforcement as District officers have limited powers.

- Processors are sourcing product from Cambodian fishers.

- The wet market has increased in response to demand from tourists.

- The fishermen are not supportive of the co-management activity, which was seeking to develop alternative livelihoods, and alternative livelihood models have not been implemented as communities are unable to define feasible options.

- There is no evidence that the Crab Advisory Council has met to advise on management decision making, or at least if it has, such an occurrence was rare.

Table 1. Workplan Overview

| Workplan Version and Date | Version 2.1, June 2024 |
| --- | --- |
| Start date | End date |
| January 2023 | December 2028 |
| FIP Lead | Improvements recommended by |
| VASEP Crab Council (VCC) | Kien Giang BSC FIP Meeting with relevant stakeholders in Rach Gia City, Kien Giang, Vietnam |
| FIP Coordinator (organization/individual responsible for reporting on Fishery Progress) | Workplan developed by (consultant or person) |
| VASEP Crab Council (VCC) | Mr Richard Banks – MSC Qualified Consultant Poseidon ARM Ltd. Msc. Tran Van Hao Marine Science & Fishing Technology Institute Nha Trang University, Vietnam Dr. Jocelyn Drugan Ocean Outcomes and MSC Technical Consultant Dr. Vu Viet Ha Research Institute for Marine Fisheries |

## UNIT OF ASSESSMENTS

Table 2. Units of Assessment (UoAs)

| UoA 1 | Description |
| --- | --- |
| Target species | Blue Swimming Crab (Portunus pelagicus) |
| Stock | Vietnam EEZ |
| Geographical area | Kien Giang coastal areas – Vietnam EEZ |
| Fishing method or gear type | Trap |
| Fishing fleet or group of vessels, or individuals fishing operators pursuing stock | Small scale fleets of Kien Giang province |
| UoA 2 | Description |
| Target species (common and scientific name) | Blue Swimming Crab (Portunus pelagicus) |
| Stock | Vietnam EEZ |
| Geographical area | Kien Giang coastal areas – Vietnam EEZ |
| Fishing method or gear type | Bottom Gillnet |
| Fishing fleet or group of vessels, or individuals fishing operators pursuing stock | Small scale fleets of Kien Giang province |

## FIP ACTIONS

Table 3. Performance Indicator Action Plan Table for Action 1

| Action Number and Name | Action 1. Determine the plan for BSC stock recovery. |
| --- | --- |
| Action Goal | A list of management options to restore the BSC stock is developed and evaluated, and a recovery strategy adopted. |
| Action Description | RIMF will determine how to rebuild the stock to agreed Target and Limit Reference Points, following evaluation of management options. The rebuilding strategy will then be implemented. |
| Expected Completion Date | 2028 |
| Priority | High |
| Estimated Cost | 80,000 USD |
| Responsible Parties | RIMF, VCC, NFI, Kien Giang Sub-DFISH & industries |
| MSC PI(s) Addressed by the Action | Stock status (1.1.1) and Stock rebuilding (1.1.2) |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 1. Determine the plan for BSC stock recovery. | Task 1-1: Review BSC stock status and BSC fisheries in Kien Giang | RIMF | VCC, DARD | 2024 | 2026 | Report with updated information on BSC stocks and fisheries activities. |
|  | Task 1-2: Determine a Plan for Stock recovery | RIMF | VCC, DARD | 2025 | 2028 | Plan for Stock recovery & implementation |

Table 4. Performance Indicator Action Plan Table for Action 2: Harvest strategy actions and control rules set.

| Action Number and Name | Action 2: Harvest strategy actions and control rules set. |
| --- | --- |
| Action Goal | Clear harvest strategy and HCRs are in place |
| Action Description | Development of a harvest strategy that will apply collectively to all UoAs, such that the stocks are fluctuating around a level consistent with MSY. Evidence must be available to show that the Harvest Strategy is achieving its objectives. |
| Expected Completion Date | 2028 |
| Priority | High |
| Estimated Cost | $40,000 USD |
| Responsible Parties | MARD, Kien Giang DARD, RIMF, VCC, NFI |
| MSC PI(s) Addressed by the Action | Stock status (1.1.1), Stock rebuilding (1.1.2), 1.2.1 Harvest Strategy and 1.2.2 on Harvest control rules |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 2: Harvest strategy actions and control rules set. | Task 2-1: A significant reduction in fishing effort | Kien Giang DARD, VCC | RIMF | 2023 | 2028 | The number of crab fleets is reduced year by year towards a more sustainable level |
|  | Task 2-2 (completed): Protection of spawning grounds | Kien Giang DARD, VCC | NTU | 2023 | 2028 | Report from MCS activities from Kien Giang DARD |
|  | Task 2-3: An increase in the crab MLS to 11 cm, and no margin of tolerance | RIMF, VCC | Kien Giang DARD | 2023 | 2028 | Scientific Report on increasing of the Crab MLS to 11cm and 10% margin of tolerance |
|  | Task 2-4: A significant increase in the crab trap minimum mesh size to prevent the catching of immature crabs | Kien Giang DARD, VCC | RIMF | 2023 | 2025 | Scientific Report on crab trap mesh size in Kien Giang |
|  | Task 2-5: Banning Chinese traps (completed). | Kien Giang DARD, VCC | NTU | 2023 | 2025 | A provincial level of regulation on banning Chinese traps fishing in Kien Giang waters |
|  | Task 2-6: Reference Points (RPs) are set up by the VCC & Kien Giang DARD | RIMF | VCC, Kien Giang DARD, NFI | 2023 | 2026 | Report on TRPs & LRPs for BSC in Kien Giang |
|  | Task 2-7: Implement Harvest Strategy | DARD | NTU, RIMF, VCC | 2025 | 2028 | Report on RPs implementations |

Table 5. Performance Indicator Action Plan Table for Action 3: A continued commitment to stock assessment.

| Action Number and Name | Action 3: A continued commitment to stock assessment |
| --- | --- |
| Action Goal | Kien Giang coastal crab stock is assessed for every 2 years |
| Action Description | Assess the Blue Swimming Crab stock in Kien Giang coastal areas by scientific parties |
| Expected Completion Date | 2028 |
| Priority | High |
| Estimated Cost | $25,000 USD per year |
| Responsible Parties | MARD, Kien Giang DARD, RIMF, VCC, NFI |
| MSC PI(s) Addressed by the Action | Stock status (1.1.1) and Stock rebuilding (1.1.2) |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 3: A continued commitment to stock assessment | Task 3-1: Stock assessment process continues | RIMF | VCC, DARD, NFI | 2023 | 2028 | Every 2 years of Stock assessment reports by scientific parties |
|  | Task 3-2: External peer review is completed and uncertainties incorporated into the updated stock assessment report | RIMF | VCC, DARD, NFI | 2025 | 2025 | Review reports |

Table 6. Performance Indicator Action Plan Table for Action 4: An ongoing commitment to logbook data collection

| Action Number and Name | Action 4: An ongoing commitment to logbook data collection |
| --- | --- |
| Action Goal | 100% of over 12m length up of crab vessels have collected logbook data |
| Action Description | A logbook system was implemented to support the stock assessment work. National Fisheries Law No.18/2017/QH14 & Circular 21/2019/TT-BNNPTNT already required ALL fishing vessels > 12m length have to submit daily fishing logbook and weekly fishing logbook for 6-12m length. |
| Expected Completion Date | 2028 |
| Priority | High |
| Estimated Cost | $25,000 USD |
| Responsible Parties | MARD, Kien Giang DARD, RIMF, VCC, NFI |
| MSC PI(s) Addressed by the Action | 1.2.3 – Information and monitoring |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 4: An ongoing commitment to logbook data collection | Task 4-1: Logbook design (completed) | MARD / DFISH | Kien Giang DARD | Completed | Completed | Logbook form on Circular 21/2018/TT-BNNPTNT |
|  | Task 4-2: Logbook program implementation | VCC, DARD | RIMF | 2023 | 2028 | Logbook program is implemented in an on-going manner |

Table 7. Performance Indicator Action Plan Table for Action 5: Collect fishery information to support the harvest strategy

| Action Number and Name | Action 5: Collect fishery information to support the harvest strategy |
| --- | --- |
| Action Goal | Information related to fishery catches will be collected via an observer program or port sampling |
| Action Description | Information related to fishing hauls, including fishing location, fishing time, species composition, species catches, sizes and other key biological information will be collected in order to support the harvest strategy. |
| Expected Completion Date | 2028 |
| Priority | High |
| Estimated Cost | $28,000 USD |
| Responsible Parties | MARD, Kien Giang DARD, RIMF, VCC, NFI |
| MSC PI(s) Addressed by the Action | 1.2.3 – Information and monitoring |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 5: Collect fishery information to support the harvest strategy | Task 5-1: Observer program or port sampling implementation | RIMF, DARD, NTU | VCC, NFI, Industries | 2023 | 2028 | Observer or port sampling reports |
|  | Task 5-2: Report on crab size in the BSC catches. | RIMF, DARD | VCC, NFI, Industries | 2024 | 2025 | Stock assessment with information on crab sizes |

Note: Action 6 was removed from the work plan, but FisheryProgress asked us to keep the Actions numbering. This is why the next action is listed as Action 7.

Table 8. Performance Indicator Action Plan Table for Action 7: Implement a prohibition on the landing of bamboo sharks, either as a direct local decree, or add to the list of prohibited ETP species (Appendix II, Decree 26)

| Action Number and Name | Action 7: Mitigate negative fishery impacts on secondary and ETP species |
| --- | --- |
| Action Goal | Assess fishery impacts on secondary and ETP species and implement mitigative measures as needed |
| Action Description | The fishery potentially interacts with vulnerable species such as bamboo sharks. We will evaluate interactions with secondary and ETP species and, as needed, implement measures to mitigate these interactions, such as through decrees and awareness building with fishers. |
| Expected Completion Date | 2028 |
| Priority | High |
| Estimated Cost | $25,000 USD |
| Responsible Parties | MARD, Kien Giang DARD, RIMF, VCC, NFI |
| MSC PI(s) Addressed by the Action | Secondary species outcome (2.2.1), Secondary species management (2.2.2), Secondary species information (2.2.3), ETP species management (2.3.2), ETP species information (2.3.3) |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 7: Implement a prohibition on the landing of bamboo sharks, either as a direct local decree, or add to the list of prohibited ETP species (Appendix II, Decree 26) | Task 7-1: Risk assessment for secondary species | RIMF | VCC, DARD | Completed 2017 | Completed 2017 | Risk Assessment Report |
|  | Task 7-2: Implementation of management action to protect bycatch species (completed) | RIMF | VCC, DARD | 2023 | 2026 | ETP protection actions |
|  | REMOVED Task 7-3: Awareness raising for prohibition on the landing of bamboo sharks, either as a direct local decree, or add to the list of prohibited ETP species (Appendix II, Decree 26) | VCC, DARD | NTU, RIMF | 2023 | 2028 | Trainings & awareness awareness raising is implemented in Kien Giang |
|  | Task 7-4 Evaluate fishery impacts on secondary and ETP species. | VCC, DARD | RIMF | 2025 | 2027 | Updated information on fishery interactions with secondary and ETP species. |
|  | Task 7-5 Implement measures to reduce fishery impacts on vulnerable species | VCC, DARD | RIMF | 2025 | 2028 | - Raise awareness of species that are vulnerable to fishery impacts and encourage adoption of protections - Design and publish an illustrated placard on the common species caught by the BSC fishery (including ETP species) and distribute it to fisheries communities to raise awareness about ETP species protection |

Table 10. Performance Indicator Action Plan Table for Action 8: The application of the Kien Giang Crab Management Plan, including the implementation of appropriate objectives

| Action Number and Name | Action 8: The application of the Kien Giang Crab Management Plan, including the implementation of appropriate objectives |
| --- | --- |
| Action Goal | The Kien Giang Crab Management Plan is in place and includes appropriate objectives |
| Action Description | Evidence will need to show that the management plan has objectives to implement and monitor the application of crab management. The Kien Giang Crab Fisheries need to be managed with an ecosystem approach, clear application of inputs and output controls, and an appropriate fishery information monitoring system. |
| Expected Completion Date | 2028 |
| Priority | High |
| Estimated Cost | $12,000 USD |
| Responsible Parties | MARD, Kien Giang DARD, NTU, RIMF, VCC, NFI |
| MSC PI(s) Addressed by the Action | Fisheries specific Objectives (3.2.1) |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 8: The application of the Kien Giang Crab Management Plan, including the development of appropriate objectives | Task 8-1: FIP and CMP completed | VCC, DARD | RIMF, NFI, Industries | 2023 | 2028 | FIP & CMP completed |
|  | Task 8-2: Crab fleet vessels are reported yearly | DARD | VCC | 2023 | 2028 (ongoing) | Yearly Statistical Report on Crab Fleets of Kien Giang Province |
|  | Task 8-3: Kien Giang Crab management includes ecosystem considerations | Kien Giang DARD | RIMF, VCC | 2023 | 2028 | The CMP has an objective reflecting an ecosystem approach to management |

Table 11. Performance Indicator Action Plan Table for Action 9: Crab Advisory Council operational

| Action Number and Name | Action 9: VASEP Crab Council (VCC) operational |
| --- | --- |
| Action Goal | VASEP Crab Council (VCC) make significant contributions to Crab Management Plan implementation |
| Action Description | The CAC/CMC (Crab Advisory Council or Crab Management Council) mentioned in the pre-assessment, which was started by DARD, is no longer active. Hence VASEP established the VASEP Crab Council (VCC) to provide technical support in decision making & consultation processes, particularly as related to sustainable development of the crab industry and the Kien Giang BSC FIP. VCC will connect related stakeholders in BSC supply chains as well as governmental authorities at both local and central levels. The VCC consists of VASEP member companies, who have partnerships with crab fishermen. The companies relay relevant information between the council and the fishermen as needed. Academic scientists participate in the VCC to provide technical advice and recommendations. The VCC is currently operational and holds larger meetings one to two times per year, in addition to extra meetings convened as needed. The VCC aims to provide input to the Kien Giang DARD and MARD on crab management measures. Under this revised action, the VCC will demonstrate that it facilitates the flow of information from stakeholders to authorities within the decision making and consultation process, in an ongoing manner. |
| Expected Completion Date | 2028 (ongoing) |
| Priority | Medium |
| Estimated Cost | $10,000 USD |
| Responsible Parties | VCC, NFI, MARD, Kien Giang DARD, RIMF |
| MSC PI(s) Addressed by the Action | Consultation (3.1.2) and Decision making (3.2.2) |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 9: Crab Advisory Council operational | Task 9-1: Vietnam Crab Council set up and fully functional, coordinator appointed | VCC | DARD & Industries | 2021 | 2024 | VCC establishment & implementations |
|  | Task 9-2: facilitate consultation between stakeholders and decision making authorities | VCC | DARD & Industries | 2023 | 2028 | VCC establishment & implementations |

Table 12. Performance Indicator Action Plan Table for Action 10: Decision making takes account of research, monitoring and evaluation

| Action Number and Name | Action 10: Decision making takes account of research, monitoring and evaluation |
| --- | --- |
| Action Goal | Scientific evidences are used on the decision making |
| Action Description | Decision making by DARD will follow the following components: - Decision making results in measures and strategies to achieve the management objectives - Serious issues identified in research, monitoring and evaluation are implemented in a transparent and timely manners - Decisions take account of the precautionary approach to fisheries management Information on the fishery’s performance and management actions is available and explanations are provided on actions or lack of actions taken. |
| Expected Completion Date | 2028 |
| Priority | Medium |
| Estimated Cost | $20,000 USD |
| Responsible Parties | MARD, Kien Giang DARD, NTU, RIMF, VCC, NFI |
| MSC PI(s) Addressed by the Action | Decision making (3.2.2) |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 10: Decision making takes account of research, monitoring and evaluation | Task 10-1: Recommend harvest strategy options to DARD | VCC, MARD, DFISH | DARD & Industries | 2025 | 2028 | Vietnam Crab Harvest Strategies are introduced |
|  | Task 10-2: VCC and DARD decision making processes to be documented to demonstrate use of advice | VCC, MARD, DFISH | DARD & Industries | 2025 | 2028 | VCC advice comes into decision making process |

Table 13. Performance Indicator Action Plan Table for Action 11: Promulgation of Fisheries Laws that are effective in reducing fishing effort by significant proportions, protect spawning stocks and prevent the catch of pre adult crabs.

| Action Number and Name | Action 11: Promulgation of Fisheries Laws that are effective in reducing fishing effort by significant proportions, protect spawning stocks and prevent the catch of pre adult crabs. |
| --- | --- |
| Action Goal | Management measures are set out in Decrees or Circulars and applied |
| Action Description | MARD/DFISH and the provincial Kien Giang DARD should ensure that a number of core principles are applied with its fisheries specific laws: - Fishing activities are sustainable and effective, in a manner consistent with preserving marine resources; and - Fishing operations must ensure conservation of related marine ecosystems and biodiversity, protecting marine environment and its natural landscapes. - Fisheries sector development strategies must be planned to be associated with national and local fisheries management plans. After a legal document is promulgated within the Vietnam management system, the competent agencies are responsible for implementing and widely disseminating it to the public. However, their efforts may not fully reach local fishermen. The VCC intends to conduct activities to raise awareness for fishermen of relevant fisheries regulations, which will increase their ability to participate in management consultation processes, as well as compliance. |
| Expected Completion Date | 2028 |
| Priority | Medium |
| Estimated Cost | $20,000 USD |
| Responsible Parties | MARD, Kien Giang DARD, RIMF, VCC, NFI |
| MSC PI(s) Addressed by the Action | 3.1.2 on Consultations, Roles & Responsibility and Compliance & enforcement (3.2.3) |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 11: Promulgation of Fisheries Laws that are effective in reducing fishing effort by significant proportions, protect spawning stocks and prevent the catch of pre adult crabs. | Task 11-1: Effective national & provincial legal system | VCC, MARD, DFISH and Kien Giang DADR | VCC, RIMF, Industries | 2021 | 2028 | Legal framework of national & provincial levels is implemented |

Table 14. Performance Indicator Action Plan Table for Action 12: Compliance resources are applied to the Kien Giang crab fishery including monitoring the minimum landing sizes, closed areas and minimum mesh sizes.

| Action Number and Name | Action 12: Compliance resources are applied to the Kien Giang crab fishery |
| --- | --- |
| Action Goal | Fishery regulations are enforced and complied with. |
| Action Description | As described in the pre-assessment, “limited resources and alternative compliance priorities compete against the ability to implement an effective compliance scheme in the KG Crab fishery. Enforcement at commune level is non-existent, and local officers, e.g. Wildlife Protection wardens, lack the powers to implement measures. A system of sanctions is now in place (Decree 45) and is applied to a limited extent.” One challenge affecting enforcement of regulations is lack of fisher awareness, which is addressed under Action 11. A second key challenge lies in how enforcement roles are assigned within the current legal framework. Specifically, local (district) agencies hold MCS (monitoring, control, surveillance) authority for coastal fisheries, but only for vessels less than 6m in length and/or less than 20 horsepower. BSC fishing vessels, despite operating within the coastal zone, are larger and technically supposed to be managed by provincial authorities. However, the provincial level DARD lacks human and financial resources to patrol and inspect the numerous BSC vessels. To address this gap, FIP stakeholders decided to support enforcement of regulations at the district level through voluntary efforts. The VCC will work with NTU in cooperation with Kien Giang DARD to collect biological indicators of Blue Swimming Crab such as minimum landing sizes (at sea, on landing and in picking stations), and inspection checks on mesh sizes and operating in closed areas as under Vietnam regulation on Decree 26/2019/ND-CP and Decree 42/2019/ND-CP of Vietnam Govt and Circular 21/2019/TT-BNNPTN. |
| Expected Completion Date | 2028 |
| Priority | Medium |
| Estimated Cost | $20,000 USD |
| Responsible Parties | MARD, Kien Giang DARD, RIMF, VCC, VASEP & Industries |
| MSC PI(s) Addressed by the Action | Compliance (3.2.3) |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 12: Compliance resources are applied to the Kien Giang crab fishery | Task 12-1: Review compliance related reports. | VCC, MARD, DFISH | DARD & Industries | 2023 | 2024 | Review reports |
|  | Task 12-2: Assess enforcement roles at district / provincial level and sanctions applied (based on Decree 42/2019/ND-CP) | Kien Giang DARD | VCC | 2023 | 2028 | Statistical Report on sanctions |
|  | Task 12-3: Inspection of minimum landing sizes (at sea, on landing and in picking stations), and inspection checks on mesh sizes and operating in closed areas. | Kien Giang DARD | VCC | 2023 | 2026 | Report on landing size & used mesh size |

Table 15. Performance Indicator Action Plan Table for Action 13: Governance Performance Review Structure in place.

| Action Number and Name | Action 13: Governance Performance Review Structure in place. |
| --- | --- |
| Action Goal | Review the performance of fisheries management governance |
| Action Description | A review of Kien Giang DARD’s implementation performance is needed. Thus, a specific review of Kien Giang DARD and Compliance performance as evidence that the required roles and responsibilities are being effectively applied will be conducted. This will be an external & independent review. |
| Expected Completion Date | Dec 2028 |
| Priority | Low |
| Estimated Cost | $5,000 USD |
| Responsible Parties | MARD, Kien Giang DARD, RIMF, VCC, NFI |
| MSC PI(s) Addressed by the Action | Performance Review (3.2.4) |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Action 13: Governance performance review structure in place. | Task 13-1: Internal and/or external reviews implementation | VCC, MARD, DFISH | DARD & Industries | 2023 | 2028 | Review reports |

MSC qualified Consultant from Poseidon Ltd

Marine Science & Fishing Technology – Nha Trang University (NTU)

MSC Technical Consultant, Ocean Outcomes

Research Institute for Marine Fisheries

There are no primary species as there are no supporting stock assessments for these species.