## Mexican North Pacific Barred sand bass-pot/trap

## Fishery Improvement Project (FIP) Workplan

Table 1: Workplan Overview

| Workplan Version and Date |  |
| --- | --- |
| Start date (expected): | End date (anticipated month/year): |
| January, 2023 | December, 2027 |
| FIP Lead (organization/individual responsible for Action Plan): | Improvements recommended by (meeting/group that supported the development): |
| FEDECOOP, Centro para la Biodiversidad Marina y la Conservación A.C. and Pronatura Noroeste A.C. | FEDECOOP, Centro para la Biodiversidad Marina y la Conservación A.C., INAPESCA and Pronatura Noroeste A.C. |
| FIP Coordinator (organization/individual responsible for reporting on FisheryProgress): | Workplan developed by (consultant or person): |
| Pronatura Noroeste A.C./ Laura Elizabeth Ibarra García | FEDECOOP and Pronatura Noroeste A. C |

#### Acronyms

| CBMC | Centro para la Biodiversidad Marina y la Conservación A.C. |
| --- | --- |
| FEDECOOP | Federación Regional de Sociedades Cooperativas de la Industria Pesquera Baja California, F.C.L. |
| INAPESCA | Instituto Nacional de Pesca |
| MSC | Marine Stewardship Council |
| PNO | Pronatura Noroeste A.C. |

#### Unit of Assessment

Table 2. Unit of Assessment (UoA)

| UoA 1 | Description |
| --- | --- |
| Target species (common and scientific name) | Barred sand bass (Paralabrax nebulifer). |
| Stock | Mexican North Pacific. |
| Geographical area | Baja California Sur, Mexican North Pacific. |
| Fishing method or gear type | Pot/trap. |
| Fishing fleet or group of vessels, or individuals fishing operators pursuing stock | Artisanal Mexican fleet. |

## FIP Actions

Table 3. Performance Indicator Action Plan Table for Action 1.2.1. Harvest strategy.

| Action Number and Name | 1. Develop a harvest strategy |
| --- | --- |
| Action Goal | Have a harvest strategy that responds to the state of the stock |
| Action Description | For the development of an adequate exploitation strategy, the collection and generation of information on the fishery is required to be used in the assessment of methodologies that allow evaluating the status of the stock and advancing in the development of an adequate exploitation strategy for the fishery. |
| Expected Completion Date | December 2025 |
| Priority | High |
| Estimated Cost | $35,000 USD |
| Responsible Parties | FEDECOOP, Pronatura Noroeste, INAPESCA and CBMC |
| MSC PI(s) Addressed by the Action | 1.2.1. Harvest strategy |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Develop a harvest strategy | 1.1. Integrate the information, the results of the stock assessment, the control rule, and the management tools, allowing the management system to respond to the state of the barred sand bass stock and meeting the management objectives of the fishery | PNO | FEDECOOP/INAPESCA /CBMC | July 2018 | December 2024 | Database with information integrated annually |
|  | 1.2. Advance in the harvest strategy | PNO | FEDECOOP/INAPESCA/CBMC | January 2018 | December 2025 | Harvest strategy implemented and agreed by the stakeholders |

Table 4. Performance Indicator Action Plan Table for Action 1.2.2 Harvest control rules and tools

| Action Number and Name | 2. Design a control rule that responds to the state of the resource, guaranteeing that the fishery is maintained according to the reference points. 3. Define the mechanisms for applying the control rule |
| --- | --- |
| Action Goal | The HCRs available to the barred sand bass fishery respond to exploitation, implementing a reduction in the catch as the point where recruitment is compromised approaches. |
| Action Description | The design of the HCR requires the identification of the control rules used in the cooperatives, in addition to analyzing appropriate alternatives to reduce fishing mortality such as the establishment of a temporary closure, quotas and evaluating the selectivity and efficiency of the fishing gear to determine if it is the most suitable. |
| Expected Completion Date | December 2025 |
| Priority | Medium |
| Estimated Cost | $25,000 USD |
| Responsible Parties | FEDECOOP/INAPESCA/PNO/CBMC |
| MSC PI(s) Addressed by the Action | 1.2.2 Harvest control rules and tools |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 2. Design a control rule that responds to the state of the resource, guaranteeing that the fishery is maintained according to the reference points. | 2.1 Review the characteristics of the trap and determine if they are the most appropriate for the barred sand bass fishery in the UoA area | FEDECOOP | INAPESCA/PNO/CBMC | January 2021 | June 2025 | Trap selectivity study results |
| 3. Define the mechanisms for applying the control rule | 3.1 Analyze and implement alternatives to reduce the most appropriate fishing mortality during the reproductive season (size, closed season and / or quota) | FEDECOOP | INAPESCA/PNO/CBMC | January 2021 | December 2025 | Consensus of the appropriate alternative to reduce mortality and Application of appropriate alternative to reduce mortality |

Table 5. Performance Indicator Action Plan Table for Action 1.2.3. Information and monitoring

| Action Number and Name | 4. Maintain a monitoring system |
| --- | --- |
| Action Goal | The fishery has an information and monitoring system that collects catch and effort data that allow understanding the behavior of the fishery. |
| Action Description | To improve the information and monitoring system, it is necessary to analyze the current system to identify areas of opportunity to improve and identify the information necessary to develop an electronic log system that allows systematizing the information and keeping a database updated. |
| Expected Completion Date | June 2025 |
| Priority | Medium |
| Estimated Cost | $20,000 USD |
| Responsible Parties | PNO, INAPESCA FEDECOOP and CBMC |
| MSC PI(s) Addressed by the Action | 1.2.3. Information and monitoring |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 4. Maintain a monitoring system | 4.1. Implement a fishery biological monitoring system in strategic locations of the UoA and the UoC, defined based on their productivity and prioritising the information needs of the fishery. | INAPESCA | FEDECOOP/PNO | January 2018 | December 2024 | Broadly and comprehensive monitoring implemented |
|  | 4.2 Perform an analysis of the distribution and abundance in aggregation zones | PNO | CBMC | January 2018 | June 2025 | Distribution and abundance analysis report |

Table 6. Performance Indicator Action Plan Table for Action 1.2.4 Assessment of stock status

| Action Number and Name | 5. Improve the stock assessment method |
| --- | --- |
| Action Goal | The assessment is appropriate for the stock and the harvest strategy. The assessment estimates the status of the stock in relation to reference points, which can be estimated and are appropriate for the stock. |
| Action Description | According to the pre-assessment, basic stock assessments have been conducted and estimated stock status relative to reference points. However, the assessment method needs to be developed further to better account for the biological characteristics of the target species and to better account for uncertainties. Thus, the goal of this action is to have a stock assessment method that takes into account most elements and factors that are related to the barred sand bass fishery. |
| Expected Completion Date | December 2024 |
| Priority | Medium |
| Estimated Cost | $14,500 USD |
| Responsible Parties | PNO/INAPESCA/FEDECOOP/CBMC |
| MSC PI(s) Addressed by the Action | 1.2.4 Assessment of stock status |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 5. Improve the stock assessment method | 5.1. Update stock assessment status such that the methodology is appropriate for the species and the harvest control rule and based on reference points reflecting the objectives in PI 1.1.1 and accounting for the main uncertainties. | PNO | INAPESCA/FEDECOOP | January 2018 | June 2024 | Update the assessment of the stock status |
|  | 5.2. Peer review of stock assessment | PNO | INAPESCA/FEDECOOP | January 2023 | December 2024 | Stock assessment peer review report |
|  | 5.3 Carry out a study relating the environmental desiring and the Sand bass fishery | PNO |  | July 2021 | December 2024 | Report on environmental variability and Barred Sand Bass fishery relation |

Table 7. Performance Indicator Action Plan Table for Action 2.4.3 Habitats information

| Action Number and Name | 6. Determine the interaction of the barred sand bass fishery with the habitats and the ecosystem in the UoA |
| --- | --- |
| Action Goal | There is a general knowledge of the types and distribution of habitats and the ecosystem within the UoA; however, there is no knowledge at a level of detail relevant to the scale and intensity of the UoA. Thus, the goal is to know the nature, distribution and vulnerability of the main habitats and the ecosystem within the UoA in a level of detail relevant to the scale and intensity of the UoA. Know the location and size of the main fishing grounds of the barred sand bass fishery and determine the distribution and abundance in the aggregation zones |
| Action Description | It is necessary to determine the location and size of the main fishing grounds through interviews and records of the fishing grounds through the monitoring of the fishery through electronic log to determine the interaction of the fishery with the habitat. |
| Expected Completion Date | December 2027 |
| Priority | Medium |
| Estimated Cost | $17,000 USD |
| Responsible Parties | FEDECOOP/PNO/CBMC |
| MSC PI(s) Addressed by the Action | 2.4.3 Information habitats 2.5.3 Information ecosystem |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 6. Determine the interaction and impact of the Barred Sand Bass fishery with the habitats and the ecosystem in the UoA | 6.1 Determine the location and size of the fishing grounds | FEDECOOP | PNO | January 2018 | July 2024 | Fishing grounds location and size report |
|  | 6.2 Determine the distribution of habitats and the ecosystem in the UoA region | PNO |  | January 2018 | December 2024 | Habitats and ecosystem distribution report |
|  | 6.3 Improve the quality information of the vulnerability of the habitats and ecosystem, and its adequacy and relevance to assess the impacts of the fishery |  |  |  | December, 2027 | Comprehensive information package |

Table 8. Performance Indicator Action Plan Table for Action 3.2.2 Decision making processes.

| Action Number and Name | 7. Formalize the decision-making processes of the cooperatives in relation to the barred sand bass fishery, by including it in the management plan or any other regulatory document. |
| --- | --- |
| Action Goal | Barred sand bass fishery advisory committee established with formal decision-making processes. |
| Action Description | Promote the installation of an advisory committee for the verdillo fishery that holds annual meetings to monitor the fishery and that has regulations and a route for decision-making. |
| Expected Completion Date | December 2026 |
| Priority | Medium |
| Estimated Cost | $6,000 USD |
| Responsible Parties | FEDECOOP/PNO/INAPESCA |
| MSC PI(s) Addressed by the Action | 3.2.2 Decision making processes |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 7. Formalize the decision-making processes of the cooperatives in relation to the barred sand bass fishery, by including it in the management plan or any other regulatory document. | 7.1. Formally establish the barred sand bass fishery management committee | FEDECOOP |  | January 2021 | December 2024 | Installation and operation of the management committee. |
|  | 7.2. Develop a roadmap on the decision-making process within the management commite. | FEDECOOP | PNO | January 2021 | December 2025 | Establishment of annual meetings to monitor the management of the barred sand bass fishery |
|  | 7.3. Gather the evidence of the agreements reached in the decision-making processes | INAPESCA | PNO | January 2021 | December 2026 | Evidence management committee file |

Table 9. Performance Indicator Action Plan Table for Action 3.2.4 Management performance evaluation

| Action Number and Name | 8. Establish mechanisms to evaluate the management system of the barred sand bass fishery |
| --- | --- |
| Action Goal | The Fishery Management System is reviewed by a third party every three years and the FIP work plan is reviewed annually by the work team. |
| Action Description | Once defined a specific management system for the barred sand bass fishery, the goal of this actions is to design and put in place mechanisms to periodically evaluate the fishery management system. |
| Expected Completion Date | December 2027 |
| Priority | High |
| Estimated Cost |  |
| Responsible Parties | FEDECOOP (Technicians cooperatives)/PNO/INAPESCA |
| MSC PI(s) Addressed by the Action | 3.2.4 Management performance evaluation |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 8.Establish mechanisms to evaluate the management system of the barred sand bass fishery | 8.1. Agree and put in place mechanisms to evaluate some parts of the fishery-specific management system | FEDECOOP | PNO/INAPESCA | July 2019 | December 2025 | Evaluation mechanisms defined and endorsed |
|  | 8.2.Review periodically the fishery-specific management system | FEDECOOP | PNO/INAPESCA | July 2020 | December 2027 | Agreement on a periodically review and management system with adjustments and referendums |

## Additional Impacts

| Social impact | It focuses on the development of good practices on board and the certification of the FTUSA capture fishing standard that will lead to a formal fair trade, involving aspects such as community development, respect for human and labor rights. |
| --- | --- |
| Status Summary | Currently, two of the 9 cooperatives that participate in the FIP are certified in good handling practices on board. Fair Trade paid a visit to the Coop. Punta Abreojos to observe the fishing activity, the processing facilities and learn about the existing models for the verdillo market to certify the verdillo fishery in the FTUSA Capture Fishing Standard; the certification process was postponed due to the COVID 19 health contingency. |
| Improvement Recommendation | It is recommended that the rest of the cooperatives be certified in good handling practices on board and continue with the certification process by Fair Trade. |

| Supply Chain Roundtable | The participation of the barred sand bass fishery is expected to provide new markets focused on sustainable products. |
| --- | --- |
| Status Summary | The verdillo fishery has characteristics that make it a sustainable product and potential to be placed in preferential markets, complying with standards that guarantee the quality of the product. Being a fishery that is part of an active FIP, it is an environmentally and socially responsible product. |
| Improvement Recommendation | Due to the characteristics of the barred sand bass fishery, this product has the potential to be incorporated into the international market as part of the Fishpeople supply chain. |

| Traceability | This additional impact aims to evaluate alternatives that allow establishing an efficient traceability system that meets the requirements of the fishery and that can be applied to all fisheries. |
| --- | --- |
| Status Summary | The SmartFish organization supports the cooperatives that make up the barred sand bass FIP in installing a traceability system that will serve the fisheries that are used by the cooperatives. The feasibility of implementing tools such as GoTrace to establish a traceability system that is easy to use and has a low operating cost has been evaluated. |
| Improvement Recommendation | It is recommended to evaluate the most appropriate needs and options to establish a traceability system that is suitable for all fisheries |