- Action Plan Overview

Table 1: Action Plan Overview

| Fishery name: | White Shrimp and Spotted Shrimp | Fishery location: | Kotabaru Waters (WPP-713) |
| --- | --- | --- | --- |
| Fishing method/gear: | Trammel Net | Fishery in ITM program? (Applicant/Yes/No): | Yes |
| Started date (expected): |  | End date (anticipated month/year of entering Full Assessment): |  |
| August, 2021 |  | July, 2026 |  |
| Project leaders (organisation/individual responsible for Action Plan): |  | Improvements recommended by (meeting/group that supported the development): |  |
| Fisheries and Marine Department of South Kalimantan Province |  | South Kalimantan Province Fishery Stakeholders |  |
| FIP Coordinator/ ITM Project Manager (name, affiliation and position if applicable): |  | Action Plan developed by (consultant or person): |  |
| PT. Sekar Laut, Tbk |  | WWF Indonesia Heri |  |
| Overview of the Action Plan (Add/delete as appropriate): |  |  |  |
| Principle 1 Sustainable utilization of shrimp based on stock status and reference point of harvest strategy that is obtained through collecting and regular monitoring fishery data Principle 2 Minimizing the impact of fisheries on secondary species, ETP species and their habitats through appropriate management as needed Principle 3 Encouraging the management of shrimp fisheries in South Kalimantan involving relevant stakeholders, i.e. the decision-making process, compliance and law enforcement, as well as evaluation in management |  |  |  |
| References (document/s on which the Action Plan was based): |  |  |  |
| The results of the pre-assessment of shrimp fisheries against MSC standards conducted by the Bio Inspecta team in 2020 |  |  |  |

Table 2: Action Plan Overview Performance Indicator detail

| Performance Indicator (PI) | Action ID and Name | Timescale |
| --- | --- | --- |
| 1.1.1 Stock status | Action 2: Conduct stock assessment for White Shrimp and Spotted Shrimp on UoA (Unit of Assessment) | 60 months |
| 1.1.2 Stock rebuilding | - |  |
| 1.2.1 Harvest Strategy | Action 3. Develop a harvest strategy and harvest control rules | 60 months |
| 1.2.2 Harvest control rules and tools | Action 3. Develop a harvest strategy and harvest control rules | 60 months |
| 1.2.3 Information and monitoring | Action 1. Implementation of data collection and data monitoring of shrimp fishery with appropriate method that suitable for target species in UoA (Unit of Assessment) | 48 months |
| 1.2.4 Assessment of stock status | - |  |
| 2.1.1 Primary species outcome | - |  |
| 2.1.2 Primary species management | - |  |
| 2.1.3 Primary species Information & monitoring | - |  |
| 2.2.1 Secondary species outcome | Action 4. Monitoring of bycatch and ecosystem status | 60 months |
| 2.2.2 Secondary species management | Action 4. Monitoring of secondary species & ETP, along with management option as needed Action 7. Develop Fisheries Management Plan FMA 713 for Shrimp fishery | 60 months |
| 2.2.3. Secondary species Information & monitoring | Action 4. Monitoring of bycatch and ecosystem status | 60 months |
| 2.3.1 ETP species Outcome | Action 4. Monitoring of bycatch and ecosystem status | 60 months |
| 2.3.2 ETP species management | Action 4. Monitoring of bycatch and ecosystem status Action 7. Develop Fisheries Management Plan FMA 713 for Shrimp fishery | 60 months |
| 2.3.3 ETP Species Information & monitoring | Action 4. Monitoring of bycatch and ecosystem status | 60 months |
| 2.4.1 Habitats Outcome | - |  |
| 2.4.2 Habitat management strategy | Action 5. Habitat-ecosystem Action 7. Develop Fisheries Management Plan FMA 713 for Shrimp fishery | 60 months |
| 2.4.3 Habitat information | Action 5. Habitat-ecosystem | 60 months |
| 2.5.1 Ecosystem outcome | Action 4. Monitoring of bycatch and ecosystem status | 60 months |
| 2.5.2 Ecosystem management strategy | Action 4. Monitoring of bycatch and ecosystem status Action 5. Habitat-ecosystem Action 7. Develop Fisheries Management Plan FMA 713 for Shrimp fishery | 60 months |
| 2.5.3 Ecosystem information | Action 4. Monitoring of bycatch and ecosystem status | 60 months |
| 3.1.1 Legal and/or customary framework | Action 6. Law enforcement Action 7. Develop Fisheries Management Plan FMA 713 for Shrimp fishery | 24 months |
| 3.1.2 Consultation, roles & responsibilities | Action 6. Law enforcement Action 7. Develop Fisheries Management Plan FMA 713 for Shrimp fishery | 24 months |
| 3.1.3 Long-term objectives | - |  |
| 3.2.1 Fishery-specific objectives | Action 2: Conduct stock assessment for White Shrimp and Spotted Shrimp on UoA (Unit of Assessment) | 60 months |
| 3.2.2 Decision-making processes | Action 7. Develop Fisheries Management Plan FMA 713 for Shrimp fishery | 53 months |
| 3.2.3 Compliance & enforcement | Action 6. Law enforcement | 24 months |
| 3.2.4 Monitoring and management performance evaluation | Action 7. Develop Fisheries Management Plan FMA 713 for Shrimp fishery Action 3. Develop a harvest strategy and harvest control rules | 53 months |

- Actions at Performance Indicator and/or Scoring Issue level

Table 3.  Performance Indicator Action Plan table for Action 1

| Action ID no | Action 1 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action Name | Implementation of data collection and data monitoring of shrimp fishery with appropriate method that suitable for target species in UoA (Unit of Assessment) |  |  |  |  |  |
| Action Goal | An agreed method for conducting species level studies and population structure of trammel net catch species in the UoA |  |  |  |  |  |
| Action summary | Collecting information regarding target species as reference for management option, such as; - The catch composition of White Shrimp and Spotted Shrimp - Biological assessment for target species to support stock status assessment - Growth, gonadal maturation and life cycle - Overview of capture trends; catch composition of each species and size, as well as fishing season information. |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | PI 1.2.3 (SG <60) |  |  |  |  |  |
| Date of completion | July 2025 |  |  |  |  |  |
| Task/s No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources - Time | Date of completion | Evidence of completion |
| A.1.1 Stakeholder meeting with academics or researchers to agree on methods and data requirements by developing a data collecting protocol to support population structure analysis of shrimp-trammel net fishing in the UoA (Unit of Assessment) | BRIN, DKP Province, Lambung Mangkurat University, Brawijaya University | DJPT-KKP, DKP Kotabaru, PPI Kotabaru, PT. Sekar Laut, & PT. Sahabat Laut Lestari | 4000 USD | 6 months | Aug 21 - Jan 22 | Agreement on methods and data requirements by developing a data collecting protocol to support population structure analysis of shrimp-trammel net fishing in the UoA (Unit of Assessment) |
| A.1.2 Conduct training for enumerators/fishermen on collecting required data | BRIN, DKP South Kalimantan Province | Lambung Mangkurat University, Brawijaya University, DJPT-KKP, DKP Kotabaru, PPI Kotabaru, PT. Sekar Laut, Enumerator, Instructor, and PT. Sahabat Laut Lestari | 1000 USD | 2 months | Feb 22 - March 22 | Report on data collecting training activities for shrimp fishermen/ enumerators in UoA & availability of enumerators |
| A.1.3 Collecting biological data and catch production of trammel net according to agreed protocols Note: data collection adapts to the data requirements of the agreed methodology | BRIN, DKP South Kalimantan Province | Lambung Mangkurat University, Brawijaya University, DJPT-KKP, DKP Kotabaru, PPI Kotabaru, PT. Sekar Laut, Enumerator, Instructor, and PT. Sahabat Laut Lestari |  | 28 months | April 22 - July 25 | Availability of biological data and production of species caught by trammel net; yearly data report |

Table 4.  Performance Indicator Action Plan table for Action 2

| Action ID no | Action 2 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Conduct stock assessment for White Shrimp and Spotted Shrimp on UoA (Unit of Assessment |  |  |  |  |  |
| Action Goal | Understand the stock status of target species and its geographical boundaries in the UoAs |  |  |  |  |  |
| Action summary | After agreeing on the appropriate management approach for the target species in the UoA, then conducting a study to determine the reference point for the white shrimp and spotted shrimp in the UoA. |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | PI 1.1.1 (SG <60) |  |  |  |  |  |
| Date of completion | July 2026 |  |  |  |  |  |
| Task/s No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources - Time | Date of completion | Evidence of completion |
| A.2.1 Meeting of stakeholders, academics and researchers in determining the method of assessing shrimp stocks | BRIN, Komnas Kajiskan, Lambung Mangkurat University, Brawijaya University | DJPT-KKP, DKP South Kalimantan Province, DKP Kotabaru, PPI Kotabaru, PT. Sekar Laut, and PT. Sahabat Laut Lestar | 10000 USD | 28 months | Aug 21 – Nov 23 | Agreement on method for conducting stock shrimp status assessment |
| A.2.2 Conduct stock status assessment and determination of reference points for the utilization of target species based on data collection that has been carried out using agreed methods | BRIN, Komnas Kajiskan | Lambung Mangkurat University, Brawijaya University, DJPT-KKP, DKP South Kalimantan Province, DKP Kotabaru-Tanah Bumbu, PPI Kotabaru, PT. Sekar Laut, and PT. Sahabat Laut Lestari | 15000 USD | 24 months | Aug 22 - July 24 | Availability of results of shrimp stock status studies and reference points for target species utilization |
| A.2.3 Review stock status relative to reference points annually (or on a timeframe appropriate to the life history characteristics of the target species) | BRIN, Komnas Kajiskan | Lambung Mangkurat University, Brawijaya University, DJPT-KKP, DKP South Kalimantan Province, DKP Kotabaru-Tanah Bumbu, PPI Kotabaru, PT. Sekar Laut, and PT. Sahabat Laut Lestari | 5000 USD | 24 months | Aug 24 - July 26 | Review report |

Table 5.  Performance Indicator Action Plan table for Action 3

| Action ID no | Action 3 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Develop a harvest strategy and harvest control rules |  |  |  |  |  |
| Action Goal | A harvest strategy for shrimp fisheries in UoA that incorporated annual review mechanism along with the harvest control rules |  |  |  |  |  |
| Action summary | Develop a harvest strategy to keep the target species stock in healthy condition, with agreed objectives, by stakeholders in the UoA. The harvest strategy should also subject to be review annually transparently. Monitoring and periodic review should be taking in place to make sure that the harvest strategy is working and achieve its objective to maintain stocks at target level, and being improved as necessary. |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | PI 1.2.1 (SG <60) PI 1.2.2 (SG <60) PI 3.2.4 (SG <60) |  |  |  |  |  |
| Date of completion | July 2026 |  |  |  |  |  |
| Task/s No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources - Time | Date of completion | Evidence of completion |
| A.3.1 Develop a draft of harvest strategy for shrimp utilization and its reference points in the UoA | BRIN, , Komnas Kajiskan, DJPT-KKP | DKP South Kalimantan | 5000 USD | 24 months | Jan 22 – Dec 23 | Availability of Shrimp utilization strategy documents and reference points draft in UoA |
| A.3.2 Stakeholder meeting to determine the option of reference point for utilization that will be included in the shrimp harvest strategy in the UoA. | DJPT-KKP | BRIN, , Komnas Kajiskan DKP South Kalimantan Province, Lambung Mangkurat University, DKP South Kalimantan Province | 5000 USD | 12 months | Jan 24 – Dec 24 | Availability of reference point options for shrimp utilization in the UoA which have been discussed by stakeholders. |
| A.3.3 Public consultation of the shrimp harvest strategy draft in the UoA | DJPT-KKP | BRIN, , Komnas Kajiskan, Lambung Mangkurat University, DKP South Kalimantan Province, DKP Kotabaru-Tanah Bumbu, Fishing Port, PT. Sekar Laut, and PT. Sahabat Laut Lestari | 5000 USD | 6 months | Jan 25 – June 25 | Report on public consultation activities related to shrimp harvest strategy documents in UoA |
| A.3.4 Ratification of shrimp harvest strategy in UoA | DKP South Kalimantan Province/POKJA | DJPT-KKP, Law Firm KKP, BRIN, , Komnas Kajiskan, Lambung Mangkurat University, DKP South Kalimantan Province, DKP Kotabaru PT. Sekar Laut, and PT. Sahabat Laut Lestari | 5000 USD | 10 months | July 25 – April 26 | Availability of regulations on shrimp harvest strategies in the UoA that have been ratified |
| A.3.5 Undertake an evaluation of the performance of the harvest strategy as per the timetable set out in the fishery management plan. | BRIN, , Komnas Kajiskan | DJPT-KKP, KKP Law Firm, Lambung Mangkurat University, DKP South Kalimantan Province, DKP Kotabaru, PT. Sekar Laut, dan PT. Sahabat Laut Lestari |  | 2 month | April 26 – May 26 | Evaluation report |
| A.3..6. Implement changes to management where indicated as necessary in the harvest strategy evaluation | BRIN, , Komnas Kajiskan | DJPT-KKP, KKP Law Firm, Lambung Mangkurat University, DKP South Kalimantan Province, DKP Kotabaru, PT. Sekar Laut, dan PT. Sahabat Laut Lestari |  | 2 months | May 26 – July 26 | Revised harvest strategy document that incorporated result from harvest strategy evaluation |

Table 6.  Performance Indicator Action Plan table for Action 4

| Action ID no | Action 4 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Monitoring of bycatch and ecosystem status |  |  |  |  |  |
| Action Goal | Monitor bycatch status which include secondary species and ETP and also ecosystem status, along with determining their option based on study and necessity |  |  |  |  |  |
| Action summary | Bycatch stock and ecosystem status monitoring is carried out to monitor the condition of bycatch stock from the trammel net impact. For the initial phase, carried out the data collection side of the catch, if known condition status of bycatch needs to stock rebuilding, there will be measures to improve the management of the stock status. The bycatch include secondary species and ETP. This action will also monitor and collect evidence on management measures implementation to ensure the fishery does not pose a risk of serious or irreversible harm to the ecosystem. |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | PI 2.2.1 (SG 60-79) PI 2.2.2 (SG <60) PI 2.2.3 (SG <60) PI 2.3.1 (SG 60-79) PI 2.3.2 (SG 60-79) PI 2.3.3 (SG 60-79) PI 2.5.1 (SG 60-79) PI 2.5.2 (SG 60-79) PI 2.5.3 (SG 60-79) |  |  |  |  |  |
| Date of completion | July 2026 |  |  |  |  |  |
| Task/s No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources - Time | Date of completion | Evidence of completion |
| A.4.1 Preparing a bycatch (secondary species & ETP) data collection form with experts | Lambung Mangkurat University, BRIN | KKHL-KKP, DJPT-KKP Fishery Instructor, DKP South Kalimantan Province, DKP Kotabaru-Tanah Bumbu | 5000 | 5 months | Aug 21 – Dec 21 | Availability of bycatch data collection form |
| A.4.2 Training for enumerators or observers on bycatch data collection (secondary species & ETP) in accordance with agreed-form and also e-log book | DKP Kotabaru | DJPT-KKP, DKP South Kalimantan Province, PT. Sekar Laut, Enumerator, Fishery Instructor, PT. Sahabat Laut Lestari | 5000 | 3 months | Jan 22 – Mar 22 | Report on enumerators or observers training in the use of agreed from & e-log books |
| A.4.3 Bycatch data collection (secondary species & ETP) using the agreed-form and e-log book | DKP Kotabaru | DJPT-KKP, DKP South Kalimantan Province, PT. Sekar Laut, Enumerator, Fishery Instructor, PT. Sahabat Laut Lestari | 3000 | 24 months | Jan 22 – Dec 24 | Bycatch data available |
| A.4.4 Dissemination and public consultation of bycatch data collection results (secondary species & ETP) | DKP South Kalimantan Province/POKJA | DJPT-KKP, BRIN, Law Firm KKP, BRIN, , Komnas Kajiskan, Lambung Mangkurat University, DKP Kotabaru, PT. Sekar Laut, dan PT. Sahbat Laut Lestari. | 1500 | 1 month | Jan 25 – Feb 25 | the availability of a report on the results of the dissemination, along with recommendations for habitat-ecosystem management options |
| A.4.5 Hold meetings and agree on bycatch management options (secondary species & ETP) | DKP South Kalimantan Province/POKJA | DJPT-KKP, BRIN, Law Firm KKP, BRIN, , Komnas Kajiskan, Lambung Mangkurat University, DKP Kotabaru, PT. Sekar Laut, dan PT. Sahbat Laut Lestari. | 1500 | 2 months | Feb 25 – Apr 25 | Report availability for bycatch management options that agreed by the stakeholders |
| A.4.6 Annual meeting to evaluate bycatch data collection (secondary species & ETP) | BRIN, | DJPT-KKP, DKP South Kalimantan, Law Firm KKP, BRIN, , Komnas Kajiskan, Lambung Mangkurat University, DKP Kotabaru, PT. Sekar Laut, dan PT. Sahbat Laut Lestari. | 3000 | 4 months | Dec 22 – July 26 | Availability of activity reports on evaluation of data collection and existing bycatch management option |

Table 7.  Performance Indicator Action Plan table for Action 5

| Action ID no | Action 5 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Habitat-ecosystem |  |  |  |  |  |
| Action Goal | Monitoring the condition of the habitat-ecosystem as a recommendation for management option as needed |  |  |  |  |  |
| Action summary | Information regarding the structure of the habitat at the fishing ground of trammel net and impact of the fishing activities need to be collected and confirm. From the data collection activities, if there's information indicate that fishing activities might cause irreversible harm to the habitat, then there will be a need to make management measures as part of this action. |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | PI 2.4.2 (SG <60) PI 2.4.3 (SG 60-79) PI 2.5.1 (SG 60-79) PI 2.5.2 (SG 60-79) PI 2.5.3 (SG 60-79) |  |  |  |  |  |
| Date of completion | July 2026 |  |  |  |  |  |
| Task/s No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources - Time | Date of completion | Evidence of completion |
| A.5.1 Conduct a study on the impact of shrimp catching activities using trammel nets on the habitat-ecosystem. | BRIN, | Lambung Mangkurat University | 5000 USD | 24 months | Jan 22 – Dec 23 | Availability of results of studies on the impact of trammel net activities on bycatch and ecosystems. |
| A.5.2 Conduct a study and inventory of coral reef and mangrove ecosystems mapping in the UoA (Unit of Assessment) area | Lambung Mangkurat University | PRL-KKP, LAPAN/LIPI-P2O, BRIN, KLHK/BKSDA | 5000 | 12 months | Jan 22 – Dec 22 | Availability of maps of coral reef and mangrove ecosystems distribution in the target area |
| A.5.3 Mapping of fishing ground for fishermen and installation of tracking system (AIS) on targeted fishermen | PT. Sekar Laut | DKP Kotabaru-Tanah Bumbu, Fishery Instructor, DKP South Kalimantan Province | 3000 | 24 months | Jan 22 – Dec 23 | Availability of maps resulting from mapping the fishing ground of fishermen |
| A.5.4 Hold a meeting to agree habitat-ecosystem management options | DKP South Kalimantan Province/POKJA | PRL-KKP, BRIN, , DJPT-KKP, KLHK/BKSDA, Law Firm KKP, BRIN, , Komnas Kajiskan, Lambung Mangkurat University, DKP Kotabaru-Tanah Bumbu, Fishing Port, PT. Sekar Laut, and PT. Sahabat Laut Lestari | 3000 | 2 months | Jan 24 – Feb 24 | The report on the results of the habitat-ecosystem management option that agreed by the stakeholders |
| A.5.5 Annual meeting evaluation of existing habitat-ecosystem management in the UoA | DKP South Kalimantan Province/POKJA | PRL-KKP, BRIN, , DJPT-KKP, Law Firm KKP, BRIN, , Komnas Kajiskan, Lambung Mangkurat University, DKP Kotabaru-Tanah Bumbu, Fishing Port, PT. Sekar Laut, and PT. Sahabat Laut Lestari. | 3000 | 4 months | March 24 – July 26 | Availability of management evaluation for habitat-ecosystem within UoA |

Table 8.  Performance Indicator Action Plan table for Action 6

| Action ID no | Action 6 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Law enforcement |  |  |  |  |  |
| Action Goal | The existing fisheries and marine management rules can be implemented by means of effective monitoring process |  |  |  |  |  |
| Action summary | FIP will need to empower community and establishes groups known as Pokmaswas to control and monitor fishing activities, as community-based surveillance groups. This mechanism includes the participation from a range of stakeholders and includes training to understand the legislation. The groups should also has mechanism in place to make sure all the law enforcement and sanction being implemented are deterrent to make sure all the related law and fishery regulation being effectively implemented. |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | PI 3.1.1 (SG 60-79) PI 3.1.2 (SG 60-79) PI 3.2.3 (SG <60) |  |  |  |  |  |
| Date of completion | July 2026 |  |  |  |  |  |
| Task/s No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources - Time | Date of completion | Evidence of completion |
| A.6.1 Establish a Work Group (Kelompok Kerja-POKJA) for shrimp fisheries management in South Kalimantan Province | DKP South Kalimantan Province | BRIN, , DJPT-KKP, Law Firm KKP, BRIN, , Komnas Kajiskan, Lambung Mangkurat University, DKP Kotabaru, PT. Sekar Laut, and PT. Sahabat Laut Lestari | 5000 USD | 12 months | Aug 21 – July 22 | Availability of SK (legal letter) for POKJA of shrimp fisheries management in South Kalimantan |
| A.6.2 Facilitation of fishermen in fulfilling vessel registration through BPKP documents and small passes (pas kecil) | DKP South Kalimantan Province/POKJA | BRIN, , DJPT-KKP, Law Firm KKP, BRIN, , Komnas Kajiskan, Lambung Mangkurat University, DKP Kotabaru, PT. Sekar Laut, and PT. Sahabat Laut Lestari | 2000 USD | 8 months | Aug 21 – April 22 | Supplying fisher have BPKP and small pass |
| A.6.3 Dissemination of existing fisheries and marine regulatory instruments in the target area to the fishermen and stakeholders | DKP South Kalimantan Province/POKJA | BRIN, , DJPT-KKP, Law Firm KKP, BRIN, , Komnas Kajiskan, Lambung Mangkurat University, DKP Kotabaru, PT. Sekar Laut, and PT. Sahabat Laut Lestari | 3000 USD | 6 month | Jan 22 – June 22 | Dissemination report |
| A.6.4 Carry out regular patrols and surveillance together with relevant stakeholders in South Kalimantan | PSDKP | BRIN, , DJPT-KKP, Law Firm KKP, BRIN, , Komnas Kajiskan, Lambung Mangkurat University, DKP Kotabaru, PT. Sekar Laut, and PT. Sahabat Laut Lestari | 15000 USD | 55 months | Jan 22 – June 26 | Patrol results report available, which detailing sanction and law enforcement being taken and implemented and proven to be effective. |

Table 9.  Performance Indicator Action Plan table for Action 7

| Action ID no | Action 7 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action name | Develop Fisheries Management Plan FMA 713 for Shrimp fishery |  |  |  |  |  |
| Action Goal | Developing a robust Fisheries Management Plan for Shrimp fishery in FMA 713, that include long and short term objectives, a clear decision making process, and all management aspect related to the fishery that consistent with MSC Principle 1 and 2 |  |  |  |  |  |
| Action summary | The Fisheries Management Plan for FMA 713 has not included shrimp specific management measures. The Fisheries Management Council 713 that managed FMA 713 based on Ministerial Decree 80/2016 need to engaged to develop shrimp specific management plan as a subset in the FMA. The management plan should include long and short term objectives with clear decision making process. The FIP also will ensure the fishery management plan that being developed, has incorporated mechanism to evaluate all parts of the fishery-specific management system and subject to internal and external review Per May 2021 there was new permen (Permen 22/2021) that regulate the Fisheries Management Council for each FMA, listing all stakeholders in the FMA and also steps in develop the management plan. It also mandate reguler review on the implementation (minimum once every two year). |  |  |  |  |  |
| Performance Indicator(s) and/or Scoring Issue(s) | PI 2.2.2 (SG <60) PI 2.3.2 (SG 60-79) PI 2.4.2(SG <60) PI 2.5.2 (SG 60-79) PI 3.1.1 (SG 60-79) PI 3.1.2 (SG 60-79) PI 3.2.1(SG <60) PI 3.2.2(SG <60) PI 3.2.4(SG <60) |  |  |  |  |  |
| Date of completion | Dec 2025 |  |  |  |  |  |
| Task/s No. | Responsible – Action lead | Responsible – Action partners | Resources – Cost | Resources - Time | Date of completion | Evidence of completion |
| A.7.1 Review Fisheries Management Plan of FMA 713 and assess the possibility to include shrimp fishery (as a sub set) | DKP South Kalimantan Province/POKJA | BRIN, , DJPT-KKP, Law Firm KKP, BRIN, , Komnas Kajiskan, Lambung Mangkurat University, DKP Kotabaru-Tanah Bumbu, Fishing Port, PT. Sekar Laut, and PT. Sahabat Laut Lestari Indonesia | - | 4 months | Sep 21 – Dec 21 | Review report |
| A.7.2 Join FMC meetings whenever possible | PT. Sekar Laut | DKP South Kalimantan Province | 3000 USD | 60 months | Aug 21-July 26 | Availability of peer review activity reports of the agreed FIP action plan |
| A.7.3 Develop a draft of Shrimp Fisheries Management Plan | DJPT-KKP, BRIN, Pusrsikan, Komnaskajiskan, DKP South Kalimantan Province | Lambung Mangkurat University, DKP Kotabaru-Tanah Bumbu, Fishing Port, PT. Sekar Laut, and PT. Sahabat Laut Lestari | 6000 USD | 40 months | Jan 22 – Apr 25 | Draf of FMP |
| A. 7.4. Finalize Shrimp Fisheries Management Plan | DJPT-KKP, BRIN, Pusrsikan, Komnaskajiskan, DKP South Kalimantan Province | Lambung Mangkurat University, DKP Kotabaru-Tanah Bumbu, Fishing Port, PT. Sekar Laut, and PT. Sahabat Laut Lestari | 2000 USD | 6 months | May 25 – Dec 25 |  |