## Canada Newfoundland and Labrador Lobster – Pot/Trap

## Fishery Improvement Project (FIP) Workplan

Table 1: Workplan Overview

| Workplan Version and Date | Version 2, January 15, 2025 |
| --- | --- |
| Start date (expected) | End date (anticipated month/year) |
| January 2025 | April 2027 |
| FIP Lead (organization/individual responsible for Action Plan) | Improvements recommended by (meeting/group that supported the development) |
| Association of Seafood Producers | Three Year Evaluation |
| FIP Coordinator (organization/individual responsible for reporting on FisheryProgress) | Workplan developed by (consultant or person) |
| Renae Butler | Renae Butler with review by Steve Devitt |

#### Acronyms

| ASP | Association of Seafood Producers |
| --- | --- |
| DFO | Fisheries and Oceans Canada |
| FAO | Food and Agriculture Organization of the United Nations |
| FFAW | Fish, Food and Allied Workers Union |
| FIP | Fishery Improvement Project |
| HCR | Harvest Control Rule |
| HS | Harvest Strategy |
| IFMP | Integrated Fisheries Management Plan |
| LRP | Limit Reference Point |
| MLS | Minimum Legal Size |
| MSC | Marine Stewardship Council |
| PA | Precautionary Approach |
| PRI | Point at which Recruitment is Impaired |
| Rep. | Representative |
| RPs | Reference Points |
| PI | Performance Indicator |
| UoA | Unit of Assessment |

#### Unit of Assessment(s)

Table 2. Unit(s) of Assessment (UoA)

| UoA 1 | Description |
| --- | --- |
| Target species (common and scientific name) | American Lobster (Homarus americanus) |
| Stock | Newfoundland and Labrador |
| Geographical area | Lobster Fishing Areas (LFA) 3-14 |
| Fishing method or gear type | Baited pot/trap |
| Fishing fleet or group of vessels, or individuals fishing operators pursuing stock | Newfoundland and Labrador licensed harvesters |

## FIP Actions

Table 3. Performance Indicator Action Plan Table for Principle 1: Sustainability of Fish Stocks

| Action Number and Name (One sentence description) | 1: Support DFO in applying a precautionary approach framework. |
| --- | --- |
| Action Goal (One sentence that describe the result of the action) | Work with DFO and other stakeholders to create and apply a precautionary approach framework and define reference points. |
| Action Description (Brief summary of the steps involved in the action and importance of the action in achieving the FIP objectives) | Work with DFO and other stakeholders including harvesters, processors and ENGOs, through a CSAS process in support of developing a precautionary approach framework with multi-indicator approach, and support the development of an LRP and Harvest Control Rules |
| Expected Completion Date | April 2027 |
| Priority (Based on the implementers criteria: e.g., lowest scoring issues are high priority or actions that are necessary to complete before beginning other actions are high priority) | Medium |
| Estimated Cost (An estimate of the budget needed to complete the action) | $20,000 CAD, plus in-kind industry and DFO contribution. |
| Responsible Parties (List of participants) | ASP, DFO, FFAW |
| MSC Performance Indicator(s) Addressed by the Action (The MSC performance indicator(s) that are directly impacted by the action. The completion of the action is likely to result in an improved score change for these performance indicators) | 1.1.1. Stock Status 1.2.1 Harvest Strategy 1.2.2 Harvest Control Rules and Tools |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 1: Support DFO in applying a precautionary approach framework. | DFO peer review proposal with stakeholders | DFO | ASP, FFAW | November 2024 | November 2025 | Published Precautionary Approach Framework Proposal. |
|  | DFO finalize Precautionary Approach Framework | DFO | ASP, FFAW | November 2025 | April 2027 | Implemented Precautionary Approach Framework |

Table 4. Performance Indicator Action Plan Table for Principle 1: Sustainability of Fish Stocks

| Action Number and Name (One sentence description) | 2. Determine undersize capture and escape mechanism analysis. |
| --- | --- |
| Action Goal (One sentence that describe the result of the action) | DFO update the NL Lobster Integrated Fisheries Management Plan (IFMP). |
| Action Description (Brief summary of the steps involved in the action and importance of the action in achieving the FIP objectives) | During the three-year evaluation of this FIP, DFO were confident that any undersize lobster is immediately sorted and put back in the ocean, as having any non-legal sized on board is a serious offence. A gauge is available to measure lobsters quickly and easily, and handling protocols for v-notching berried females and returning them to the water. DFO did not believe that the escape gap needed any adjustment and were confident that the mortality of undersized lobster from the fishery was negligible. An update to the IFMP would reiterate management measures and the conservation and protection plan related to implementing the harvest strategy. The legal requirements are also communicated to each harvester in their Conditions of Licence. |
| Expected Completion Date | June 2025 |
| Priority (Based on the implementers criteria: e.g., lowest scoring issues are high priority or actions that are necessary to complete before beginning other actions are high priority) | High |
| Estimated Cost (An estimate of the budget needed to complete the action) | $10,000 CAD, plus in-kind industry and DFO contribution |
| Responsible Parties (List of participants) | ASP, DFO, FFAW |
| MSC Performance Indicator(s) Addressed by the Action (The MSC performance indicator(s) that are directly impacted by the action. The completion of the action is likely to result in an improved score change for these performance indicators) | 1.2.1 Harvest Strategy |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| DFO to Update IFMP | Update of IFMP | DFO | ASP | January 2025 | June 2025 | Updated IFMP |

Table 5. Performance Indicator Action Plan Table for Principle 1: Sustainability of Fish Stocks

| Action Number and Name (One sentence description) | 3. Improve consistency and monitoring of lobster removals |
| --- | --- |
| Action Goal (One sentence that describe the result of the action) | Improvement of catch reporting. |
| Action Description (Brief summary of the steps involved in the action and importance of the action in achieving the FIP objectives) | A move from paper to electronic logbooks will improve lobster landing data and processing time. Elogs are being rolled out in select NL fisheries in spring 2025. DFO is also reminding of the importance of returning their logbooks and purchase slips https://www.nfl.dfo-mpo.gc.ca/en/node/2223. |
| Expected Completion Date | June 2026 |
| Priority (Based on the implementers criteria: e.g., lowest scoring issues are high priority or actions that are necessary to complete before beginning other actions are high priority) | Medium |
| Estimated Cost (An estimate of the budget needed to complete the action) | $10,000 CAD, plus in-kind industry and DFO contribution |
| Responsible Parties (List of participants) | ASP, DFO, FFAW |
| MSC Performance Indicator(s) Addressed by the Action (The MSC performance indicator(s) that are directly impacted by the action. The completion of the action is likely to result in an improved score change for these performance indicators) | 1.2.3 Information and Monitoring |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Improve consistency and monitoring of lobster removals | Implementation of Elogs Improved data | DFO | ASP | January 2025 | June 2026 | Improved data return rates. |

Table 6. Performance Indicator Action Plan Table for Principle 2: Minimizing Environmental Impacts

| Action Number and Name (One sentence description) | 4. Determine lobster-specific bait usage |
| --- | --- |
| Action Goal (One sentence that describe the result of the action) | Gathering and analysis of qualitative information regarding quantity, species and provenance of bait use in the lobster fishery. |
| Action Description (Brief summary of the steps involved in the action and importance of the action in achieving the FIP objectives) | Conduct a confidential survey of harvesters and bait suppliers. |
| Expected Completion Date | January 2026 |
| Priority (Based on the implementers criteria: e.g., lowest scoring issues are high priority or actions that are necessary to complete before beginning other actions are high priority) | High |
| Estimated Cost (An estimate of the budget needed to complete the action) | $12,000 plus in-kind industry and DFO contribution |
| Responsible Parties (List of participants) | ASP, DFO, FFAW |
| MSC Performance Indicator(s) Addressed by the Action (The MSC performance indicator(s) that are directly impacted by the action. The completion of the action is likely to result in an improved score change for these performance indicators) | 2.1.3 Primary species information |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Determine lobster-specific bait usage | Perform a survey and tally results | ASP | FFAW | March 2025 | January 2026 | Completed survey. |

Table 7. Performance Indicator Action Plan Table for Principle 2: Minimizing Environmental Impacts

| Action Number and Name (One sentence description) | 5. Determine bycatch and ETP species encounters |
| --- | --- |
| Action Goal (One sentence that describe the result of the action) | Determine the impact of bycatch encounters in lobster trap fishery on status of secondary species stocks And ETP species |
| Action Description (Brief summary of the steps involved in the action and importance of the action in achieving the FIP objectives) | Improved logbook returns/implementation of Elogs will support this action by improving data return and reporting. Harvesters are required to report any SARA species in their logbooks and retention of bycatch of other species is not permitted per the Fishery (General) Regulations. Harvesters are required to report any sightings or interactions with North Atlantic Right Whales |
| Expected Completion Date | January 2027 |
| Priority (Based on the implementers criteria: e.g., lowest scoring issues are high priority or actions that are necessary to complete before beginning other actions are high priority) | Medium |
| Estimated Cost (An estimate of the budget needed to complete the action) | $14,000 plus in kind industry and DFO contributions |
| Responsible Parties (List of participants) | ASP, DFO, FFAW |
| MSC Performance Indicator(s) Addressed by the Action (The MSC performance indicator(s) that are directly impacted by the action. The completion of the action is likely to result in an improved score change for these performance indicators) | 2.2.3 Secondary species information 2.3.1 ETP species outcome 2.3.2 ETP species management 2.3.3 ETP species information |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Determine bycatch encounters | Improved return data on bycatch and ETP interactions | DFO | ASP | January 2025 | January 2027 | Data showing a minimal impact of the lobster fishery on secondary species |