## Indonesia Indian Ocean skipjack tuna – pole & line

## Fishery Improvement Project (FIP) Workplan

Table 1: Workplan Overview

| Workplan Version and Date | 2.0 |
| --- | --- |
| Start date (expected) | End date (anticipated month/year) |
| January 2025 | December 2029 |
| FIP Lead (organization/individual responsible for Action Plan) | Improvements recommended by (meeting/group that supported the development) |
| - Indonesian Pole&line and Handline Fisheries Association (AP2HI) - International Pole&line Foundation (IPNLF) | - Indonesian Pole&line and Handline Fisheries Association (AP2HI) - International Pole&line Foundation - Masyarakat dan Perikanan Indonesian (MDPI) Foundation |
| FIP Coordinator (organization/individual responsible for reporting on FisheryProgress) | Workplan developed by (consultant or person) |
| Indonesian Pole&line and Handline Fisheries Association (AP2HI) | Ilham Alhaq and Herman |
| International Pole&line Foundation | Maskur Tamanyira |
| Masyarakat dan Perikanan Indonesia (MDPI) Foundation | Riza Baroqi |

#### Acronyms

| AP2HI | Indonesian Pole&line and Handline Fisheries Association |
| --- | --- |
| IPNLF | International Pole&line Foundation |
| FIP | Fishery Improvement Project |
| MDPI | Masyarakat dan Perikanan Indonesia |
| MMAF | Ministry of Marine Affairs & Fisheries |
| MSC | Marine Stewardship Council |
| NTMP | National Tuna Management Plan |

#### Unit of Assessment(s)

Fill in the following table, which will be considered the scope against which the fishery is assessed against the MSC Fisheries Standard.

Table 2. Unit(s) of Assessment (UoA)

| UoA 1 | Description |
| --- | --- |
| Target species (common and scientific name) | Skipjack Tuna (Katsuwonus pelamis) |
| Stock | Indian Ocean |
| Geographical area | East Nusa Tenggara |
| Fishing method or gear type | Pole and line |
| Fishing fleet or group of vessels, or individuals fishing operators pursuing stock | Indonesian licensed fishers targeting IO Skipjack tuna with pole-and-line or handline fishing gear that part of AP2HI group |
| UoA 2 | Description |
| Target species (common and scientific name) | Skipjack Tuna (Katsuwonus pelamis) |
| Stock | Indian Ocean |
| Geographical area | West Nusa Tenggara |
| Fishing method or gear type | Pole and line |
| Fishing fleet or group of vessels, or individuals fishing operators pursuing stock | Indonesian licensed fishers targeting IO Skipjack tuna with pole-and-line or handline fishing gear that part of AP2HI group |

## FIP Actions

Table 3. Performance Indicator Action Plan Table for Action 1

| Action Number and Name (One sentence description) | 1. National Tuna Management Plan (NTMP) |
| --- | --- |
| Action Goal (One sentence that describe the result of the action) | Ensure the next iteration of the NTMP is compatible with IOTC management measures |
| Action Description (Brief summary of the steps involved in the action and importance of the action in achieving the FIP objectives) | IOTC require that conservation and management measures adopted for areas under national jurisdiction shall be compatible in order to ensure conservation and management of highly migratory fish stocks in their entirety for the stock that covers the entire region not just for the member country EEZ waters. Indonesia is a CMM and cooperates with the RFMO to produce scientific advice. The Indonesian government is responsible for ensuring management measures applied within Indonesian waters are compatible with those of the IOTC, and that fishing by Indonesian vessels is carried out in accordance with any measures put in place by IOTC. This PI requires organized and effective cooperation with other parties to deliver management outcomes consistent with Principles 1 and 2. For Indonesia AWs this is expected to lead to a similar outcome as for IO waters – requiring some local delivery of an equivalent Harvest Strategy and HCR for SKJ (And rebuilding measures for YFT if this is to proceed to MSC assessment). Yet this have not stated clearly in the NTMP particularly for Indian Ocean objectives. |
| Expected Completion Date | December 2027 |
| Priority (Based on the implementers criteria: e.g., lowest scoring issues are high priority or actions that are necessary to complete before beginning other actions are high priority) | Medium |
| Estimated Cost (An estimate of the budget needed to complete the action) | $10,000 USD |
| Responsible Parties (List of participants) | MMAF, AP2HI, IPNLF, MDPI |
| MSC Performance Indicator(s) Addressed by the Action (The MSC performance indicator(s) that are directly impacted by the action. The completion of the action is likely to result in an improved score change for these performance indicators) | 3.1.1 Legal/customary framework 3.2.1 Fishery-specific objectives |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 1. National Tuna Management Plan | Evaluate the NTMP | MMAF | AP2HI, IPNLF, MDPI | June 2025 | June 2026 | Evaluation report and or Evaluation Meeting Minutes |
|  | Review the NTMP | MMAF | AP2HI, IPNLF, MDPI | June 2026 | December 2027 | - Evaluation report - Evaluation Meeting Minutes - New NTMP |

Table 4. Performance Indicator Action Plan Table for Action 2

| Action Number and Name (One sentence description) | 2. Support decision making processes respond to skipjack catches in excess of HCR annual catch limits. |
| --- | --- |
| Action Goal (One sentence that describe the result of the action) | Decision-making processes at IOTC level respond to skipjack catches in excess of HCR annual catch limits. |
| Action Description (Brief summary of the steps involved in the action and importance of the action in achieving the FIP objectives) | Advocacy by Indonesia in support of tuna harvest strategy development is undertaken by MMAF. Outcomes should demonstrate that within IOTC implementation of the harvest strategy set out in Resolution 16/02, or by some other means as appropriate, has been undertaken. |
| Expected Completion Date | December 2029 |
| Priority (Based on the implementers criteria: e.g., lowest scoring issues are high priority or actions that are necessary to complete before beginning other actions are high priority) | Medium |
| Estimated Cost (An estimate of the budget needed to complete the action) | $10,000 USD |
| Responsible Parties (List of participants) | MMAF, AP2HI, IPNLF, MDPI |
| MSC Performance Indicator(s) Addressed by the Action (The MSC performance indicator(s) that are directly impacted by the action. The completion of the action is likely to result in an improved score change for these performance indicators) | 3.2.2 Decision-making processes |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 2. Support decision making processes respond to skipjack catches in excess of HCR annual catch limit | Support Indonesia delegation on annual meeting IOTC | MMAF | AP2HI, IPNLF, MDPI | April 2025 | December 2029 | Meeting minutes Report documents |
|  | Dissemination on IOTC result for Indonesia stakeholders | MMAF | AP2HI, IPNLF, MDPI | May 2025 | December 2029 | Meeting minutes Report document |

Table 5. Performance Indicator Action Plan Table for Action 3

| Action Number and Name (One sentence description) | 3. Support HS development within IOTC |
| --- | --- |
| Action Goal (One sentence that describe the result of the action) | Indonesian support for actions to develop HS within IOTC |
| Action Description (Brief summary of the steps involved in the action and importance of the action in achieving the FIP objectives) | IOTC agreed to a formal management procedure (MP) for skipjack in 2024 (Resolution 24/07), replacing the previous interim HCR (Resolution 21/03). The procedure for setting the catch limit is completely revised from previously. However, the problem for these two PIs for skipjack still remains, in that there is currently no system for allocation of the catch limits such that they are not exceeded. Yellowfin does not have a clear harvest strategy, other than the interim rebuilding plan. The FIP organisations support MMAF to advocate for harvest strategy and harvest control rules to improve management at IOTC ensuring productive yellowfin tuna stocks in the region, including lobbying for progress on catch allocations and for better control and management of drifting FADs (e.g. as cosignatories to a letter to the European Commission on FADs). |
| Expected Completion Date | December 2029 |
| Priority (Based on the implementers criteria: e.g., lowest scoring issues are high priority or actions that are necessary to complete before beginning other actions are high priority) | Medium |
| Estimated Cost (An estimate of the budget needed to complete the action) | $10,000 USD |
| Responsible Parties (List of participants) | MMAF, AP2HI, IPNLF, MDPI |
| MSC Performance Indicator(s) Addressed by the Action (The MSC performance indicator(s) that are directly impacted by the action. The completion of the action is likely to result in an improved score change for these performance indicators) | 1.2.1 Harvest strategy 1.2.2 Harvest control rules & tools |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 3. Support HS development within IOTC | Support Indonesia delegation on annual meeting IOTC | MMAF | AP2HI, IPNLF, MDPI | April 2025 | December 2029 | Meeting minutes Report documents |
|  | Dissemination on IOTC result for Indonesia stakeholders | MMAF | AP2HI, IPNLF, MDPI | May 2025 | December 2029 | Meeting minutes Report document |
|  | Awareness raising for stakeholders in provincial level about what Harvest Strategy and Harvest Control Rules are, and how important to determine HS particularly in IO | BRIN and MMAF | AP2HI, IPNLF, MDPI | May 2025 | December 2029 | Meeting minutes Report document |

## Additional Impacts

Some FIPs include objectives that go beyond the MSC PIs. Please provide additional details below on additional impacts that FIP stakeholders are working to address.

| Addition Impact Title | Additional Impact Description |
| --- | --- |
| Status Summary |  |
| Improvement Recommendation |  |