WORK PLAN UPDATE

FISHERY IMPROVEMENT PROJECT (FIP) OF THE PERUVIAN

LONGLINE MAHI-MAHI FISHERY (Coryphaena hippurus)

Document prepared for WWF-Peru by

Luis Ambrosio Blázquez

December, 2024

Table 1. Summary of the Work Plan

| Version and date of the Work Plan | Version 7 Revised in December 2024 |
| --- | --- |
| Start date | End date |
| November 2013 | December 2027 |
| Leader of the FIP (organization responsible for the Action Plan) | Improvements recommended by (meeting / group supporting development) |
| WWF | Meeting with stakeholders |
| FIP Coordinator (organization / person responsible for reporting in FisheryProgress) | Work plan developed by (consultant or person) |
| WWF | Luis Ambrosio Blázquez |

Acronyms

| GDSIS | General Directorate of Supervision, Inspection and Sanction |
| --- | --- |
| FIP | Fishery Improvement Project |
| EPO | Eastern Pacific Ocean |
| UoA | Unit of Assessment |
| FMR | Fishery Management Regulation |
| PMA | Perú Mahi Alliance |
| COREMAHI | Mahi-mahi Producers and Processors Regional Committee |
| ETP | Threatened or endangered protected species |
| IATTC | Inter-American Tropical Tuna Commission |
| IMARPE | Instituto del Mar del Perú |
| IPIAP | Instituto Publico de Investigación de Acuicultura y Pesca de Ecuador |
| PRODUCE | Ministry of Production (Peru) |
| SAC | Scientific Advisory Committee |
| MEF | Ministry of Economy and Finance (Peru) |
| MSC | Marine Stewardship Council |
| ROP | Reglamento de Ordenación Pesquera |
| WWF | World Wildlife Fund |

# Evaluation unit

Table 2. Evaluation unit (UoA)

| UoA | Description |
| --- | --- |
| Target Species (common and scientific name) | Perico o Mahi-mahi (Coryphaena hippurus) |
| Stock | Eastern Pacific Ocean |
| Geographic area | Exclusive economic zone of Peru |
| Fishing gear | Longline |
| Fishing fleet, group of vessels, or individual fishing operators that operate on the stock | Peruvian artisanal fishing fleet |

# FIP Actions

## FIP Actions for Principle 1

Table 3. Action plan of performance indicators for action 1.1.2. Definition of stock units.

| Action number and name | 1.1.2. Definition of stock units (PARTIALLY COMPLETED) |
| --- | --- |
| Action goal | Understand the population distribution and population structure of mahi-mahi in the EPO |
| Description of the action | The definition of the stock unit (independent biological units) is an aspect to be considered in the definition of the Unit of Assessment (UoA), which is the spatial framework on which the MSC standard assessment is applied. Ultimately, this will determine whether it is necessary to move towards bilateral or multilateral efforts to harmonize research, monitoring and management strategies for a fishery, in the case of a stock shared between different countries. In order to adequately define the mahi-mahi el population(s), different genetic studies and a tagging program have been carried out. These initiatives are reflected in the present action. ● Genetic studies. In the case of the dorado fishery, several genetic studies have been conducted to clarify its structure in the EPO (Gozzer et al., 2015; Téllez and Caballero, 2014; Tripp-Valdez et al., 2014). In general, these studies have observed high intrinsic genetic variability, with no evidence of genetically distinct populations. However, the authors also suggest that the quality of these studies could be improved in terms of spatial and temporal coverage of the samples used and the genetic methods employed. Following this line of research, a regional genomic study is currently being developed to identify dorado populations in the EPO, a task that is being promoted and coordinated by COREMAHI1. This study is led by Dr. Sofía Ortega of the Interdisciplinary Center of Marine Sciences of the National Polytechnic Institute and Dr. Píndaro Díaz of the Institute of Marine Sciences and Limnology of the National Autonomous University of Mexico (UNAM). This study will apply the RADseq technique, which uses restriction enzymes and molecular identifiers for the extraction and sequencing of the genome of mahi-mahi mahi individuals. The individuals will be collected in three countries (Costa Rica, Ecuador and Peru) with the support of INCOPESCA, IPIAP and IMARPE. The analysis will be carried out in the laboratories of UNAM and IMARPE, while sequencing will be carried out at the University of Georgia. ● Tagging and recapture. Tagging techniques have proven to be very useful for understanding the migratory patterns of tuna species and could also be a useful tool for understanding the migratory patterns of Mahi-mahi in the EPO. In this sense, COREMAHI has included in its scientific plan 2021-2026 a “C. hippurus tagging study to improve the knowledge of its stock structure in the EPO”, the objectives of this study are: (a) Estimate the movements of dorado between north and south of the equator to improve knowledge of the life history of C. hippurus and its stock structure in the EPO. b) Obtain information on the movement and dispersal rates of C. hippurus and water temperature in the EPO, by tagging individuals of C. hippurus, to estimate: (i) tag loss rates; (ii) mortality rates of dorado; (iii) information on population size; and (iv) behavioral attributes. As of 2024, the date of the progress review of the FIP, the action has been partially completed with some pending elements to close it. Thus, according to the information provided by IMARPE, and in relation to the genomic study (Milestone 4), samples have been collected during 2023 and 2024 in Peru and Ecuador, but this sampling will continue until February 2025 in both countries, with the objective of strengthening the number of samples of the study. Regarding Milestone 3, during 2023 and 2024, training was conducted in Ecuador and Peru for captains, fishermen and observers on the registration and placement of tags on mahi-mahi. In Ecuador more than 111 tags were deployed, and in 2023 six tags were recovered in the EPO, mainly in catches on FADs. For 2024 and 2025 this work will continue, with plans to train in Peru between January and February 2025 before starting tagging in that country. |

| Expected compliance date | December, 2026 |
| --- | --- |
| Priority | Medium |
| Estimated cost ($ US) | 35,000 |
| Responsible parties | IMARPE, SFP, CIAT, COREMAHI |
| MSC IDs associated with the action | 1.2.3 Information and monitoring |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 1. Define the stock unit(s) | M3b: By the year 2025, the results obtained with the implementation of the tagging project in Peru and Ecuador will be analyzed. M3c: By 2026, it is expected to have a published scientific article. | IMARPE | COREMAHI, SFP, IATTC | December, 2024 | December, 2026 | Reports or papers containing the results of tagging studies |
|  | M4b: By the year 2025, the analysis of the results obtained from the genomic libraries of the mahi-mahi in Ecuador and Peru will be carried out. M4c: By the end of 2025, it is expected to have an updated scientific publication on the genomic study of the mahi-mahi, including environmental factors in the analysis of the results obtained. | IMARPE | COREMAHI, SFP, IATTC | December, 2024 | December, 2025 | A scientific paper on the preliminary results of the study has already been published. https://www.frontiersin.org/journals/marine-science/articles/10.3389/fmars.2023.1294509/full Other published studies or scientific papers |

Table 4. Action plan of performance indicators for action 1.1.3. Development of monitoring procedures.

| Share number and name | 1.1.3 Development of monitoring procedures (PARTIALLY COMPLETED) – REVISED SEPT. 2024 |
| --- | --- |
| Action goal | Improve monitoring and data collection. |
| Description of the action | This action proposes carrying out tasks with two approaches, the first aimed at collecting data dependent on fishing and the second at collecting data independent from fishing. Although this action started in the past, it is considered that it is still necessary to continue implementing it to obtain the best scientific information available, modifying and increasing the expected results. The data necessary for a better understanding of the fishery are categorized into dependent and in dependent. - Fishery-dependent data For the collection of catch and effort data, PRODUCE is working on the implementation of electronic logs at the fleet level, for which it has recently developed an application called SITRAPESCA, which has two modules of interest. The first aimed at extraction that allows defining setting times and fishing areas, as well as the volumes extracted by each setting. The second module of interest is the download module that allows the shipowner to register and consult the downloads of each of its fishing operations, including the shipments of the resource to different destinations such as processing plants, markets, fishing terminals or others. This database will be managed by PRODUCE and will allow the generation of more information regarding the catches and the effort applied. Regarding the biological monitoring that allows generating information on the size structure of the catches, sexual maturity and other biological aspects. It is important to mention that IMARPE maintains a monitoring program in port for more than 10 years, where it collects such information. However, it is recognized that the monitoring is not directly directed to the mahi-mahi fishery and is therefore considered “opportunity monitoring”. Recently, and with the aim of improving this situation, work has been carried out on a collaborative research pilot plan that has been promoted by WWF and that includes the participation of some companies linked to the PMA. Through this initiative, fishermen collect and preserve samples that are later sent to IMARPE for analysis of size structure, stomach content and maturity. On the other hand, IMARPE carries out periodic exploratory fisheries to obtain biological information on the state of the main fishery species exploited in the country, including mahi-mahi. The last one for this species was carried out in September 2024. The data complement other data obtained in the fishery and are the basis for the annual establishment of the parameters of fishing activity during the authorized fishing periods. - Independent data from the fishery As part of the initiatives proposed in the PMA Plan, the need to ‘prepare the design of a fisheries research survey and identify sources of funding for its implementation’ was identified in the previous FIP implementation period. The research survey for fishery-independent information should be aimed at collecting key information to feed stock assessment models, such as stock size structure, recruitment, growth, maturity and other biological or oceanographic parameters that reduce the uncertainty of the estimates. Moreover, COREMAHI-sponsored research studies (tagging and genetic) should be considered as part of these data. Regarding milestone 8, related to the collecting fishery-dependent data, given the number of vessels in the fishery, logbooks are still not being used by the entire fleet; therefore, this milestone is not considered complete. Milestones 11 and 12 are considered met since evidence has been presented in accordance with the expected results. To give continuity to Milestone 13, related to fishery observers, an extension of this milestone (13b) is proposed to continue and expand the observation work on board the mahi-mahi fleet to obtain mahi-mahi samples according to the sampling program proposed by IMARPE. |

| Expected compliance date | December, 2026 |
| --- | --- |
| Priority | High |
| Estimated cost ($US) | $ 45 000 |
| Responsible parties | IMARPE, PRODUCE, PMA, WWF |
| MSC IDs associated with the action | 1.2.1 Harvest strategy 1.2.2. Harvest control rules and tools |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1.3. Follow-up procedure development | M8: Implementation of logbooks for the collection of catch and effort data. | PRODUCE | IMARPE, WWF | July, 2021 | December, 2025 | - Technical reports of fully implemented fleet logbooks |
|  | M11: Implementation of a biological monitoring program. | IMARPE | PMA, WWF |  | COMPLETED (2024) | H11: - REPORT ON THE EXPLORATORY FISHING OF THE RESOURCE MAHI-MAHI (Coryphaena hippurus) FROM SEPTEMBER 1 TO SEPTEMBER 30, 2023 - sampling protocol for the mahi-mahi (Coryphaena hippurus) and other oceanic fishes - PROCEDURE FOR COLLECTING BIOLOGICAL SAMPLES OF MAHI-MAHI FROM THE COMPANIES ASSOCIATED WITH PMA TO IMARPE |
|  | M12: Independent monitoring design for biological data collection. | MARPE | PMA, WWF |  | COMPLETED (2024) | Reports with the results of mahi mahi tagging studies Scientific paper on the preliminary results of a genetic mahi mahi study: https://www.frontiersin.org/journals/marine-science/articles/10.3389/fmars.2023.1294509/full |
|  | M13b (NEW): Continue the observer program and maintain it as a mechanism for fishery-dependent data collection. | IMARPE | PMA, WWF | December, 2024 | December, 2026 | Technical reports completed |

Table 5. Action plan of performance indicators for action 1.1.4. Stock assessment methods

| Share number and name | 1.1.4A. NEW- September 2021: Stock assessment methods (COMPLETED) |
| --- | --- |
| Action goal | Know the status of the stock of the target population of the Peruvian mahi-mahi fleet. |
| Description of the action | This action initially considered 4 tasks aimed at concluding the implementation of a stock assessment method based on size structures. At the third meeting of the IATTC, data needs and appropriate stock assessment methods were identified for the mahi-mahi fishery considered a data-limited fishery. With information from Ecuador and Peru, the IATTC scientific staff carried out an exploratory assessment of the C. hippurus stock in the “core” region (Peru-Ecuador) using the Stock Synthesis method (Aires-da-Silva et al. 2016)2, an exploratory management strategy evaluation (MSE) for the Southern EPO (Valero et al., 2016)3, and an evaluation of possible reference points, control and harvest rules for C. hippurus in the EPO (Valero et al., 2019) 4. Although these studies have been a contribution to the knowledge of the state of the mahi-mahi stock in the EPO, the scientific staff of the IATTC has recommended future research to improve the analysis of the assessments. This recommendation was made during the 10th Meeting of the Scientific Advisory Committee (Scientific Advisory Committee - SAC) in May 2019, in which it was recommended "that the IATTC staff continue to work with the Members or Cooperating Non-Members of the IATTC (CPC) in the investigation on the state of the mahi-mahi stock ". Due to the previous recommendation, at the 12th meeting of the SAC in May 2021, a scientific plan was presented that includes projects identified by actors producing and processing mahi-mahi (COREMAHI) and by the fisheries research institutes of Ecuador (IPIAP) and Peru (IMARPE). From this, two new tasks emerge for the Peruvian mahi-mahi action plan, which are incorporated as part of this action since they are aimed at improving the knowledge of the stock status of the target population of the Peruvian fleet. These evaluations must contain an estimate of the status of the stock based on Biological Reference Points and it is expected that they will be configured as a permanent and systematic input of the future Catch Control Rule. Both stocks assessments (national and regional) have been carried out and published, so both milestones (M74 and M75) are considered to have been met. |

2  https://www.iattc.org/Meetings/Meetings2016/SAC-07/PDFs/Docs/_English/SAC-07-06a(i)-Dorado-assessment.pdf

3  https://www.iattc.org/Meetings/Meetings2016/SAC-07/PDFs/Docs/_English/SAC-07-06a(ii)_Management-strategy-evaluation-MSE-for-dorado.pdf

4 https://www.iattc.org/Meetings/Meetings2019/SAC-10/Docs/_English/SAC-10- 11_Potential%20reference%20points%20and%20harvest%20control%20rules%20for%20dorado%20in%20the%20EPO.pdf

| Expected compliance date | Dec, 2024 |
| --- | --- |
| Priority | High |
| Estimated cost ($US) | 100,000 |
| Responsible parties | IMARPE, IATTC, IPIAP, COREMAHI |
| MSC IDs associated with the action | 1.1.1. Stock status 1.2.4. Assessment of Stock status |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1.4A. NEW- September 2021: Stock assessment methods | M74: Stock assessment at the national level and adjustment of the model based on a binational project | IMARPE |  |  | COMPLETED (2024) | - CARACTERIZACIÓN GENÓMICA DE LAS POBLACIONES DEL MAHI-MAHI CORYPHAENA HIPPURUS, EN EL PACÍFICO ORIENTAL: SENTANDO LAS BASES PARA EL DISEÑO DE ESTRATEGIAS DE ADMINISTRACIÓN - Stock Assessment of the dolphinfish (Coryphaena hippurus)) in the South-East Pacific Ocean - Stock assessment of Coryphaena hippurus in the South- East Pacific Ocean under environmental cycles |
|  | M75: Stock assessment at the regional level (Peru - Ecuador) | IMARPE | IATTC, IPIAP, COREMAHI |  | COMPLETED (2024) |  |

Table 6. Peer review of the model used for the national stock assessment of mahi-mahi

| Share number and name | 1.1.4B (NEW) Peer review of the model used for the national stock assessment of mahi-mahi |
| --- | --- |
| Action goal | Review the assessment models used by IMARPE to ensure that the model is aligned with other stock assessments |
| Description of the action | Peer review of fish stock assessments is a common procedure carried out to contrast the validity and rigor of the methodologies used and the results obtained. In this way, the assessments reviewed are robust and accurate. |
| Expected compliance date | Dec, 2026 |
| Priority | High |
| Estimated cost ($US) | 3,000 |
| Responsible parties | IMARPE |
| MSC IDs associated with the action | 1.2.4. Assessment of Stock status |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1.4B (NEW) Peer review of the model used for the national stock assessment of mahi-mahi | M80: The model used for the IMARPE mahi-mahi stock assessment has been peer-reviewed by scientists. | IMARPE |  | December, 2025 | December, 2026 | Technical report or publication |

Table 7. Action plan of performance indicators for action 1.2.1 Development and implementation of conservation measures.

| Share number and name | 1.2.1 Development and implementation of conservation measures (COMPLETED) |
| --- | --- |
| Action goal | Develop a harvest strategy |
| Description of the action | The harvest strategy must be based on a series of conservation and management measures that work together with the objective of not damaging the recruitment and keeping the population around a point consistent with MSY. In this sense, the Peruvian regulation has taken an important step in the development of a Fisheries Management Regulation (ROP, for its Spanish acronym), specific for the Mahi-mahi fishery (Ministerial Resolution No. 141-2021-PRODUCE). The ROP includes a series of conservation measures previously established such as the legal minimum size and the closure, but also incorporates the possibility of restricting fishing for conservation reasons by declaring a Maximum Total Catch Limit (MTCL), based on the recommendations provided by IMARPE. The ROP was officially adopted on July 27, 2021 through Decreto Supremo N° 017-2021-PRODUCE and now needs to be implemented. There are specific regulations that include conservation measures as specified in milestones 20 and 22 and are therefore considered to be completed. |
| Expected compliance date | December, 2021 |

| Priority | High |
| --- | --- |
| Estimated cost ($US) | 0 |
| Responsible parties | PRODUCE |
| MSC IDs associated with the action | - Harvest strategy - Harvest control rules and tools |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 1.2.1 Development and implementation of conservation measures | M20: Agreement on measures to be implemented as part of the general harvest strategy for the conservation of the mahi-mahi | PRODUCE |  |  | COMPLETED by adoption of the ROP | ROP MAHI-MAHI: https://pma.org.pe/wp-content/uploads/2022/03/rop-mahi-mahi.pdf |
|  | M22: Implementation of management measures (e.g. closures, hook size, etc.) | PRODUCE |  |  | COMPLETED (2024) | - Aprobación de la bitácora de pesca física para las actividades extractivas del recurso mahi-mahi - RM N° 000341-2023-PRODUCE - Establecen temporada de pesca del recurso mahi-mahi a nivel nacional, en el período comprendido entre el 1 de octubre y el 30 de abril de cada año - RM N° 245-2014-PRODUCE - Autorizan la ejecución de la pesca exploratoria del recurso mahi-mahi - RM N.º 288-2023-PRODUCE - Establecer el Límite Máximo Total de Captura (LMTC) del recurso mahi-mahi en cuarenta y cinco mil (45 000) toneladas - RM N.º 359-2023-PRODUCE - Ampliación de la cuota a 61 mil toneladas - RM N.º 022-2024-PRODUCE - OPINIÓN SOBRE LA POSIBILIDAD DE APROVECHAR LA MAYOR CANTIDAD DE MAHI-MAHI CORRESPONDIENTE A LA TEMPORADA DE PESCA 2023-2024 - OPINIÓN CIENTIFICA RESPECTO A LA POSIBILIDAD DE INCREMENTAR EL LIMITE MÁXIMO TOTAL DE CAPTURA DEL RECURSO DE MAHI-MAHI PARA EL PERIODO 2023-2024 - Dan por concluidas las actividades extractivas del recurso mahi-mahi - RM N.º 000036-2024-PRODUCE - Lineamiento para el monitoreo y seguimiento del avance de cuotas o límites de captura establecidos para recursos hidrobiológicos - RM N° 365-2020-PRODUCE - Stock Assessment of the dolphinfish (Coryphaena hippurus)) in the South-East Pacific Ocean - Stock assessment of Coryphaena hippurus in the South- East Pacific Ocean under environmental cycles - LEY Nº 31982 - AUTORIDAD MARÍTIMA NACIONAL Y FEMA COORDINAN ACCIONES PARA APLICAR NUEVA LEY DE INTERDICCIÓN EN ACTIVIDADES ILEGALES EN PESCA https://pescaformal.pe/wpcontent/uploads/2023/10/Reporte-Formalizaci%C3%B3n_Setiembre-2023.pdf |

Table 8. Action plan of performance indicators for action 1.2.2 Development and implementation of catch control rules.

| Action number and name | 1.2.2 Development and implementation of harvest control rules (PARTIALLY COMPLETED) REVISED SEPT 2024 |
| --- | --- |
| Action goal | Implement harvest control rules |
| Description of the action | The HCR implementation is essential to achieve the MSC standard. HCRs should be based on changes in exploitation rates depending on the status of the stock compared to biological reference points. Stock assessment procedures are needed to estimate stock status, limit and establish fishing mortality rates and biomass levels to define HCRs. Although, within the framework of the IATTC, an exploratory evaluation of the management strategy (MSE) for the Southern EPO was carried out (Valero et al., 2016), it focused on testing specific harvest strategies such as temporary closures and minimum extraction size. However, to design and test the HCR (M23) it is advisable to develop a Management Strategy Evaluation, simulating the behavior of the population against these eventual rules. Currently, the mahi-mahi Fishery Management Regulation (ROP for its Spanish acronym) provides a legal tool for the application of HCR, since in its Article 6 it indicates that “The Ministry of Production, based on available scientific information provided by IMARPE, establishes the Maximum Total Capture Limit (MTCL) for each fishing season of the mahi-mahi fishery”. However, HCRs have not yet been designed, tested, or implemented. For the HCR based on an LMTC that the ROP stipulates to be implemented, a Directorial Resolution of the General Directorate of Policies and Regulatory Analysis in Fisheries and Aquaculture must be developed. In this resolution, the indicators are approved to help to quantify the goal of the general objectives established in the ROP. Therefore, it is expected to contain Biological Reference Points (BRP) and to consider MSY as the minimum operational objective to maintain in the mahi-mahi population. In addition, if there is a history of overexploitation, the HCR should consider a population recovery strategy in a period less than one generation of mahi-mahi. Ultimately, at the national level, Peru through the fishery ROP and fishery-specific management measures for fishing seasons should be considered fishery-specific HCRs. In this sense, milestone 23 is completed. IATTC Resolution 23-09 adopted at the 101st Meeting of the Commission on mahi-mahi management research establishes the basis for CPCs to collect and submit to the IATTC catch and interaction data for dorado, as well as fishing effort data relating to dorado from their fleets. The objective of this information is to update, to the extent possible, the stock assessment of mahi-mahi conducted by the IATTC staff between 2012 and 2016, and to present it to the Scientific Advisory Committee in 2026. In addition, as appropriate, recommendations for CPCs on harvest control rules for the mahi-mahi dorado longline fishery will be updated during the 2026 meeting of the Scientific Advisory Committee. It is considered that for the fulfillment of this action and the improvement of the scoring of the MSC indicators concerned, it is appropriate for Peru to provide the appropriate information from the mahi-mahi fishery to the IATTC and, jointly, to collaborate in the analysis and proposals for Harvest Control Rules as indicated in the Resolution. Milestone 24 of the action included the implementation of HCR at national and international level. While at the national level, with the efforts made by IMARPE, this milestone is resolved, this is not considered to be the case at the international level. Therefore, the milestone 24 is modified to follow up this extension of the action at the international level |

| Expected compliance date | December, 2027 |
| --- | --- |
| Priority | High |
| Estimated cost ($US) | 30,000 |
| Responsible parties | IMARPE, IPIAP, IATTC |
| MSC IDs associated with the action | - Harvest strategy - Harvest control rules and tools |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 1.2.2 Development and implementation of capture control rules | M23: Design and test of harvest control rules | PRODUCE | IMARPE |  | COMPLETED (2024) | - INFORME SOBRE EL DESARROLLO DE LA PESQUERÍA DE MAHI-MAHI (CORYPHAENA HIPPURUS) DURANTE LA TEMPORADA DE PESCA 2022-2023, SITUACIÓN ACTUAL Y PERSPECTIVAS DE EXPLOTACIÓN PARA LA TEMPORADA 2023-2024 - RM N.º 359-2023-PRODUCE (cuota temporada 2023-2024) - RESOLUCIÓN MINISTERIAL Nº 00334-2022-PRODUCE (cuota temporada 2022-2023) - RESOLUCIÓN MINISTERIAL Nº 00108-2022-PRODUCE (cuota temporada 2021-2022) - NOTICIA DE LOS TALLERES EN QUE EL IMARPE PARTICIPAN https://www.gob.pe/institucion/imarpe/noticias/869472-investigadores-del-imarpe-fortalecen-sus-capacidades-en-evaluacion-de-estrategias-de-manejo-pesqueros |
|  | M24b: HCR implementation (internationally level) | PRODUCE | IMARPE | July, 2021 | December, 2027 | HCR at international level (IATTC)implemented |

## FIP Actions for Principle 2

Table 9. Action plan of performance indicators for action 2.1.4. Develop a management strategy to ensure that the fishery does not have an unacceptable impact on ETP species.

| Share number and name | 2.1.4. Develop a management strategy to ensure that the fishery does not have an unacceptable impact on ETP species (PARTIALLY COMPLETED) - REVISED SEPT. 2024 |
| --- | --- |
| Action goal | Reduce the impact on ETP species |

| Description of the action | As a result of the implementation of bycatch monitoring procedures and interaction with ETP species (Action 2.1.8), a management strategy should be developed aimed at reducing the impact on ETP species, supported by information. It is important to recognize that the current ROP considers the implementation of measures aimed at reducing the impact on ETP species. Specifically, the ROP considers in its Article 10: - Numeral 10.6. If the bycatch of turtles or other species protected by current provisions is observed due to extractive activities, every reasonable effort is made to rescue it alive and return it to the marine environment as soon as possible. Likewise, if a turtle is brought on board, every effort is made to contribute to its recovery before it is returned to the sea. For such purposes, the owners of the vessels must ensure that the necessary instruments for the release of incidentally captured turtles are carried on board the vessel, and must have: line cutter, unhooker and chinguillo (net), and ensure that at least one member of the crew is trained in sea turtle handling and release practices. - Numeral 10.7 Longline fishing boats use hooks that prevent the capture of sea turtles. However, the measures must be accompanied by a monitoring program to determine their effectiveness, which would be achieved with the fulfillment of action 2.1.8. FONDEPES has been responsible for carrying out the training of the crew members in charge of fulfilling the mandate of paragraph 10.6 of the mahi-mahi ROP. To date, several workshops have been held for this purpose. However, as of the date of the progress evaluation, crew members from all vessels have not yet been trained. Therefore, the action is not considered closed and continues to run until the proposed date of December 2026. Milestone 37 remains open. In relation to milestone 35, evidence has been presented in the form of a report analyzing the results of the information obtained from the electronic monitoring pilot project. |
| --- | --- |
| Expected compliance date | December, 2026 |
| Priority | High |
| Estimated cost ($US) | $ 15 000 |
| Responsible parties | IMARPE, PRODUCE |
| MSC IDs associated with the action | - ETP Species Outcome - ETP Species Management - ETP Species information 2.5.2. Ecosystem Management |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1.4 Develop a management strategy to ensure that the fishery does not have an unacceptable impact on ETP species. | M35: Analysis of the results obtained through the implementation of milestones 76 and 77 – Remote Monitoring Program. | IMARPE |  |  | COMPLETED (2024) | Results report on the analysis of data recorded in the TrazApp and remote electronic monitoring cameras. |
|  | M36: Use results obtained by monitoring the interaction of ETP species and the fishery to develop management strategies that minimize fishing-related mortality. | IMARPE |  |  | Awaiting publication on bycatch from the data of the electronic monitoring project implemented (2024) | Report of bycatch published |
|  | M37: Implementation of management measures aimed at minimizing fishing- related mortality. | FONDEPES |  | July, 2021 | December, 2026 | Training results reports |

Table 10. Action plan of performance indicators for action 2.1.8. Development and implementation of bycatch monitoring procedures and interaction with ETP species.

| Share number and name | 2.1.8. Pilot program for remote monitoring of bycatch and interaction with not target species and gear loss to support management (PARTIALLY COMPLETED)- REVISED SEPT 2024 |
| --- | --- |
| Action goal | Monitor bycatch and interaction of the fishery with ETP species |
| Description of the action | To comply with the MSC standard in the components that assess catch or damage to non-target species, information is required to estimate their mortalities. To this end, it was initially proposed to monitor the fishery's interactions with primary, secondary and ETP species through an observer program. This proposal was projected through Action 2.1.1, milestone 27 of the original action plan for this fishery. The program included a) characterizing and quantifying bycatches of birds, turtles and sharks, b) understanding the causes of these interactions, and c) evaluating and monitoring the effectiveness of mitigation measures to avoid these interactions. However, the on-board observer program could not be implemented in a way that met the intended objectives. The poor habitability of the vessels and the long duration of the vessel trips (approximately 20 days) prevent the implementation of an adequate human observation system on board. For this reason, the parties concerned decided to cancel Action 2.1.1, Milestone 27 and replace it with a new action. On the other hand, a pilot project was designed for remote monitoring using cameras and artificial intelligence to capture bycatch information and interaction with ETP species. (Milestone 76) The pilot project was financed by the National Fisheries and Aquaculture Innovation Program (PNIPA 2020 - 2021) and with funds from the companies that make up the Peru Mahi Alliance. This pilot project was carried out on 10 vessels so milestone 76 of the action was completed. As a result of the remote camera monitoring pilot project, it was found that it was not feasible to scale it across the fleet due to the high cost of implementing the system on a statistically representative number of the mahi-mahi fleet. In addition, there are additional costs associated with the maintenance of the system, the hiring of professional technical reviewers for the videos, among others. For this reason, Milestone 77 will not be covered and is therefore be removed from the Action Plan. In parallel, in relation to the original objectives of Action 2.1.8, WWF has implemented an electronic fishing app whose use has been promoted in the framework of the PMA this app called TrazApp has been widely used. In 2019, the app was used by more than 200 users, recording around 3,000 fishing trips and more than 28,000 tonnes of landings. This app includes the reporting of interactions with ETP species, especially turtles, where the number of interactions and the state in which they were released is reported. This tool would complement the remote monitoring information, but it should be noted that it is dependent on fishermen reporting the information. With the remote camera monitoring information from the implemented pilot, human observer information, fishing logbook data, the use of the SITRAPESCA traceability application and fishermen's contributions to TrazApp, it should be possible to a) characterize and quantify bycatch, to determine the existence of secondary target species b) understand the causes of these interactions and c) evaluate and monitor the effectiveness of measures to not impede the recovery of secondary target species. However, given that the scaling up of human and electronic monitoring, tested in the development of this action, is not possible for various reasons explained above, a new action is proposed to fill the gap in on-board monitoring of longliners catching mahi-mahi (A2.1.9) and to bring together the various initiatives mentioned above. (See Action 2.1.9). On the other hand, although the pelagic gear used to catch mahi-mahi in Peru is not found on the seabed, it is necessary to implement a mechanism to record the loss of fishing gear, which could eventually drift towards coastal areas and impact the habitat or more broadly the ecosystem. This is considering the size of the fleet, which in 2015 was estimated at 2,346 vessels. To this end, it was initially proposed to use the catch logbook (defined in M8), to collect information on the loss of fishing gear (action 2.2.1 milestones 42 and 43), where geographical coordinates and gear specifications (number of hooks, types of hooks, length of longline, etc.) should be recorded. However, the traceability application designed, SITRAPESCA, does not contemplate the capture of this information. As a solution, it is proposed to introduce this field in SITRAPESCA so that this information is officially recorded. On the other hand, in relation to Milestone 79 on strategies to minimize the impact on ETP species, it is considered that it is necessary to continue with the progress already initiated in relation, fundamentally, to the use of the inverted T for sea turtles and to incorporate seabirds as part of the Action. Furthermore as an extension of the scope of this action for the next three-year period and given the impact that longline fisheries can have on certain seabirds, IMARPE, in collaboration with the New Zealand Department of Conservation, is in the process of approving a research project that in the first stage will focus on characterizing the behavior of seabirds that interact directly with the mahi-mahi fishery, determining in which part of the gear they are more susceptible to being captured incidentally, as well as at what moment of the operation of the line (set, operation or collection). Based on the results obtained, the second stage will identify, design and implement the most suitable mitigation tests to reduce albatross and petrel mortality in this fishery, including the possibility of adapting bird scaring mechanisms, modification of part of the fishing gear, good practices for discarding entrails, retention of second-use bait, modification of bait characteristics, etc. |

| Expected compliance date | December, 2026 |
| --- | --- |
| Priority | High |
| Estimated cost ($US) | $160,000 |

| Responsible parties | PRODUCE, IMARPE |
| --- | --- |
| MSC IDs associated with the action | 2.1.1 Primary species Outcome 2.1.3. Primary species information - Secondary Species Outcome - Secondary Species Management - Secondary species information 2.3.3. ETP species information 2.4.3. Habitats information |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 2.1.8. Development and implementation of a pilot program for remote monitoring of bycatch and interaction with ETP species and gear loss- NEW | M76: Pilot implementation of remote monitoring program | WWF-IMARPE | OSPAS |  | COMPLETED (2024) | Results report on the analysis of data recorded in the TrazApp and remote electronic monitoring cameras. |
|  | M77: Scaling up of the remote monitoring program | WWF-IMARPE | OSPAS |  | NOT IMPLEMENTED- REMOVE FROM WORKPLAN (2024) |  |
|  | M78: Report of the declarations of loss of gear and interaction with bycatch. | IMARPE | WWF PRODUCE | July 2021 | December 2026 | SITRAPESCA report of declarations of gear loss and interaction with accompanying fauna. (Not completed 2024) |
|  | M79: Generate strategies to minimize the impact on ETP species if needed (Turtles and birds). | IMARPE | New Zealand Department of Conservation | July 2022 | December 2026 | Inverted T report (Completed) Inverted T report expanded rest of fleet (December, 2026) |

Table 11. Action plan of performance indicators for action 2.1.9. Protocol for validation of observer data against those obtained from fishermen's logbooks and progressive increase of human observers. (NEW ACTION)

| Share number and name | 2.1.9 Protocol for validation of observer data against those obtained from fishermen's logbooks and progressive increase of human observers. (NEW ACTION) |
| --- | --- |
| Action goal | Improving knowledge of fishery impact with ETP species |
| Description of the action | For Milestone 76 of Action A2.1.8 of the previous FIP triennium, an electronic monitoring pilot project was implemented and completed in April 2023. A total of 136 fishing hauls were monitored using TrazApp cameras and electronic logbooks on board 12 fishing vessels during the 2022 and 2023 mahi-mahi fishing season, collecting data on bycatch and catches of target species. This data is collected in a database created for this purpose and, in August 2023, the analysis report of the information obtained was published. However, the costs associated with a possible expansion of this technology were not considered feasible for such a large fleet considering all the components of the system (purchase and installation of cameras and other electronic equipment, maintenance, data analysis, personnel involved, etc.). However, MSC requirements demand that fisheries demonstrate that the impact on the different components of the marine environment is known, that they do not affect their survival and that management strategies are in place to minimize them. Therefore, it is necessary for fisheries to incorporate reliable mechanisms to know and measure these impacts. In general, it is considered adequate for this purpose to incorporate human observers on board vessels with a percentage of coverage that accredits that the observation effort made serves to identify and quantify these impacts. On occasions, the difficulties of human observers carrying out these tasks, either due to the limited habitability of the vessels or the cost of hiring them for such a large fleet, among others, require innovative mechanisms. Although Peruvian regulations do not require specific observer coverage for longline fisheries, the IATTC, through Resolution C-19-08 (on scientific observers aboard longline vessels) agreed that “Each Member and Cooperating Non-Member (CPC) shall ensure that at least 5% of the fishing effort deployed by its longline fishing vessels over 20 meters length overall carries a scientific observer”. In addition, it should be noted that the Scientific Advisory Committee (SAC), at its 10th meeting in May 2019, determined that the appropriate measure of longline fishing effort for calculating observer coverage is “number of hooks”. On the other hand, the new version of the MSC standard (3.1) incorporates relevant changes to determine the accuracy of the catch composition of the Assessment Unit. In this sense, it is important that this accuracy is adequate and that concrete measures are established to ensure compliance with the MSC criteria in the future. Given that this is not a task that can be accomplished in the short term, it is necessary to provide the fishery with the necessary tools to achieve this. Therefore, this new action will have two lines of work. On the one hand, IMARPE will elaborate a protocol with the methodology to validate the data obtained from the logbook, using as support other more accurate and reliable sources of information such as IMARPE's onboard and/or shore-based Monitoring and Tracking Programs, as well as technological tools such as satellite tracking of vessels that allow us to analyze the dynamics of the fishing fleet distribution. On the other hand, the number of human observers on board the mahi-mahi fleet will be progressively increased to have the best information and use it as a contrast to the information provided by the fishermen in the logbooks. |
| Expected compliance date | December, 2027 |

| Priority | High |
| --- | --- |
| Estimated cost ($US) | $ 240,000 |
| Responsible parties | IMARPE |
| MSC IDs associated with the action | 2.1.3. Primary species information 2.2.1. Secondary Species Outcome 2.2.2. Secondary Species Management 2.2.3. Secondary species information 2.3.3. ETP Species information 2.4.3. Habitats information |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| Protocol for validation of observer data against those obtained from fishermen's logbooks and progressive increase of human observers | M81: Creation of a protocol for validation of fishing logbook information. | WWF-IMARPE | PMA | December, 2024 | December, 2025 | Protocol created and approved |
|  | M82: Implementation of the new protocol in the fishery | WWF-IMARPE | PMA | December, 2024 | December, 2027 | Evidence of protocol implementation: - Minutes of meetings - Pictures - Reports |
|  | M83: Increasing the number of human observers on board the fleet | WWF-IMARPE | PRODUCE; Ministry of Economy and Finance | December, 2024 | December, 2027 | Evidence of observer number increase: - Labor contracts - Observers reports |

## FIP Actions for Principle 3

Table 12. Action plan of performance indicators for action: NEW Sep 18: Analysis of existing conflict resolution mechanisms.

| Action number and name | 3.1.1 REVISED Sept 2021: Analysis of existing conflict resolution mechanisms – (COMPLETED) |
| --- | --- |
| Action goal | Review of existing mechanisms to resolve conflicts to determine if they comply with MSC regulations. |
| Description of the action | In the previous review of the action plan, it was established that, since it is possible that there are sufficient conflict resolution processes for the requirements of the standard, it was necessary to carry out a review of the conflict resolution mechanisms and respect for rights. Although both elements are considered in the legal framework, doubts persisted as to whether the conflict resolution mechanisms were applied in a transparent and appropriate manner to the context of the UoA and, on the other hand, whether there were mechanisms to recognize rights established using people to be able to respect them (M72). In the meetings with stakeholders, during the previous evaluation, it was clarified that there are tools for conflict resolution and that these fall under the Presidency of the Council of Ministers which is established by Supreme Decree 022-2017 PCM appropriate to DS 042 2018 PCM. In addition, in the 2021 FIP audit, the auditors were told that there are tools for both Conflict Resolution and Consultation and Participation Procedures. These documents were reviewed considering that they comply with the requirements of the standard (see audit 2021), therefore the previous tasks involving the formation of a permanent working group are not necessary and were removed from the 2021 workplan. However, the previous assessment recommended making available to users an analysis with the systematization of the procedures necessary to meet the requirements of indicators 3.1.1, Legal or customary framework, and 3.1.2, Consultations, roles and responsibilities. This analysis was completed in July 2023, and therefore Action 3.1.1 is considered complete. |
| Expected compliance date | July 2023 |
| Priority | Low |
| Estimated cost ($US) | 15,000 |
| Responsible parties | WWF |
| MSC IDs associated with the action | 3.1.1. Legal or customary framework 3.1.2 Consultations, roles and responsibilities |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 3.1.1. Analysis of existing conflict resolution mechanisms | Milestone 72: Review existing conflict resolution mechanisms | WWF | PMA |  | COMPLETED (2023) | Report on Conflict Resolution in the Artisanal Fishing Sector – Natalia Mora Summary PPT: Regulatory improvement and consultation mechanisms in the Fishing Sector – Veronica Rojas- PRODUCE |

Table 13. Action plan of performance indicators for action 3.2.1 Specific objectives of the fishery.

| Action number and name | - Specific objectives of the fishery - REVISED SEPT. 2024 |
| --- | --- |
| Action goal | Develop a specific management system for the fishery |
| Description of the action | This action is well advanced since the fishery management regulation (ROP) has been published and applied. Although this instrument establishes objectives for the fishery, it does not expressly indicate the population status to be obtained for mahi-mahi, however, in the Transitory Complementary Provisions the Monitoring and Evaluation of the ROP has been established, which is executed through a Directorial Resolution of the General Directorate of Policies and Regulatory Analysis in Fisheries and Aquaculture of the Vice-Ministerial Office of Fisheries and Aquaculture. In this resolution, the indicators that allow quantifying the goal of the general objectives established in the ROP are approved. Therefore, it is expected to contain Biological Reference Points (BRP) and indicators for this purpose. In this way, the desired population objective for the fishery and the corresponding decision-making procedures are clarified. Although the short- and long-term objectives have been designed and are explicitly contained in the ROP (M50), their effectiveness has not yet been tested and therefore it cannot be said that they are well defined and measurable (M51). The action remains open to meet Milestone 51 |
| Expected compliance date | December, 2025 |
| Priority | High |
| Estimated cost ($US) | $ 15 000 |
| Responsible parties | PRODUCE |
| MSC IDs associated with the action | - Fishery specific objectives - Decision making processes |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 3.2.1 Specific objectives of the fishery | Milestone 50: Design explicit short- term and long-term goals consistent with MSC Principles 1 and 2 | PRODUCE |  |  | COMPLETED (2024) | ROP mahi-mahi Other regulations related to mahi-mahi fishery |
|  | Milestone 51: Implementation of short and long-term objectives consistent with MSC Principles 1 and 2 | PRODUCE |  | September, 2021 | December, 2025 | ROP mahi-mahi Other regulations related to mahi-mahi fishery Related scientific reports |

Table 14. Action plan of performance indicators for action 3.2.3. Compliance and enforcement.

| Action number and name | 3.2.3. Compliance and enforcement- REVISED SEPT. 2024 |
| --- | --- |
| Action goal | Develop a specific management system for the fishery |
| Description of the action | Initially, in the Peruvian mahi-mahi FIP it was considered that the Monitoring, Control and Surveillance (MCS) mechanisms exist within the fishery management framework. However, existing mechanisms must be enforced to ensure that the objectives of the management system are achieved. Several activities have been identified as possible activities that could improve the current MCS system. Milestone 55: Analysis of the inefficiencies of the Monitoring, Control and Surveillance system (MCS) The mechanisms that could lead to sustainable practices such as the control of fishing effort, legal minimum size and fishing season, must be applied properly, for this the MCS system must be able to enforce the defined measures and strategies. Regarding this milestone, it was mentioned in the meeting with the interested parties that a monthly analysis is carried out by the GDSIS of PRODUCE to identify critical points of non-compliance with the regulations, such as ports and plants with a high incidence of infractions, to then make decisions to redirect inspection efforts. It was also indicated that the inspection coverage of mahi-mahi landings is between 50- 60% of the total landings. According to this, this task could be considered completed considering the systematic effort that allows identifying inefficiencies of the MCS system. However, during the audit no formal documents were in view that evidence this work, such as protocols or reports on the implementation of the inspection mechanisms. Milestone 56: Analysis of the fishing inspection capacity with proposals on how to increase it Based on the above information regarding the inefficiency analysis process of the MCS system, deficiencies in inspection coverage and lack of personnel are identified. However, these documents were not available during the audit. Milestone 57: Increase the capacity of fishery inspectors In the meeting with the interested parties, the representative of the GDSIS of PRODUCE mentioned that each year the personnel assigned to the inspection has increased, and that in fact, thanks to this, the inspection coverage has increased. However, this was not demonstrated during the audit regarding the increase made in terms of the number of inspectors nor about the increase in coverage that has occurred in recent years. Milestone 61: Incorporate CCTV at selected landing points In the audit carried out in 2018, the pilot implementation of a CCTV system by the GDSIS in the ports of Paita and Talara was declared as a supplementary element of the MCS system, whose objective is: - Alert that vessels are developing activities at times when inspection personnel are not present, - Support to the security of the inspectors and - Deterrent tool for acts of bribery. At the meeting held as part of this audit, PRODUCE´s GDSIS staff stated that the CCTV system has been expanded to the ports of Chimbote, Callao and Ilo. In addition, he stated that there is an intention to continue expanding the coverage of this initiative to other ports. The main utility of this system is that it has made it possible to identify the arrival of boats, at any time and day, which makes it possible to assign inspection personnel to the landing point outside of working hours or on holidays. In addition, at the meeting indicated that this has provided more security to the inspectors in the development of their work. Based on the background provided, this milestone is completed. This action was not completed within the planned period. The following Milestones have not had progress that can be considered as substantive to the objectives of the action: - H55: Analysis of inefficiencies in the MCS system. - H56: Analysis of fisheries inspection capacity with proposals on how to increase it. - H57: Enhance the capacity of fisheries inspectors - H61: Incorporate CCTV on board vessels and at selected landing sites They therefore remain open in the new FIP implementation period. Milestone 62: Design workshops to sensitize fishermen, ship owners, buyers and fishing companies about the importance of fishing regulations. During the meeting with the interested parties, it was indicated that the GDSIS of PRODUCE has within its functions to "Formulate and implement training programs, technical assistance and other actions, at other levels of government and related agents within the framework of its competences" (Art 86. DS Nº2 2017 - PRODUCE), which is implemented in practice by conducting workshops to fishermen, and other agents and even more extensively to the community in general, about the management measures applied to marine resources. Milestone 63: Develop awareness workshops As defined in milestone 62, it is concluded that this task is performed periodically. And it is expected that this will be developed in the future since it is part of the legal functions of GDSIS. However, reports that provide evidence of the performance of these activities were not available during the audit. Both Milestones 62 and 63 remain active given the importance of permanent socialization that must be achieved an adequate for conflict resolutions, consultation procedures and participation in the fishery. It is advisable to generate reports of these activities as verifiers before a possible complete evaluation. In the immediate term, these workshops should focus on the implementation of the ROP, especially the Catch Control Rule. Milestones H62 and H63 (Design workshops to raise awareness of fishermen, vessel owners, buyers and fishing enterprises on fisheries regulations and conduct workshops) were already completed in the previous FIP period, so no further comments are added in this report. |

| Expected compliance date | Dec, 2026 |
| --- | --- |
| Priority | High |
| Estimated cost ($US) | $ 30,000 |
| Responsible parties | PRODUCE |
| MSC IDs associated with the action | 3.2.3 Compliance & Enforcement |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 3.2.3. Compliance and enforcement | Milestone 55: Analysis of MCS system inefficiencies | PRODUCE |  | July, 2021 | December, 2025 | Technical reports Meeting minutes |
|  | Milestone 56: Analysis of the fishing inspection capacity with proposals on how to increase it | PRODUCE |  | July, 2021 | December, 2026 | Technical reports Meeting minutes |
|  | Milestone 57: Increase the capacity of fisheries inspectors | PRODUCE |  | July, 2021 | December, 2026 | Technical reports Meeting minutes Number of inspector jobs created |
|  | Milestone 61: Incorporate CCTV at selected landing points | PRODUCE |  | July, 2021 | July, 2026 |  |
|  | Milestone 62: Design workshops to sensitize fishermen, shipowners, buyers and fishing companies about fishing regulations. | PRODUCE | WWF |  | COMPLETED (2024) | Reports of the workshops held last year and in January 2024 |
|  | Milestone 63: Conduct workshops | PRODUCE | WWF |  | COMPLETED (2024) | Reports of the workshops held last year and in January 2024 |

Table 15. Action plan of performance indicators for action 3.2.4 Evaluation of management performance

| Action number and name | 3.2.4 Management performance evaluation – REVISED SEPT.2024 |
| --- | --- |
| Action goal | Develop a specific management system for the fishery |
| Description of the action | Under the regulation of the organization and functions of PRODUCE (DS 009-PRODUCE-2017), the General Directorate of Policies and Regulatory Analysis in Fisheries and Aquaculture, specifically the Directorate of Monitoring and Evaluation has the functions of evaluating the implementation of regulations in fishing (including mahi-mahi). It is expected that once the fishery management regulation (ROP) is promulgated, the monitoring and evaluation of the regulations will be carried out since it establishes that by means of a Directorial Resolution of the General Directorate of Policies and Regulatory Analysis in Fisheries and Aquaculture the indicators will be established that allow quantifying the goal of the general objectives established, as well as the plan for monitoring compliance with the provisions contained in the Operating Regulations, which will form part of the permanent evaluation. For this, Milestone 67 is considered closed. For milestones 68 and 69 (Design and implement an external review cycle to monitor and evaluate the performance of the fishery-specific management system) no progress has been made in relation to these milestones. However, in the assessment of possible scoring of this indicator it is considered that some parts of the management system have been externally assessed, but on an occasional basis. It is therefore considered that further progress is needed in the design and implementation of the external evaluation cycle that would allow all parts of the management system to be evaluated on a regular basis. The new action 1.1.4B incorporated into this action plan consists of a peer review of the stock assessment model carried out by IMARPE and would form part of the external evaluation process for the fulfillment of this action. This action has been partially completed. Milestones 68 and 69 have not been closed and therefore the action should remain open. |
| Expected compliance date | December, 2027 |
| Priority | High |
| Estimated cost ($US) | 12,000 |
| Responsible parties | PRODUCE |
| MSC IDs associated with the action | 3.2.4 Management Performance Evaluation |

| Action | Tasks/ Milestones | Responsible (lead) | Responsible (supporting role) | Starting date | Expected completion date | Evidence of completion / results |
| --- | --- | --- | --- | --- | --- | --- |
| 3.2.4 Management performance evaluation | Milestone 67: Design and implement an internal audit system to monitor and evaluate the performance of the specific fishery management system. | PRODUCE |  |  | COMPLETED (2024) | Final report on compliance with the mahi-mahi ROP published by the Monitoring and Evaluation Department. |
|  | Milestone 68: Design an external review cycle to monitor and evaluate the performance of the fishery-specific management system. | PRODUCE |  | July, 2021 | December, 2026 | Technical reports Meeting minutes |
|  | Milestone 69: Implement a two-year external review cycle to monitor and evaluate the performance of the fishery- specific management system. | PRODUCE |  | December, 2021 | December, 2027 | Technical reports Meeting minutes |