Fisheries Improvement Project for the Vietnamese Tuna longline and handline Fisheries Sector

Action Plan, Budget and Terms of Reference

UPDATED REPORT

Revised by FIP leads in January 2025 from previous (2023) version originally provided by Poseidon ARM Ltd

CONTENTS

1.INTRODUCTION	5

2.THE ACTION PLAN	11

GOAL 1. STOCK STATUS AND FISHERIES MANAGEMENT: TO ENSURE THAT THE TUNA CATCHES DO NOT EXCEED SUSTAINABLE LEVELS	17

Outcome 1.1 Stock status improved and reference points applied in management	17

Outcome 1.2 Data collection and Information systems strengthened	20

Outcome 1.3 Management strategies applied and supported by tools and the application of strong information and research.	21

GOAL 2. ECOSYSTEM MANAGEMENT: TO PROMOTE THE ECOSYSTEM BASED APPROACH TO FISHERIES MANAGEMENT	24

Outcome 2.1: Primary and secondary species subject to a management strategy	24

Outcome 2.2: Shark management measures implemented	1

Outcome 2.3 Turtle management strengthened	1

Outcome 2.4. Habitats subject to a management strategy	2

Outcome 2.5: Ecosystems and biodiversity assessments made for the Vietnamese and South China Sea region	2

3. GOVERNANCE SYSTEMS: TO STRENGTHEN GOVERNANCE SYSTEMS IN VIETNAM’S TUNA FISHERY	3

Outcome 3.1: Fisheries Law effectively implemented	3

Outcome 3.2: Roles and responsibilities and consultation processes fully implemented	4

Outcome 3.3: Fishery specific management objectives applied	6

Outcome 3.4: Decision making process strengthened	7

Outcome 3.5: Effective application of compliance systems	8

Outcome 3.6: Research plan is in place	9

3.TERMS OF REFERENCE	10

4.1 DATA COLLECTION FOR TARGET, OTHER RETAINED, BYCATCH, ETP SPECIES	10

4.2 STOCK ASSESSMENT AND ECOSYSTEM MODELING	16

4.4BYCATCH & ECOSYSTEM IMPACT ANALYSIS	20

RESEARCH INSTITUTION: To be nominated (RIMF)	20

4.4 DEVELOPMENT OF HARVEST STRATEGIES RULES AND TOOLS AND BYCATCH MITIGATION MEASURES	24

4.5.1 INSTITUTIONAL STRENGTHENING: GOVERNANCE, CONSULTATION AND DECISION MAKING	29

The Ministry of Agriculture and Resource Development, Department of Capture Fisheries & Resource Exploitation and Protection and the Tuna Fisheries Management Council	29

A.MARD	30

B.D-Fish	32

C.TUNA FISHERIES MANAGEMENT COUNCIL	34

4.6 COMPLIANCE	37

JOINT TUNA COMPLIANCE WORKING GROUP	37

4.7 PROJECT MANAGEMENT	39

A.WWF REGIONAL COORDINATOR	39

B.WWF NATIONAL MANAGER	41

C.INTERNATIONAL M&E CONSULTANT	43

| Acronyms |  |  |
| --- | --- | --- |
| Vietnamese Institutions Acronyms |  |  |
| CCM |  | Cooperating Commission Member |
| CMM |  | Conservation and Management Measure |
| CNM |  | Cooperating Non Member |
| EEZ |  | Exclusive Economic Zone |
| FMA |  | Fisheries Management Area |
| IUU |  | Illegal, Unreported and Unregulated |
| MSC |  | Marine Stewardship Council |
| MoU |  | Memorandum of Understanding |
| NPOA |  | National Plan of Action |
| NTMP |  | National Tuna Management Plan |
| RFMO |  | Regional Fisheries Management Organisation |
| SC |  | Scientific Committee |
| SPC |  | Secretariat of the Pacific Community |
| TCC |  | Technical Conservation Committee |
| TAC |  | Total Allowable Catch |
| TURF |  | Territorial User Rights in Fisheries |
| UNFSA |  | United Nations Fish Stocks Agreement |
| VDS |  | Vessels Days Scheme |
| UNFSA |  | United Nations Fish Stocks Agreement |
| VMS |  | Vessel Monitoring Scheme |
| WCPFC |  | Western Central Pacific Fisheries Commission |
| WCPO |  | Western Central Pacific Ocean |
| WPEA OFM |  | West Pacific East Asia Oceanic Fisheries Management Project |
| MSC Acronyms |  |  |
| BMT |  | MSC FIP Benchmarking and Monitoring Tool |
| EAFM |  | Ecosystem Approach to Fisheries Management |
| ETP |  | Endangered, Threatened and Protected |
| FIP |  | Fishery Improvement Project |
| MSC |  | Marine Stewardship Council |
| PSA |  | Productivity Sensitivity Analysis |
| RBF |  | Risk Based Framework |
| SICA |  | Scale Intensity Consequence Analysis |

# INTRODUCTION

The original fisheries improvement project (FIP) Action Plan was developed following a FIP stakeholder meeting held in Qui Nhon, Vietnam in June 2013 and was finalized in November 2013.  There was also a Progress Review held in Nha Trang, September, 2013 and a further reviews held in Nha Trang, Vietnam on October 8, 2015, and thereafter a remote review in November 2019. The purpose of this document is to update the Action Plan for December 2024 reporting period, in particular given the extension of the FIP end date to December 2025.  This updated Action Plan is therefore largely based on results of the FIP review meeting held at WWF in January 2022, with no major changes to the tasks prescribed, except to reflect any new activities that are underway, reconfirm activities which have not yet been implemented, and revise timelines. This Action Plan includes information on the proposed tasks for each of the defined activities and  the expected timeframe to complete the task and the current status. No scoring guideposts have been changed since the last (Jan 2023) Action Plan.  Work plans for each outcomes are also described, along with a proposed Road Map towards the implementation of a Harvest Strategy which is both compactible with the Commission Members, and should, if implemented, allow Vietnam to comply with Para 47 of CMM 2021-01, detailing the appropriate harvest control tools for Vietnam’s ‘other commercial fisheries’. The project logframe has also been adjusted to reflect any amendments. The document also includes the use of MSCs Benchmark Tracking Tool.

The Unit of Certification is Yellowfin and Bigeye tuna caught by handline in the Vietnamese EEZ;

This document identifies the activities and range of activities required in the Action Plan for the fisheries to meet the Marine Stewardship Council (MSC) standard. The most important feature to this is that all target species (Principle 1), must focus on the stock status and management activities throughout the range of the stock, whilst ecosystem interactions (for secondary species, and Endangered, Threatened, and Protected (ETP) species) relate specifically to the fishery under assessment.  It should be noted that MSC is in the process of developing a revied standard, at which time, a further review of the tasks set may be required.

This document serves to improve the guidance for the activities and milestones required in the Action Plan to reach the MSC Standard, integrating changes and clarifying any areas of uncertainty which may have been identified by the stakeholders during the FIP review meeting in November 2016.

The Action Plan itself incorporates reference to Stakeholder Terms of Reference (Section 4), which are revised and developed to include changes to timelines and associated budgets. The results generated from the Action Plan are reviewed by the WWF FIP Coordinator (Keith Symington), and Vietnam WWF consultant Binh Voung Trong.

The report contains a summary conclusion of where the fishery is at relative to attainment pf MSC.

VINATUNA is facilitating the development of the FIP Action Plan, supported by WWF Vietnam. The overarching management issues fall to the Ministry of Agriculture and Resource Development (MARD), in association with defined management actions prepared by WCPFC (Western and Central Pacific Fisheries Commission). The associated fisheries management tasks fall to responsibility of Department of Capture Fisheries, under General Directorate of Fisheries (D-Fish) and sub DECAFIREP at provincial level. Research functions may be supported by the Secretariat of the Pacific Community (SPC), but with a critical role to be played by Research Institute for Fisheries Management (RIMF). The Plan is further developed to include a FIP tracking document with activities linked to the MSC scoring guideposts and more specific milestones. The results generated from the Action Plan are subject to periodic internal and external reviews to ensure they will meet the MSC standard.

An assessment of current status of the fisheries against the principle guideposts is summarized below.

Table 1: Summary of pre-assessment scoring

| Principle | Component | PI number | Performance Indicator | Scoring 2013 | Scoring 2024 |
| --- | --- | --- | --- | --- | --- |
| 1 | Outcome | 1.1.1 | Stock status – yellowfin tuna | Pass | Pass |
|  |  |  | Stock status – bigeye tuna | Fail | Pass |
|  |  | 1.1.3 | Stock rebuilding – bigeye tuna | Fail | ###### NA |
|  | Management | 1.2.1 | Harvest Strategy – yellowfin tuna | Fail | ###### Fail |
|  |  |  | Harvest strategy – bigeye tuna | Fail | ###### Pass with Condition |
|  |  | 1.2.2 | Harvest control rules and tools – yellowfin tuna | Fail | ###### Fail |
|  |  |  | Harvest control rules and tools – bigeye tuna | Fail | Pass with Condition |
|  |  | 1.2.3 | Information and monitoring – yellowfin tuna | Pass with condition | Pass with recommendation |
|  |  | 1.2.3 | Information and monitoring – bigeye tuna | Pass with condition | Pass with recommendation |
|  |  | 1.2.4 | Assessment of stock status - yellowfin tuna | Pass | Pass |
|  |  | 1.2.4 | Assessment of stock status - yellowfin tuna | Pass | Pass |
| 2 | Primary species | 2.1.1 | Outcome - handline swordfish | Fail | Pass |
|  |  | 2.1.2 | Management – handline swordfish | Fail | Pass |
|  |  | 2.1.3 | Information – handline | Fail | Pass |
|  | Secondary | 2.2.1 | Outcome - handline blue marlin | Fail | Pass |
|  |  | 2.2.2 | Management - handline | Fail | Pass with Condition |
|  |  | 2.2.3 | Information – handline | Fail | Pass with Condition |
|  | ETP species | 2.3.1 | Outcome - handline | Fail | Pass |
|  |  | 2.3.2 | Management - handline | Fail | Pass with Condition |
|  |  | 2.3.3 | Information – handline | Fail | Pass |
|  | Habitats | 2.4.1 | Outcome - handline | Pass | Pass |
|  |  | 2.4.2 | Management - handline | Pass | Pass |
|  |  | 2.4.3 | Information – handline | Pass | Pass |
|  | Ecosystem | 2.5.1 | Outcome - handline | Fail | Pass |
|  |  | 2.5.2 | Management - handline | Fail | Pass |
|  |  | 2.5.3 | Information – handline | Pass with condition | Pass |
| 3 | Governance and Policy | 3.1.1 | Legal and customary framework | Pass with condition | Pass |
|  |  | 3.1.2 | Consultation, roles and responsibilities | Pass with condition | Pass |
|  |  | 3.1.3 | Long term objectives | Pass with condition | Pass |
|  | Fishery specific management system | 3.2.1 | Fishery specific objectives – handline | Fail | Pass |
|  |  | 3.2.2 | Decision making processes – handline | Fail | Pass |
|  |  | 3.2.3 | Compliance and enforcement – handline | Fail | Pass with Condition |
|  |  | 3.2.4 | Management performance evaluation | Pass with condition | Pass with condition |

A summary of the current status (FIMP-BMT index sheet) is shown in Tables 2 to 4. For the purpose of simplicity, longline and handline are combined. The critical distinction between them is that longline catches some bigeye tuna, and may have some interactions with protected species.

Table 2: MSC BMT Index summary table for the Vietnam tuna longline fishery, 2024

Figure 1: MSC BMT scoring overview Vietnam tuna longline fishery, 2021

Figure 2:  BMT Progress tracker

# THE ACTION PLAN

A summary logframe is provided in a separate attachment.  The original FIP contained three basic goals, 15 outcomes, 21 activities and 55 milestones. With the attainment of some of activities, there are now 21 activities and 49 milestones.

The project goals are as follows:

- Stock status and fisheries management: To ensure that the tuna catches do not exceed sustainable levels

- Ecosystem management: To promote the ecosystem based approach to fisheries management

- Governance systems: To strengthen governance systems in Vietnam’s Tuna fishery

The fifteen outcomes are as follows:

- Stock status improved and reference points applied in management

- Data collection and Information systems strengthened

- Management strategies applied and supported by tools and the application of strong information and research

- Retained and bycatch species subject to a management strategy

- Shark management measures implemented

- Turtle management strengthened

- Habitats subject to a management strategy

- Ecosystems and biodiversity assessments made for the Vietnamese and South China Sea region

- Fisheries Law effectively implemented

- Roles and responsibilities and consultation processes fully implemented

- Positive incentives promoted

- Fishery specific management objectives applied

- Decision making process strengthened

- Effective application of compliance systems

- Regular Internal and occasional External Review of the main parts of the handline management system

The deliverables against specific activities will be addressed in the section below.

This section represents a summary of the current positions on the milestones set to evaluate the achievement of outcomes in the Vietnam Fisheries Improvement Plan facilitated by WWF-VN and WWF-CTP. The Fisheries Improvement activities were agreed between the consultants, WWF and VINA Tuna after consultation with D-FISH.

The report concludes that in the FIP’s ninth year:

- 23 milestones have been achieved;

- 5 milestones are progressing well; and

- there is limited to no evidence of achievement for 21 milestones.

Six milestones have been removed as they are no longer relevant.

The required actions to be considered for implementation for the extended period through to December 2025 are as follows:

1. Development of a national tuna harvest strategy, which:

- Implement the WCPFC Harvest Strategy incorporating agree Limit and Target Reference points for yellowfin and bigeye tuna;

- Workshopping with industry to determine the management tools set, ensuring that the limits are compatible with WCPFC measures for other commercial fisheries, consisting of effort of catch controls set for other commercial fisheries (Para 54 and 55 of CMM 2021-01;

- Adopt management limits for all Vietnamese commercial fisheries, which are applied by Province and by fishing method

2. Strengthen catch logbook data collection so that it meets with the targets set by D-FISH, as stipulated in the WPEA Project (40%, transitioning to 100%);

3. Development of a shark action plan, which

- Record all shark species caught

- Ensure that if caught, any fins landed must be attached to the trunk

4. ETP Management mitigation

- Ensure the effective application of Circle hooks to prevent turtle catch

5. Strengthening the Tuna Management Plan to incorporate:

- Linking the harvest strategy and harvest rules and tools (quota, effort limits etc) to the RFMO Limit and Target Reference Points; and ensuring that actions will be taken by Vietnam if any tuna species reaches the Point of Recruitment Impairment

- Inserting ‘Implement bycatch based risk assessment to determine the impacts of fisheries on the ecosystem’ as a separate action point under II ‘Collecting data to serve for management of the oceanic tuna fisheries’.

- Insert Implement technical measures to protect any vulnerable bycatch species, especially sharks and turtle, under III Implementing the management measures

- Incorporation of an external review procedure which can critically assess the implementatiion of the Plan, identify bottlenecks and make recommendatios for change

6.  Occasional external review of performance (which can form an M&E requirement) within the Management Plan.

7. Strengthening the transparency in the decision -making process to include:

- Clarifying the decision-making processes that results in measures and strategies to achieve the fishery-specific objectives

- Ensure that the decision-making processes responds to serious and other important issues identified in relevant research, monitoring, evaluation and consultation, in a transparent, timely and adaptive manner

- That the decision-making processes use the precautionary approach and are based on best available information and that Information on fishery performance and management action is available on request, and explanations are provided for any actions or lack of action associated with findings and relevant recommendations emerging from research, monitoring evaluation and review activity.

- Provide explanations for any actions or lack of action associated with findings and relevant recommendations emerging from research, monitoring, evaluation and review activity.

7. Implementing a compliance strategy to ensure that fishers conform to the harvest control tools and bycatch management requirements.

The progress of the actions completed in 2021/2023 are as follows:

Goal 1: Stock status improved and reference points applied in management

The status of the Milestones for each Goal are listed below:

Blue = Completed
Green = Ongoing

Red = Not done

Goal 1: To ensure that the tuna catches do not exceed sustainable levels

Outcome 1.1: Stock status improved and reference points applied in management

Milestone 1: MARD/RIMF participating in SC WGs and WCPFC general session discussions on reference points

Milestone 2: Setting of LRPs and TRPs at WCPFC for all species (YFT, BET)

Milestone 3: MARD/RIMF participating in SC WGs for the revision of the core WCPFC CMM on bigeye and yellowfin strategy

Milestone 4: Catch and / or effort limits set for bigeye and yellowfin tuna for Vietnam other commercial fisheries (WCPFC CMM 2016-01, papa 46/47) (either 2001-2004 levels or an alternative) and based on an historic reference point

Outcome 1.2: Data collection and Information systems strengthened

Milestone 5: Logbook coverage > 75% for HL, and improved coverage of other fisheries

Milestone 6: Port sampling for key gear types implemented in all main ports/provinces

Milestone 7: Tuna vessel register operational at Provincial level linked to National recording system

Milestone 8: National tuna data collection system implemented and fully effective

Outcome 1.3: Management strategies applied and supported by tools and the application of strong information and research.

Milestone 9: Vietnam compliant with CMM 2021-01 or any subsequent amendment

Milestone 10: Compliance reporting and annual report on the effectiveness of the CMM

Milestone 11: Workshop on exploring options for input (effort) and output (quotas) for longline and handline fisheries based on TRPs and LRPs and CMM 2012-01 (years 2001-2004 levels)

Milestone 12: Establishing a framework within which harvest control rules would be set and delegating appropriate responsibilities to the Provinces

Milestone 13: Introduction Vietnamese management measures for all tuna fisheries in Vietnam

Milestone 14: Fisher awareness programme

Milestone 15: Undertake and assess evidence that the measures established are effective

Goal 2:  To promote the ecosystem based approach to fisheries management

Outcome 2.1: Primary and secondary  species subject to a management strategy

Milestone 16: Establish an observer scheme to monitor all catches of retained species and document the level of discarding from the handline and longline fisheries

Milestone 17: Extend port sampling procedures to cover primary and secondary species (and informed by the observer scheme)

Milestone 18 Document observer data and port sampling verification, and prepare summary reports of main and vulnerable species (retained) interactions other than bigeye tuna

Milestone 19 Training in risk assessment and the application of EAFM

Milestone 20 Prepare a risk assessment report based on observer data

Outcome 2.2: Shark management measures implemented

Milestone 24b: Prohibit shark finning at sea

Milestone 25: Ensure that all shark species are covered under observer reporting above

Milestone 26: Fisher shark awareness programme

Milestone 27: Evaluate the effectiveness of management measures for shark species identified in the CMMs and CITES

Outcome 2.3: Turtle management strengthened

Milestone 28: Ongoing monitoring of turtle bycatch and life status in the handline fisheries (Milestone 13 and 15)

Milestone 29a: Implement effective management mitigation measures for turtles which are as close to zero as possible and Implement an optimum management mitigation strategy with support measures which aim to (a) reduce turtle interactions as close to zero as feasible and (b) are consistent with national and international (WCPFC) obligations and the NPOA-Turtles. consistent with national and international (WCPFC) obligations.

Milestone 30: Fisher awareness programme

Milestone 31: Evaluate the effectiveness of management mitigation measures for turtles based on best practice

Outcome 2.4: Habitats subject to a management strategy

Milestone 32: Gear losses incorporated into observer reporting

Goal 3: To strengthen governance systems in Vietnam Tuna management

Outcome 3.1: Fisheries Law effectively implemented

Milestone 36: Clarification of the application of the Convention (and CMMs) to Vietnam

Milestone 37: Vietnam becomes a WCPFC CCM

Milestone 38: National legal system effective and organized and effective cooperation with other parties, where necessary, to deliver management outcomes consistent with MSC Principles 1 and 2

Milestone 39: Applying relevant tuna regulations/decrees (catch/effort limits etc)

Milestone 40: Tuna Fishery Consultation Council fully operational and all roles & responsibilities defined

Outcome 3.2: Roles and responsibilities and consultation processes fully implemented

Milestone 41: Explicit reference would have to ensure that any change in fleet capacity takes account of the precautionary approach to fisheries management, and adherence to appropriate scientific advice, most specifically adhering to the LRPs set in management

Milestone 42: Evidence would need to show that the Precautionary Approach to Fishery Management (PAFM) is explicitly understood and enacted at both national and provincial level

Outcome 3.3: Management Plan

Milestone 43: Definitions to include handline fisheries and all target species

Milestone 44: Management Plan finalised, complies with MSC principles and contains a consultation process and includes a monitoring & performance component

Outcome 3.3: Decision making process strengthened

Milestone 46: Introduce clear guidelines for taking management decisions, probably as a component of the management plan.

Milestone 47: Evidence is available that explanations to be provided for decisions taken, and should follow the basis of the management plan when introduced, which may include precautionary actions

Outcome 3.4 Effective application of compliance systems

Milestone 48: Risk assessment of enforcement actions following the introduction of P1 and P2 associated management measures

Milestone 49: Review of sanctions for non-compliance

Milestone 50: Effective evidence of systematic compliance and an effective system of sanctions

Outcome 3.5: A national research plan is in place

Milestone 51: A research plan prepared publically available

Milestone 52: Research results are disseminated to all interested parties

THE REVISED ACTION PLAN

## GOAL 1. STOCK STATUS AND FISHERIES MANAGEMENT: TO ENSURE THAT THE TUNA CATCHES DO NOT EXCEED SUSTAINABLE LEVELS

Outcome 1.1 Stock status improved and reference points applied in management

A new WCPFC stock assessment for yellowfin, were published in 2020 (Vincent, et al, 2020) and bigeye (Ducharme-Barth  et al, 2020). Yellowfin tuna eexploitation of WCPO yellowfin tuna to be below FMSY. Median Frecent/FMSY was 0.36 (80 percentile range: 0.27-0.47) but above above20%SBF=0,. The yellowfin assessment shows that the stock is highly likely to be above the PRI (MSC V2, P1.1.1SG 80 a). The problem issues are that: Reportedly large increases in catches of small yellowfin tuna have been occurring in WCPFC Region 3 (Indonesia, Philippines and Papua New Guinea) since 2012.

The bigeye tuna stock WCPO bigeye tuna to be above 20%SBF=0 with a downturn in recruitment. However, the bigeye tuna stock assessment shows that the stock is highly likely to be above the PRI (MSC V2, P1.1.1SG 80 a).

Activity 1.1.1: WCPFC would have to set explicit limit reference points which are consistent with the MSC definition of BLIM (0.2 B0), and for these to be applied to the harvest strategy (1.2.1).

The associated milestones are:

- Milestone 1: MARD/RIMF participating in SC WGs and WCPFC general session discussions on reference points

- Milestone 2: Vietnam Setting of LRPs and TRPs at for all species caught including specifically for YFT,  and BET.

The first component falls to the explicit responsibility WCPFC in setting limit and target reference points. However, the introduction of these reference points will also have to apply as a component of Vietnam’s tuna management strategy (Activity 1.3.1).

Limit Reference points were initially set for these species at the WCPFC General Session (WCPFC, 10) at 20%SB recent, F=0. (WCPFC 10). Target Reference points are under revision with the intent of having an agreed TRP and Harvest Strategy by 2024.

A harvest strategy exists for WCPFC tuna species in WCPFC CMM 2021-01. The strategy makes explicit reference to the PNA purse seine VDS scheme, effort controls for other purse seine fisheries and the implementation of limits for other commercial fisheries. If Vietnam wishes to pursue WCPFC membership, as well as MSC Certification, it will have to address the issue of compatible measures and the implementation of input or output controls on its commercial fisheries where catches exceed 2,000 metric tonnes (yellowfin, bigeye and skipjack) in any of Vietnam’s commercial fisheries. These controls will have to demonstrate that management measures are in place to implement actions, if the stock falls below the Limit Reference point, or approaches the Point of Recruitment Impairment (PRI).

Following an agreement on strategy at WCPFC,  the Government of Vietnam would be required to set an explicit  LRP of 20 %SB recent, F=0 and a TRP, at the same level as agreed by WCPFC.  A three-country stock assessment workshop was held in Haiphong, Vietnam (WPEA, November, 2015). These showed the bigeye biomass already below the LRP; and the Yellowfin biomass in decline. This would suggest that there would need to be a reduction in the current level of effort over and above the CMM requirements.

MARD officials usually attend these meetings, when there is a need for stock assessment specialists to attend.

| Assigned stakeholders | WCPFC with MARD and RIMF participation |
| --- | --- |
| Priority | High |
| Status | Priority for implementation |
| Timeframe | Dec 2025 |
| MSC Performance Indicator(s) | 1.1.1 Stock status and 1.2.3 Stock Assessment. |

Activity 1.1.2: An effective rebuilding strategy would have to be implemented for bigeye tuna. This will require CCM and CNMs to implement effective measures, but could only be achieved in the much longer term, i.e. 5-10 years, or greater.

The associated milestones are:

Milestone 3: MARD/RIMF participating in SC WGs for the revision of the core WCPFC CMM on bigeye and yellowfin strategy

Milestone 4: Catch and / or effort limits set for bigeye and yellowfin tuna for Vietnam consistent with WCPFC methodology (either 2001-2004 levels or an alternative) and based on an historic reference point.

Vietnam fishery managers, D-FISH (national) and scientists (RIMF) need to participate at the WCPFC SC, but also at any specific WG. These meetings are held at the annual WCPFC Science Committee meetings, or any specific sub regional meetings such as those conducted under WPEA.

D-Fish has set out an Adjustment Plan and Outline for Implementation of the Tasks “the Target fishing quality state term in Vietnam’s sea program 2020-2025 period (Box 1)

Box 1: Progress towards Vietnamese Tuna Harvest Strategy and Management Tools

Determining quotas and piloting allocation of ocean tuna catch quotas (yellowfin, bigeye) for tuna fishing in the provinces: Binh Dinh, Phu Yen and Khanh Hoa. - Develop a mechanism to monitor and manage tuna fishing quotas (yellowfin, bigeye) for tuna fishing in the provinces: Binh Dinh, Phu Yen and Khanh Hoa. Period 2022 – 2025: - Determining quotas, assigning tuna fishing quotas (yellowfin, bigeye, skipjack) for seine, gillnet and handline fisheries in 10 provinces and cities City: Da Nang, Quang Nam, Quang Ngai, Binh Dinh, Phu Yen, Khanh Hoa, Ninh Thuan, Binh Thuan, Ba Ria – Vung Tau, Tien Giang. - Developed a mechanism to monitor and manage tuna fishing quotas for seine, gill and hanline fishing in 10 provinces and cities: Da Nang, Quang Nam, Quang Ngai, Binh Dinh , Phu Yen, Khanh Hoa, Ninh Thuan, Binh Thuan, Ba Ria – Vung Tau, Tien Giang. - Proposing and submitting to competent authorities the model of Organization in charge of quota assignment and management. Content 1. Assessment of the current status of tuna fishery in Vietnam's waters. - Review and collect existing data and data and collect additional data; - Overview and assessment of the current status of tuna resources in Vietnam's waters. - Assess the current status of tuna fishing in Vietnam's waters; determine the fleet structure, output structure, fishing productivity and economic efficiency of the ocean tuna fishing fleet. - Assessment of the current status of infrastructure and logistics services for tuna fishing in Vietnam's waters. - Assess the socio-economic conditions of the fishing community engaged in ocean tuna fishing such as: education level, age structure, labor, customs, income and degree of dependence on tuna fishery; - Evaluate the management and requirements of the yellowfin and bigeye tuna chain industry. - Reviewing regulations on monitoring, inspection and control of fishing quotas in Vietnam. - Collect additional data on operating coefficient (BAC) of fleets; Content 2. Research to determine the quota of tuna catches (yellowfin, bigeye) for fishing in the central waters of Vietnam. - Research to determine the maximum sustainable catch and optimal fishing force for tuna fishing in Vietnam's waters. - Research to determine the right tuna fishing quota for fishing fleets in the central waters. Content 3. Pilot implementation of quota allocation for ocean tuna fishing (yellowfin, bigeye) in central coastal provinces. - Piloting the allocation of catch quotas to tuna fishing fleets in the provinces of Binh Dinh, Phu Yen and Khanh Hoa. - Provide a mechanism for allocating, monitoring and managing tuna fishing quotas suitable for fishing fleets. 5.2. Period 2022 - 2025: Content 1. Summarizing and evaluating the results of piloting the allocation and management of catch quotas for yellowfin and bigeye tuna fishing in 3 provinces - Summarizing and evaluating the results of piloting allocation and management of fishing quotas for yellowfin and bigeye tuna fishing in the provinces of Binh Dinh, Phu Yen and Khanh Hoa. - Assessing the impact of the allocation of quotas for tuna catches positive for fishing activities. Content 2. Assessment of the current status and fluctuations of the tuna fishery (yellowfin, bigeye, skipjack) in the waters of Vietnam. - Assess the current status and changes of tuna fishery in Vietnam's waters. - Collect additional data and analyze the current status of tuna fishing activities in Vietnam's waters. - Collect additional data on the activity coefficient (BAC) of tuna fishing fleets. Content 3. Research, determine the quota of tuna catches (yellowfin, bigeye, skipjack) in the waters of Vietnam. - Research to determine the maximum sustainable catches and optimal fishing intensity for tuna fishery in Vietnam's waters. - Research and determine the right tuna fishing quota for seine, gillnet and fishing fleets in the offshore waters of Vietnam. Content 4. Develop a mechanism to manage, allocate and assign quotas for tuna catches (yellowfin, bigeye, skipjack) in Vietnam's waters. - Develop a mechanism for allocating and managing catch quotas for fleets engaged in seine, gillnet and handline. - Study and propose appropriate quota allocation for fishing fleets engaged in seine, gillnet and tuna fishing in the central and southeastern coastal provinces. - Develop a mechanism to adjust fishing output quotas according to the annual cycle suitable for fleets. - Proposing and submitting to competent authorities the model of Organization in charge of quota assignment and management. Content 5. Develop solutions to develop the tuna fishery in Vietnam's waters in a sustainable and responsible manner. - Solutions to mechanisms and policies to develop the tuna fishing industry. - Solutions to develop a fleet of tuna fishing boats. - Solutions to develop infrastructure, logistics services for tuna fishery. - Scientific, technical, technological solutions and trade promotion.

| Assigned stakeholders | WCPFC with MARD and RIMF participation; |
| --- | --- |
| Priority | High |
| Status | Priority for implementation |
| Timeframe | 2020-2025 |
| MSC Performance Indicator(s) | 1.1.3 and 2.1.1 Target species and rebuilding (retained bigeye) |

### Outcome 1.2 Data collection and Information systems strengthened

Activity 1.2.1: Continue to improve national data collection and monitoring at all levels

The associated milestones are:

Milestone 5: Logbook coverage > 75% for LL and HL, and improved coverage of other fisheries e.g. purse seine, gillnet

Milestone 6: Port sampling for key gear types implemented in all main ports/provinces

Milestone 7: Tuna vessel register operational at Provincial level linked to National recording system

Milestone 8: National tuna data collection system implemented and fully effective

Collection of catch and landings data for Vietnamese oceanic tuna fisheries is primarily undertaken at provincial level, with provincial fisheries organizations (Sub D-DECAFIREP) based in the main landing sites. The collection of provincial data has been considerably strengthened with support since 2010 from the West Pacific East Asia Oceanic Fisheries Management Project (now about to enter WPEA OFM III) and covers improved logbook recording, landings records and port sampling. These data are fed from Sub DECAFIREP to D-FISH, where they are entered and collated, then incorporated in mandatory reporting to WCPFC. The national data collection system (VN-Fishbase) developed for the oceanic tuna fishery by FiCen is operational.

The milestone has NOT achieved its objective, but not at the intended target of 75%. The management authorities use TUFMAN to manage and report on their data and will move to TUFMAN 2 over the next year or so.  Logbook coverage of the handline fishery is reasonably progressing in seven main producing provinces, including Binh Dinh, Phu Yen, Khanh Hoa (up to 57%). Coverage of port sampling and landings is reasonable.   The data is included in the SPC stock assessments.

Logbook training has been applied by D-Fish/VINTUNA and WWF. Industry companies support the LB program and promote purchasing policies from those vessels working with the logbook training program.

The vessel registry (VNFISHBASE) is now fully operational. Central database linked to the Provinces. This is encoded at Provincial level. This is reported to MARD. Provinces also send a copy to RIMF and incorporated into commercial fishery database.

Because of overall harmonization is WCPFC assessments, information is currently scored at > 80. SPC note considerable improvement in the quality of data available (WPEA Report, 2020). However, were the Vietnamese fisheries subject to assessment, it is quite likely that the MSC assessors would add a Recommendation to increase the quality of data available from Vietnam.

The principal partners for these activities are fishermen sub DECAFIREP and D-FISH.

| Assigned stakeholders | WCPFC with MARD and RIMF participation; |
| --- | --- |
| Priority | High |
| Status | Ongoing and subject to continual improvement |
| Timeframe | Dec 2025 |
| MSC Performance Indicator(s) | 1.2.3 Target species information |

### Outcome 1.3 Management strategies applied and supported by tools and the application of strong information and research.

Activity 1.3.1: Implementation of a compatible harvest strategy in Vietnam waters (and compliance with CMMs), which would include longline, purse seine and handline fishing, and would be consistent with Vietnam’s obligations developed through any future changes to 2012-01.

The following Milestone is in place:

Milestone 9: Vietnam's compliant with CMM 2021-01, or any subsequent amendment

Clarification of Vietnam’s management obligations to WCPFC (Activity 3.1.1) have been evaluated in a paper submitted by Poseidon on behalf of WWF to the FIP group. The paper concludes that irrespective of the issue of the South China Sea falling outside the Convention Area, if Vietnam is serious about pursuing membership of WCPFC, it must implement the CMMs, and most specifically, must formulate compatible management strategies consistent with those required of ‘other commercial fisheries’ catching > 2,000 mt of skipjack, yellowfin and bigeye tuna.  It is also noteworthy that in order to achieved MSC status, irrespective of the Convention issues, Vietnam must should implement CMM 2016-01.

| Assigned stakeholders | WCPFC/MARD/D-Fish/sub DECAFIREP; |
| --- | --- |
| Priority | High |
| Status | Strengthening existing understanding |
| Timeframe | Dec 2025 |
| MSC Performance Indicator(s) | 1.2.1 Harvest strategy |

Activity 1.3.2: Setting a monitoring system in place (consistent with CMM 2010-03) which evaluates the effectiveness of the management measures

Milestone 10: Compliance reporting and annual report on the effectiveness of the CMM

This component falls to the explicit responsibility MARD and D-Fish to monitor the application of measures at sub DARD level. D-Fish will have to design, and amend a set of measures that follow the above CMMs, and then monitor compliance. An annual report will be submitted from sub DECAFIREP to D-Fish to MARD.

The Confidential Part 2 Compliance report reportedly contains reference to ‘Non Applicable’ for these measures. D-Fish has indicated a willingness to comply with these standards, but this requires a higher level decision (MARD) to support this initiative..

| Assigned stakeholders | WCPFC/MARD/D-Fish/sub DECAFIREP; |
| --- | --- |
| Priority | High |
| Status | Changing status to implementing the measures and having these evaluated |
| Timeframe | Dec 2025 |
| MSC Performance Indicator(s) | 1.2.1 Harvest strategy |

Activity 1.3.3: Establishing national harvest control rules (input and output restrictions) across the range of tuna fisheries which allow for limits to be implemented as reference points are approached. The rules and tools will need to take account of best practice examples to illustrate their appropriateness (e.g. overall capacity limits, quotas and closed seasons).

The following milestones are in place, but have yet to be implemented

Milestone 11: Workshop on exploring/establishing limits based on TRPs and LRPs and CMM 2012-01 (years 2001-2004 levels), and making allowances for uncertainties

Milestone 12: Establishing a framework within which harvest control rules would be set and delegating appropriate responsibilities to the Provinces

Milestone 13: Introduction Vietnamese management measure for the Vietnam tuna fishery

Milestone 14: Fisher awareness programme

Milestone 15: Undertake and assess evidence that the measures established are effective.

Once Reference points have been set in management, the Government of Vietnam will need to review its system of management tools for all its fisheries. These would cover either output controls (quotas) or input controls (limits to vessels, days or closed season. This requites a commitment  to funding a national workshop of Harvest Strategy development.

| Assigned stakeholders | MARD/D-Fish/sub D-Fish/fishers; WWF |
| --- | --- |
| Priority | High |
| Status | Priority for implementation |
| Timeframe | Dec 2025 |
| MSC Performance Indicator(s) | 1.2.1 Harvest Strategy and 1.2.2 Harvest control rules and tools |

Recommendation 1 for 2016/2015 is for Vietnam to develop its harvest strategy for all its fleets catching more than 2,000 mt in conformity with Para 54/55 (WCPFC 2021-01).

The following actions would therefore need to be considered:

1`. Implement species specific Limit Reference Points for yellowfin and bigeye tuna at 20% SB0.

2. Analyse catch data by species to determine fleet catches > 2,000 mt

3. Discuss alternative reference year strategies, from 2001-2004, with Indonesia and Philippines

3. Develop national limits for longline, handline and other Vietnamese commercial fisheries

4. Extend these limits to each Province

5. Provide detailed breakdown of fishery limits to WCPFC.

6 Ensure that the Provinces implement a monitoring system to ensure compliance.

Section 4.4 contains a specific Terms of Reference for a series of workshops. Funding for this initiative will have to be investigated.

## GOAL 2. ECOSYSTEM MANAGEMENT: TO PROMOTE THE ECOSYSTEM BASED APPROACH TO FISHERIES MANAGEMENT

### Outcome 2.1: Primary and secondary species subject to a management strategy

Activity 2.1.1: Document the catch of bigeye tuna, shark, billfish, baitfish and other species in the handline and longline fisheries (See FIP action 2.1.3). Note that there are already WCPFC CMMs in place that require selected pelagic shark species catches to be recorded

Milestone 16: Establish an observer scheme to monitor all catches of retained species and document the level of discarding from the handline and longline fisheries

Milestone 17: Extend port sampling procedures to cover retained species (and informed by the observer scheme)

Milestone 18: Document observer data and port sampling verification, and prepare summary reports of main and vulnerable species (retained) interactions other than bigeye tuna.

Accurate information has been collated on total removals from the fishery including for primary and secondary species. Catches of protected shark species as per the Convention of Migratory species (oceanic whitetip or silky sharks, hammerhead, thresher and porbeagle) are singularly likely to be below 2%. However, logbooks have been amended to include recording of shark species and there is a process in place to ensure that shark species caught are accurately recorded. The status of baitfish stocks harvested for longline and handline fisheries is likely to be low risk.

An observer program has commenced and is aimed at collecting operational and by-catch/ETP species data. Current deployment is estimated to be less than 2% of the total trips. Much of the early work has been through the support of WWF and Sea Delight. The observer training has been undertaken with the support of the WPEA program, using SPC training modules. The early work is intended to guide eventual industry-funded larger scale observer placement. VinaTuna is identifying ways to expand the observer scheme and will establish a cost recovery system.

WPEA II is also committed to strengthening the port sampling program set up under WPEA I This will incorporate identification of secondary species and ETPs species, as well as implement testing of key target species inputs such as weight size and trophic content sampling.

| Assigned stakeholders | sub DECAFIREP/RIMF/Fishers/private sector; |
| --- | --- |
| Priority | High |
| Status | Implemented |
| Timeframe | Dec 2025 |
| MSC Performance Indicator(s) | 2.1.3, 2.2.3 and 2.3.3 Retained species (including bait), bycatch and ETP status |

Activity 2.1.2: Undertake primary species and secondary management strategy for all billfish and bait stocks (e.g. squid and flying fish) and any other retained or bycatch species, if data shows catch rates to be 5% or more.

The following milestones are in place.

Milestone 19: Training in risk assessment and the application of EAFM

Milestone 20: Prepare a risk assessment report based on observer data (Revised wording)

Earlier Milestones 21 to 23 are deleted

Secondary species information has been reviewed and subject to a risk assessment by RIMF. The Risk Based framework for longline (Figure 3) and handline (Figure 4), has identified 6 main species for handline respectively. With the new data available from the observer programs, Swordfish and Blue Marlin have been identified at 4-8% of the total catch respectively, with Swordfish at 6% COPA) (main) and Blue Marlin (8%).  Stock assessments are available from WCPFC https://www.wcpfc.int/current-stock-status-and-advice:

North Pacific Swordfish: https://www.wcpfc.int/doc/07/north-pacific-swordfish

# Pacific Blue Marlin: https://www.wcpfc.int/doc/11/pacific-blue-marlin

Neither species are subject to overfishing, neither require necessary management action (P2), and both species are identified as Low Risk within the RIMF Risk assessment;

Figure 3 Risk assessment conducted for the longline and handline fisheries

3ii Handline

Source: RIMF (Appendix 1)

Commenced with pilots in 2021, the FIP has initiated a program of at-sea crew-based monitoring of ETP bycatch (COPPA program).  This program has proven to be successful and useful to DFISH, and will be continued through to the envisioned FIP end date i.e. Dec 2025

| Assigned stakeholders | RIMF/NIO, DECAFIREP/sub DECAFIREP/fishers & processors; Vinatuna |
| --- | --- |
| Priority | High |
| Status | Implemented |
| Timeframe | Dec 2025 |
| MSC Performance Indicator(s) | 2.1.1. 2.2.1, 2.3.1, 2.1.2, 2.2.2, 2.3.2 Primary and Secondary species. |

### Outcome 2.2: Shark management measures implemented

Activity 2.2.1: Implement the requirement that shark fins are landed attached to the carcass and that there is no evidence of finning taking place at sea

Milestone 24: Prohibit shark finning at sea

Milestone 25: Ensure that all shark species are covered under observer reporting above

Milestone 26: Fisher awareness program

Milestone 27: Evaluate the effectiveness of management measures for shark species identified in the CMMs and CITES

The WPEA OFM program includes provision to ensure the accurate recording of shark species in order to determine the numbers caught and to assess potential risks to these species. Observer training will also strengthen the capacity of observers and port samplers to identify shark species. WWF and partners will also apply and educational program for fishers aimed at eliminating the practice of finning, supported by the buyers.

The revised Decree 26 now includes prohibitions on harvest of all shark species historically documented in the HL tuna fishery, including blue shark (the only species that has flagged as “medium risk” in the 2019 Risk Assessment).  There are reports of widespread communications (speaker announcements) at the ports instructing fishers to not retain shark species and to refrain from finning activities. VINATUNA have continued with various stakeholder awareness workshops and materials (e.g. ETP posters) throughout 2023/2024 and with new, modest support from Resource Legacy Fund to continue this outreach in 2025.

| Assigned stakeholders | DECAFIREP/sub DECFIREP/fishers and processors; WWF |
| --- | --- |
| Priority | High |
| Status | Implemented |
| Timeframe | Dec 2025 |
| MSC Performance Indicator(s) | 2.1.2, 2.2.2 ETP and secondary (shark) management |

### Outcome 2.3 Turtle management strengthened

Activity 2.3.1: Monitor and implement a turtle management mitigation policy.

Milestone 28: Monitor of turtle bycatch and life status in the handline and longline fisheries

(Milestone 13 and 15)

Milestone 29 a: Implement an optimum management mitigation strategy with support measures which aim to (a) reduce turtle interactions as close to zero as feasible and (b) are consistent with national and international (WCPFC) obligations and the NPOA-Turtles (New wording)

New Milestone 29 b: Where risks are identified, instigate trials to reduce the interactions. Once incorporated, this is likely to achieve a pass.

Milestone 30: Fisher awareness program

Milestone 31: Evaluate the effectiveness of management mitigation measures for turtles based on best practice

IUCN/DECAP has prepared a Marine Turtles Action Plan 2015-2020, to be approved by MARD by 2016

Observer data do tend to show low levels of interaction, and low mortality rates (1 in 5 dead on capture). Vietnam has its own prescribed Decree, which prohibits the landing of turtles. Turtle avoidance also forms part of the occasional Sub D-Fish educational process at regional level. Evidence from workshops and published work, however, suggests that mitigation measures in the form of circle hooks have not been fully implemented (WWF 2021) and scientifically and thus an optimum mitigation strategy has not been developed, nor have circle hooks been fully within the fishery.  Studies completed by VinaTuna (2021) have indicated that C-hook use in the HL fishery has grown steadily since the commencement of awareness programs and at-sea trials under the FIP, and now sits at approximately 40% usage.

The FIP continues to work with DFISH in advocating for stronger language re: turtle mitigation strategy inside of the National Tuna Management Plan, and for general wider adoption of C-hooks.  VINATUNA have continued with C-hook distribution and testing with the fleet, including stakeholder awareness workshops and materials (e.g. posters) throughout 2023/2024 and with new, modest support from Resource Legacy Fund to continue with C-hook activities in 2025.

Box 2: Implementation report on Turtle Mitigation Management

Khanh Hoa has the highest level of experience using C-hooks among the three provinces with 59.6% of respondents saying that they have used circle hooks. While Binh Dinh and Phu Yen have 45.3% and 30.7% of respondents who have used C-hooks, respectively. (WWF 2021) The evaluation: RESULTS 5 YEARS OF IMPLEMENTATION SEA WASHING CONSERVATION ACTION PLAN FOR 2016 – 2025 provides background to the implementation of the Turtle Management Mitigation Strategy The legal document system has been built and basically completed to meet the requirements of protection and conservation of sea turtles and international integration. Research, application, and improvement of KTHS fishing gear have been initially carried out, with initial results in reducing the rate of unintentional fishing for sea turtles, especially tuna fishing. Con Dao National Park is recognized as a member of IOSEA Sea Turtle Conservation Area Network (TCTS/Con Dao National Park - 2019) The natural spawning grounds of sea turtles are mostly located in the MPA and are strictly protected; The rescue and re-release of sea turtles has been done well, with the participation and coordination of management agencies and the whole society. The communication and training to raise awareness and capacity building on the protection and conservation of sea turtles are well implemented, creating effective and pervasive effects in the whole society. The detection and handling of violations on protection and conservation of sea turtles has made positive changes with the participation of many stakeholders. Regulations on the protection of sea turtles in particular and endangered, precious and rare aquatic species still overlap, leading to difficulties in enforcement. Funding for the implementation of priority tasks and projects is limited, leading to many un-implemented or asynchronous contents, so the efficiency is not high. The sea turtle conservation plan still lacks content to control, prevent illegal trade, and handle violations of sea turtle traffickers; There is no clear role of law enforcement forces such as: CSMT, Customs, QLTT, Army, Fisheries control... Some priority projects have not yet received funding for implementation (DFISH, 2021).

The results indicate that Milestone 29 has only been partially achived.

| Assigned stakeholders | MARD/WWF/VINATUNA/D-Fish/sub D-Fish/DARD; WWF |
| --- | --- |
| Priority | High |
| Status | Ongoing |
| Timeframe | Dec 2025 |
| MSC Performance Indicator(s) | 2.1.3 ETP status |

### Outcome 2.4. Habitats subject to a management strategy

There are no habitat impacts associated with the handline fishery. The parallel MSC assessment of the Philippines fishery. Unlike other handline fisheries in the South China Sea and Western Pacific (Indonesia and Philippines), Vietnamese fishers to not use FADs, and there are no benthic interactions.

### Outcome 2.5: Ecosystems and biodiversity assessments made for the Vietnamese and South China Sea region

Activity 2.5.1: Assess the ecosystem impact for the Vietnam EEZ /South China Sea Sub region

Some work has been undertaken by SPC on the ecological effects within the western Pacific as a whole. These indicate a very diverse ecosystem and broad resilience of the ecosystem to high levels of exploitation whilst the biomass remains high. However, if the biomass is reduced for apex predators including yellowfin, bigeye and shark species, the dynamics may well change for the worse. This therefore requires an extension of the trophic ecosystem modeling work to include the South China Sea.

Modeling the impact of fishery removals on the ecosystem has been undertaken as part of the SEAPODYM research provided by CLS.

The Philippines tuna handline assessment did not score the contribution to Ecosystems from the handline fishery, and the fishery achieved SG 80 based on the wider ecosystem work undertaken by SPC.

| Assigned stakeholders | D-Fish / WPEA |
| --- | --- |
| Priority | Intermediate |
| Status | Removed as a FIP requirement |
| Timeframe | 2017 |
| MSC Performance Indicator(s) | 2.5.1, 2.5.2, 2.5.3 Ecosystem status: |

## 3. GOVERNANCE SYSTEMS: TO STRENGTHEN GOVERNANCE SYSTEMS IN VIETNAM’S TUNA FISHERY

### Outcome 3.1: Fisheries Law effectively implemented

Activity 3.1.1: Clarification of Vietnam's status within the convention, and extension of the convention area to the Vietnam

Milestone 36: Clarification of the application of the Convention (and CMMs) to Vietnam

Milestone 37: Vietnam becomes a WCPFC CM (Commission Cooperating Member Member)

There is presently no clarity on how WCPFC CMMs are presently treated in Vietnam. Whilst Vietnam is a CNM, as the convention area does not extend to the South China Sea, the binding nature of the country is uncertain and requires clarification. However, WPEA II accepts that CMMs should be mainstreamed and implemented with the programmes support. Whilst Vietnam’s status as a CNM is linked to support to data collection, pursuit of full membership is likely to require CMM implementation.

Fisheries Law and Decree No 33/2010/ND-CP states that the government needs to cooperate with other parties, where necessary, to enhance effective management of fisheries The Law of the Land supports this by providing land title/exclusive rights for clam cooperatives. The Fisheries Law also includes protection of environment and habitat (Article 15).

Others laws also provide a framework for Principle 2; e.g. Biodiversity Protection Law (see Luu. 2009, p22), Law of Marine Resources and Environment, Law on Environment Protection. There are various decrees underneath these laws

Vietnam Civil Law sets out requirements for the Ministry to collaborate with other sectors and local government to achieve objectives of laws. No other countries are involved – no international binding procedures are required.

Amendments to the current National fisheries law are still in progress 2017. The amendments will need to be checked to ensure that the law supports management outcomes consistent with MSC Principles 1 and 2. It is highly probably that legal drafting has taken account of advice (Nguyen, et al).

| Assigned stakeholders | WCPFC/MARD |
| --- | --- |
| Priority | High |
| Status | Developing existing activity |
| Timeframe | 2017 |
| MSC Performance Indicator(s) | 3.1.1 Legal and customary framework |

Activity 3.1.2:  Revise fisheries legislation containing the core elements which prioritise sustainable fisheries, and contain provisions for automatic implementation of international conventions including the WCPFC CMMs

Milestone 38: National legal documentary system, effective and organised and effective cooperation with other parties, where necessary, to deliver management outcomes consistent with MSC Principles 1 and 2

Milestone 39: Effectively applying of relevant tuna regulations/decrees (catch/effort limits etc)

Vietnam should also introduce a number of core principles into its legislation

- Adherence to WCPFC’s regulations and CMMs in order to comply with Article 25 of WCPFC. This includes extension to Decree 31, stipulating regulation on financial penalties with fishing vessels violating WCPFC’s regulations.

- to ensure fishing operations must be associated with economic efficiency and protecting and restocking marine resources; conserving related marine ecosystems and biodiversity, protecting marine environment and its natural landscapes. Fisheries sector development strategies must be planned to be associated with national and local fisheries management plans.

| Assigned stakeholders | MARD |
| --- | --- |
| Priority | High |
| Status | Expansion of existing activities |
| Timeframe | Ongoing |
| MSC Performance Indicator(s) | 3.1.1 Legal and customary framework |

### Outcome 3.2: Roles and responsibilities and consultation processes fully implemented

Activity 3.2.1: Implementation of the Consultation Council through the NTMP process

Milestone 40: Tuna Fishery Consultation Council fully operational and all roles & responsibilities defined

The Tuna Fisheries Consultation Council (TFCC), created by the Government of Vietnam, under the management of VINATUNA, serves the important purpose of closely re-evaluating current management measures to formulate interim precautionary management measures, as well as long term, management measures. The composition of the TFCC includes: MARD, relevant members of the Peoples Committee, D-Fish, DARD, relevant sub DECAFIREP/DARD management and compliance officials, RIMF, VINATUNA, nominated industry representatives and WWF.

| Assigned stakeholders | VINATUNA and all stakeholders |
| --- | --- |
| Priority | High |
| Status | Ongoing |
| Timeframe | Ongoing |
| MSC Performance Indicator(s) | 3.1.2 Consultation, roles & responsibilities |

Activity 3.2.2: Revise the a tuna fisheries strategy so that long term and short term objectives demonstrate effective implementation of sustainable fisheries management systems

Milestone 41: Explicit reference would have to ensure that any change in fleet capacity takes account of the precautionary approach to fisheries management, and adherence to appropriate scientific advice, most specifically adhering to the LRPs set in management

Milestone 42: Evidence would need to show that the Precautionary Approach to Fishery Management (PAFM) is explicitly understood and enacted at both national and provincial level

MSC scoring requires strategic long-term objectives to guide decision making, consistent with MSC principles 1 and 2, and the precautionary approach. The current national strategy (2010) focuses heavily on growth and objectives, but with one reference to sustainability development. Hence, either there needs to be some provision to revise the strategy, or incorporate changes into law (Activity 3.1.2). Note that assessors will have to satisfy themselves that sustainability objectives are not secondary to growth objectives.

Vietnam must ensure that it conforms to the strategy to reduce effort on bigeye tuna, and not increase effort on yellowfin. Proposals to expand catches offshore and on the high seas are not consistent with the requirements of WCPFC. It is accepted however, that issues such as the 2001-2004 reference years may be inappropriate, and these are issues where Vietnam could work together with Philippines and Indonesia.

| Assigned stakeholders | VINATUNA and MARD |
| --- | --- |
| Priority | High |
| Status | Currently in process |
| Timeframe | Ongoing |
| MSC Performance Indicator(s) | 3.1.3 Short and long term objectives |

### Outcome 3.3: Fishery specific management objectives applied

Activity 3.3.1: The handline fishery is included along with the other tuna fisheries contained within the management plan

Milestone 43: Definitions to include handline fisheries and all target species

Milestone 44: Management Plan finalised, complies with MSC principles and contains a consultation process and includes a monitoring & performance component

Milestone 45: Evidence that the management plan is being applied and its effectiveness is assessed by a process of regular internal and external reviews

MARD Circular  42 adopts the Tuna Management Plan. This is supported by Decision 3562 (Tuna Management National Action), 10 September 2015, gazetting the Plan into Law. The Plan contains all the appropriate requirements, i.e. short and long term objectives, as well as a commitment to ecosystem-based tuna fisheries management. The plan also contains a list of outcomes, activities and measurable indicators. The current TMP refers to ‘cau’ which includes both handline fisheries and longline fisheries.

The application of the management system, as defined in the Plan, is reviewed internally every year (as per law). However, it is noteworthy that for MSC purposes, an external performance review would be appropriate. The definition of external review includes a government or research department external to the management organisation. External review could therefore include either MARD Policy Unit, or independent qualified consultant.

Some explicit actions should be reviewed in respect to the Plan.

Activities and Implementation Plan:

- Stipulate that the harvest strategy and harvest rules and tools (quota, effort limits etc) are linked to the RFMO Limit and Target Reference Points; and that actions will be taken by Vietnam if any tuna species reaches the Point of Recruitment Impairment

- Insert ‘Implement bycatch based risk assessment to determine the impacts of fisheries on the ecosystem’ as a separate action point under II ‘Collecting data to serve for management of the oceanic tuna fisheries’.

- Insert Implement technical measures to protect any vulnerable bycatch species, especially Endangered, Threatened and Protected sharks and turtle, under III Implementing the management measures

| Assigned stakeholders | MARD/D-FISH |
| --- | --- |
| Priority | High |
| Status | Developed from existing activity (currently in draft) |
| Timeframe | Q4 2016 |
| MSC Performance Indicator(s) | 3.2.1 Fishery specific objectives |

### Outcome 3.4: Decision making process strengthened

Activity 3.4.1: Clarify decision making structure which is defined with the NTMP

Milestone 46: Introduce clear guidelines for taking management decisions, probably as a component of the management plan;

Milestone 47: Evidence is available that explanations to be provided for decisions taken, and should follow the basis of the management plan when introduced, which may include precautionary actions.

The MSC requires:

- There are established decision-making processes that result in measures and strategies to achieve the fishery-specific objectives.(SG 3.2.2 80 (a))

- That the decision-making processes respond to serious and other important issues identified in relevant research, monitoring, evaluation and consultation, in a transparent, timely and adaptive manner and take account of the wider implications of decisions; (SG 3.2.2 80 (b))

- That the decision-making processes use the precautionary approach and are based on best available information. Information on fishery performance and management action is available on request, and explanations are provided for any actions or lack of action associated with findings and relevant recommendations emerging from research, monitoring evaluation and review activity (SG 3.2.2 80 (c).

- Explanations are provided for any actions or lack of action associated with findings and relevant recommendations emerging from research, monitoring, evaluation and review activity ((SG 3.2.2 80 (d).

The pre-assessment identified a need to improve the inadequacy of the decision making process at across all level of fishery management.  Decisions would have to incorporate binding decisions at EEZ level and compatible measures for territorial waters. The process also requires that stakeholders are informed of decisions with explanations provided and provides information and explanations to stakeholders on request, including when judicial decisions have been implemented. The vehicle to implement the decision makig process would be best placed in the Tuna Management Plan.

| Assigned stakeholders | MARD/D-FISH |
| --- | --- |
| Priority | High |
| Status | Requires implementation into the TMP |
| Timeframe | 2017 |
| MSC Performance Indicator(s) | 3.2.2 Decision making |

### Outcome 3.5: Effective application of compliance systems

Activity 3.5.1: Strengthen the compliance monitoring system

Milestone 48: Risk assessment of enforcement actions following the introduction of P1 and P2 associated management measures

Milestone 49: Review of sanctions for non-compliance

Milestone 50: Effective evidence of systematic compliance and an effective system of sanctions

Enforcement systems in Vietnam are gradually being strengthened following an emphasis on improved enforcement requirements to satisfy the EU IUU regulation. These include a strengthening of the sanction system (Decree No 103). Fishery specific management measures will be applied as part of the target species and ecosystem management strategies, rules and tools. In order to illustrate an effective compliance system, it is important to first establish a process of optimizing control activities through use of risk assessment techniques. The assessors will also need to ensure that the compliance system is effective and that there is no systematic non-compliance.

Evidence of enforcement actions applied in the fishery has been partially provided (i.e. compliance with VMS and evidence of sanctions applied). Once harvest control limits and other management measures have been adopted, the MCS measures in place will need to demonstrate that industry is compliant with the measures. These will need to include compliance with VMS, Catch logbook recording, compliance with output limits set, and compliance with shark finning and the use of circle hooks.

| Assigned stakeholders | Department of Fishery surveillance/DECAFIREP/Sub DECAFIREP |
| --- | --- |
| Priority | High |
| Status | Ongoing |
| Timeframe | Dec 2023 |
| MSC Performance Indicator(s) | 3.2.3 Compliance and enforcement |

- STATE OF READINESS FOR MSC CERTIFICATION.

Based on a review of the scoring, and the review of FIP actions taken, the FIP consultant makes the following observations:

1.2.1 The adoption of Yellowfin and Bigeye harvest strategies - Conditional Pass - (A Condition in all MSC YFT and BET assessments): has been delayed until 2024. Without due reference to MSC Standards Default, all YFT and BET Certified fisheries will be withdrawn.

1.2.2 Harvest Control Rules and Tools - Conditional Pass /Fail (By 2025) - (A Condition in all MSC YFT and BET assessments): Whilst Vietnam has developed a working document that seeks to implement Harvest Control Rules and Tools, the tools have not been developed, and any such tools would have to demonstrate compatibility with Para 47 in WCPFC 2021-01.

1.2.3 Target species Information - Pass but a Recommendation: Because of the low levels of catch logbook reporting,  An assessment would most probably pass the fishery, based on harmonization of overall information available to support WCPFC stock assessments, but set a Recommendation for Vietnam to improve the catch reporting coverage

2.2.2 Shark finning - Fail / Conditional Pass-: Evidence will need to show that shark finning is not taking place, or that any shark fins landed are attached to the carcass

2.2.3 Information of shark specific catch in the handline - Conditional Pass

2.3.2 ETP Management – Conditional Pass/Fail: Demonstrate the effective application of Turtle Mitigation Management Measures

3.2.2 Decision making - Pass with Condition – Demonstrate the application of the Precautionary Approach to Fisheries Management in the Decision Making Syatem

3.2.3 Compliance - Fail –– Demonstrate effective application of compliance systems and systematic compliance by industry

3.2.4 Performance Review - Pass with Condition – Demonstrate the application of occasional external review to all parts of the Management System.

# TERMS OF REFERENCE

## 4.1 DATA COLLECTION FOR TARGET, OTHER RETAINED, BYCATCH, ETP SPECIES

SUB DECAFIREP

#### BACKGROUND

VINATUNA, supported by the WWF Asia Pacific Seafood Trade Network and national government agencies (MARD and DECAFIREP), industry bodies, VASEP, private sector exporters, are engaged in a Fishery Improvement Project (FIP). This project will be carried out to support the long-term goal of Marine Stewardship Council certification of Pacific Ocean yellowfin tuna in the handline and longline fisheries. To this end, all stakeholders have endorsed an Action Plan which, when implemented, will satisfy the MSC standards, but will also embrace activities required to support WCPFC management measures and are expected to underline the outcomes of the Vietnamese Tuna Management Plan. As part of this process, the Government of Vietnam will support a data collection programme which will produce the required data for input into stock assessments conducted by SPC, but will also link to the work of Research Institute for Fisheries Management in providing information to the MARD and D-Fish and other stakeholders on tuna stock status and ecosystem and Environmental Risk Assessments (ERA) within the Vietnamese EEZ and will further support the development of a national tuna management strategy consistent with WCPFC requirements

##### Global objective

The expected position by that by Dec 2025:

- Sufficient relevant information related to stock structure, stock productivity and other data available to support the harvest strategy;

- There is good information on all other fishery removals (secondary species)

- Stock abundance and fishery removals are regularly monitored at a level of accuracy consistent to cover Harvest Control Rules

- Sufficient information is available to allow fishery related mortality and the impact of fishing to be quantitatively estimated for at risk species, especially sharks;

- Information is sufficient to measure trends and support a full strategy to manage impacts on shark species.

- Sufficient data are available to allow the nature of habitat impacts to be identified

- There is evidence that the fishery is highly unlikely to disrupt the key elements underlying ecosystem structure and function to a point where there would be a serious or irreversible harm

##### Specific objectives

The purpose of the TOR is to set out the requirements for D-Fish to implement a data collection system consistent with SPC/WPEA requirements in order to support stock assessments and Environmental Risk Assessment for other retained, ETP species and habitats (ERA) in support of regional and national fishery research management decision making.

##### Requested Services

Sub D-Fish/DARD will implement data collection for a period of 5 years and beyond, contributing to assessment of stock status and guiding the implementation of a number of measures that support a regional and national Harvest Control Strategy (HCS) for yellowfin (YFT) and bigeye tuna, other retained, bait species bycatch in the Vietnam EEZ. A number of specific outputs need to be introduced along with supporting measures, which require deliberation by sub D-Fishs. These are:

- Continue to improve national data collection and monitoring of tunas at all levels and across all fisheries;

- Continue to document the catch of shark, billfish, bait species and other species in the handline and longline fisheries.

- Monitor of turtle bycatch and life status in the handline and longline fisheries

- Support the assess the ecosystem impact for the Vietnam EEZ /South China Sea Sub region by collecting trophic information through port sampling

- Strengthen the system of data collection on tuna to ensure that there is a high confidence that the information is robust for data collected from the full range of national tuna fisheries (handline, longline, purse seine and gill net);

As part of the sub D-Fish’s undertakings, the team of data collectors will:

- Identify information requirements and gaps which will support knowledge of stock structure, stock productivity, stock abundance, fishery removals and other information such as environmental variables;

- Implement a catch logbook data collection system, following WCPFC and MARD requirements

- Strengthen the data collection and port sampling system on stock structure, stock productivity, stock abundance, trophic data and fishery removals, by preparing a standard sampling protocol,

- Develop a comprehensive observer scheme to international standards (equivalent to established Regional Observer Programme (ROP standards) which will include adoption of observer modules, implement a training programme, and initiate an observer monitoring programme (with established debriefing and verification processes).

- Strengthen the system of data collection for other retained, bycatch and bait species and ensure that there is a high confidence that the information is robust for data collected from the handline and longline fisheries;

- Implement a fisheries information system to record, integrate, and analyse the potentially large quantity of data, according to an agreed plan that integrates data collection from across the range of fisheries and allows for access and compatibility with data bases (e.g. TUFMAN) used at regional level.

The available information should be:

- of a standard to quantifiably support the SPC and RIMF stock data and assessment requirements;

- sufficiently accurate to support a comprehensive strategy to manage tuna and to assess whether the strategy is achieving its objective;

- support a comprehensive strategy on managing other secondary species and bait removals;

- data continually collected to detect any increase in risk to tuna, other secondary species and bait species.

The outputs that must be achieved by Dec 2025 are as follows:

- Tuna vessel register operational at Provincial level linked to National recording system

- Logbook coverage > 75% for LL and HL, and improved coverage of other fisheries (by Q4 2018)

- Port sampling implemented in main ports/provinces

- Extend port sampling procedures to cover retained species (and informed by the observer scheme)

- Establish an observer scheme to monitor all catches of retained species and document the level of discarding from the handline and longline fisheries

- Ensure that all shark species are covered under observer reporting

- Monitor of turtle bycatch and life status in the handline and longline fisheries

- Incorporate a requirement to record gear losses into the national observer programme

- Document observer data and port sampling verification, and prepare summary reports of main and vulnerable species (retained) interactions other than bigeye tuna

The expectation is that a tuna data collection system implemented and fully effective:

- Sub D-Fish collectors engaged in all the main fishing ports

- Port sampling data collection system fully operational in all the main tuna ports

- Observer programme fully operational longline and handline (5% or more)

- Catch and effort database operational and supporting interrogation both at national and RFMO level (e.g. TUFMAN II)

- Longer term training needs identified and implemented

- Training a pool of observers and coordinating their deployment, according to the required international standards

The following funding assumptions are made and are to be explored in more depth

- Enumerators, observers and a data base manager based in each sub DECAFIREP office. Funding will be provided directly from the Donor funds, Provincial Peoples Committee Central Government funds and the private sector.

- The observer scheme (observers and debriefers) will be partly private sector funded but will fall under the responsibility of sub DECAFIREP. The number of observers recommended, will conform to international requirements or best practice. Coverage is expected to be 5% for all longline and handline vessels, but may increase if additional funding is available;

#### EXPERTS’ PROFILE
The following experts are expected to be in place. D-FIsh and sub DARD already have assigned managers, statistical officers, enumerators and data collectors in place, and will need to ensure implementation of the appropriate manpower and system support to apply these. The programme will include Binh Dinh, Phu Yen, Khanh Hoa, Quang Nam, Quang Ngai, Da Nang, Ninh Thuan, Binh Thuan, Baria-Vung Tau.

- National Tuna coordinator

- Qualifications and skills

- Masters or Doctorate in biological or social sciences

- A high level of computer literacy with experience in data entry and extraction

- Working experience in dealing with fisheries data

- Familiarity with the WCFPC TUFFMAN data base

- General professional experiences

- Strong communication skills to support problem solving in data collection

- DECAFIREP Technicians

- Qualification and skills

- A degree in fisheries or agricultural science or engineering

- Training in process or completed at international level

- Training of trainers will be provided by SPC under the WPEA Programme

- Data base managers (9, 1 per centre)

- Qualifications and skills

- A high level of computer literacy with experience in data entry and extraction

- Working experience in dealing with fisheries data

- Familiarity with the WCFPC TUFFMAN data base

- General professional experiences

- Strong communication skills to support problem solving in data collection

- Enumerators / data verifiers (3-6 per Province)

- Qualifications and skills

- A bachelors degree in marine science and / or statistics is preferred

- A high level of numeracy with experience in data entry and extraction, preferably from the one of the two externally funded programmes (WPEA or other donor support).

- General professional experiences

- Working knowledge of data collection

- Strong communication skills to support problem solving in data collection

- Observer trainers (4)

- Qualifications and skills

- A degree in marine science and / or statistics is preferred

- Experience in training and lecturing to University Standard

- Senior observer/debriefers (6)

- Qualifications and skills

- A bachelors degree in marine science and / or statistics is preferred

- A high level of computer literacy with experience in data entry and extraction

- General professional experiences

- Field experience in  data collection

- Strong communication skills to support problem solving in data collection

- Observers (At a rate of 5% coverage for 700 longliners and 1,500 handliners)

- Qualifications and skills

- A bachelors degree in marine science and / or statistics is preferred

- A high level of computer literacy with experience in data entry and extraction

- General professional experiences

- Successfully completed a training course in observer duties

- Strong communication skills to support problem solving in data collection

#### DURATION

- DECAFIREP are expected to have completed a revised WPEA incorporating the above within 3 years with an initial programme extending for a 5 year period, up to the date of the MSC Assessment.

- .

#### PLANNING

The assignment comprises a combination of scientific and technical input supported for data collection, sampling.

#### BUDGET

Annual operational costs to be decided in consultation with DECAFIREP.

EXPECTED MILESTONES AND REPORTING

The required outputs are set out in the table below:

| MILESTONES | Timeline | REPORTING MEANS OF VERIFICATION |
| --- | --- | --- |
| Logbook coverage > 75% for LL and HL, and improved coverage of other fisheries | Ongoing | WPEA data reports |
| Port sampling implemented in main ports/provinces | Ongoing | WPEA data reports |
| Tuna vessel register operational at Provincial level linked to National recording system | Ongoing | MARD statistical tables |
| National tuna data collection system implemented and fully effective | Ongoing | MARD statistical tables |
| Establish an observer scheme to monitor all catches of retained species and document the level of discarding from the handline and longline fisheries | Ongoing | Observer deployment and reporting system endorsed by voluntary or statutory agreement |
| Extend port sampling procedures to cover retained species (and informed by the observer scheme) | Ongoing | Port sampling reports |
| Document observer data and port sampling verification, and prepare summary reports of main and vulnerable species (retained) interactions other than bigeye tuna | Ongoing | Statistical data and summary reports |
| Implement shark NPOA and introduce measures to protect at risk shark species | Q 4 2017 | Decree implemented sharks (and billfish) |
| Ensure that all shark species are covered under observer reporting above (Milestone 13 and 15) | Q 1 2017 | Observer reports and estimate of shark catches by species |
| Monitor of turtle bycatch and life status in the handline and longline fisheries | Ongoing | Observer reports and estimate of turtles catches |
| Incorporate a requirement to record gear losses into the national observer programme | Implemented | Observer reports on gear loss in longlines |
| Collection of biological samples to adequately assess Pacific ecosystems | Ongoing | WPEA output |

## 4.2 STOCK ASSESSMENT AND ECOSYSTEM MODELING

VINATUNA, supported by the WWF Asia Pacific Seafood Trade Network and national government agencies (MARD and DECAFIREP), industry bodies, VASEP, private sector exporters, are engaged a Fishery Improvement Project (FIP). This project will be carried out over a period of 5 years, to support the long term goal of Marine Stewardship Council certification of Pacific Ocean yellowfin tuna in the handline and longline fisheries. To this end, all stakeholders have endorsed a an Action Plan which, when implemented, will satisfy the MSC standards, but will also embrace activities required to support WCPFC  management measures and are expected to underline the outcomes of the Vietnamese Tuna Management Plan. As part of this process, the Government of Vietnam will provide input into the WCPFC Scientific Committee (SC), as well as undertaking its own research through RIMF to assess the biomass within the Vietnamese EEZ.  RIMF will be responsible for interpretation of the national stock assessment results, and MARD responsible for directing activities relating to the adoption of reference points.

#### DESCRIPTION OF the ASSIGNMENT

##### Global objective

The expected position by Dec 2025 is that:

- It is highly likely that the stock is above the point where recruitment would be impaired;

- The stock is at or fluctuating around its target reference point;

- The assessment is appropriate for the stock and for the harvest control rule;

- The assessment takes uncertainty into account;

- Trophic interactions are fully understood

##### Specific objectives

The purpose of the TOR is to set out the requirements for RIMF to provide scientific support to stock assessment support, working with the scientists of the Oceanic Fisheries Programme, SPC. The work of RIMF will be to provide scientific advice to MARD for the establishment of catch limits or equivalent catch limits against the Target and Limit Reference Points set by WCPFC.

##### Requested Services

RIMF will provide services supported by DECAFIREP data (3.1) contributing to assessment of stock status and guiding the implementation of a number of measures that support a regional and national Harvest Control Strategy (HCS) for skipjack (SKJ), yellowfin (YFT) and bigeye (BET) tuna in the Pacific Ocean including the EEZ and territorial waters of Vietnam. A number of specific outputs need to be introduced along with supporting measures, which will require deliberation by the Tuna Fisheries Management Council in order to set harvest strategies. These are:

- Contributing to the discussion on Limit Reference Points (LRPs) for yellowfin and bigeye, at the relevant WCPFC SC and General Sessions. The LRP would have to be set at a point above the level at which there is an appreciable risk of impairing reproductive capacity; The TRP set such that the stock is maintained at a level consistent with BMSY or some measure or surrogate with similar intent or outcome;

As part of the institution’s undertakings, the team of scientists and technicians will:

- Prepare a Research Plan for the tuna and other retained species caught by all fisheries (Which will also includes ecosystem research (section 3.3));

- Identify information requirements and gaps which will support knowledge of stock structure, stock productivity, stock abundance, fishery removals and other information such as environmental variables and ensure that these are incorporated into WPEA support activities;

- Undertake training in stock assessment, ecosystem modelling (MULTIFAN-CL, ECOSIM. ECOPATH, SEAPODYM) and risk assessment to promote a higher level of input from Vietnamese scientists into WCPFC Scientific Committee deliberations;

- Support increasing awareness of research needs, outcomes and application at provincial and national level to all stakeholders;

- Provide technical advice to the TMC and MARD, which will lead to the establishing of a robust and precautionary harvest strategy for Vietnamese fisheries, and will support the extension of WCPFC Commission Management Measures to Vietnamese waters.

The outputs that must be achieved are as follows:

- 5 year RIMF Tuna Research Plan containing the above services (and following international best practice and MSC requirements) established by year 1

- Improving scientists’ knowledge in stock assessment techniques completed by OFP, SPC, within 3 years

- Target and limit reference available for Western Central Pacific by the end of year 3.

- An annual review of the research programme, and by year 4 have completed an external review.

- Attending technical committee meetings at WCPFC (dealing with stock assessment and the LRP/ TRP context, and on stock rebuilding)

The following funding assumptions are made and are to be explored in more depth

- A senior scientist and technician are to be employed by RIMF, funded by MARD.

#### EXPERTS’ PROFILE
The following experts are expected to be in place. RIMF already haa an assigned scientist and will need to ensure implementation of the appropriate manpower and system support to apply these)

Senior scientist

- Qualifications and skills

- A post graduate qualification in stock assessment

- Training in process or completed at a regional or international centre of excellence

- Knowledge of tropical tuna fisheries

- General professional experiences

- Proven track record in stock assessment from a Vietnamese Research Centre
and at least 5 years of professional experience in the provision of advice to fishery managers

- Experience in the application of stock assessment techniques, data requirements and models

- Technicians

- Qualification and skills

- A degree in fisheries or agricultural science or engineering

- Training in process or completed at international level

- Stock assessment training will be provided by SPC under the WPEA Programme

#### DURATION

- RIMF is expected to have completed a revised Research Programme incorporating the above within 1 year, with an initial programme extending for a 5 year period, up to the date of the MSC Assessment.

- .

#### PLANNING

The assignment comprises a combination of scientific and technical input supported by the WPEA data collection (3.1).

#### BUDGET

Annual operational costs to be determined by MARD.

The required outputs are set out in the table below:

EXPECTED MILESTONES AND REPORTING

The required outputs are set out in the table below:

| MILESTONES | Timeline | REPORTING MEANS OF VERIFICATION |
| --- | --- | --- |
| MARD/RIMF participating in SC WGs and WCPFC general session discussions on reference points | Ongoing | WCPFC SC (11th Regular Session) (http://www..int/meetings) |
| Setting of LRPs and TRPs for YFT and BET at national level that are compatible with WCPFC requirements. | Ongoing | Scientific papers on RPs and General Session report |
| MARD/RIMF participating in SC WGs for the revision of the core WCPFC CMM on bigeye and yellowfin strategy | Ongoing | WCPFC attendance records |
| Advice provided on catch and / or effort limits set for bigeye and yellowfin tuna for Vietnam consistent with WCPFC methodology (either 2001-2004 levels or an alternative) and based on an historic ref | Priority Action | Technical paper submitted to a National Workshop with proposed LRPs and TRPs to be set for yellowfin and bigeye tuna |
| Training in ecosystem modeling | To be implemented | WPEA Reports |
| Ecosystem analysis and reporting to support adoption of EAFM | To be implemented | SPC training |
| A research plan prepared publically available | Ongoing | Research results are disseminated to all interested parties |
| Research results are disseminated to all interested parties | Ongoing |  |

## BYCATCH & ECOSYSTEM IMPACT ANALYSIS

### RESEARCH INSTITUTION: To be nominated (RIMF)

#### BACKGROUND

VINATUNA, supported by the WWF Asia Pacific Seafood Trade Network and national government agencies (MARD and DECAFIREP), industry bodies, VASEP, private sector exporters, are engaged a Fishery Improvement Project (FIP). This project will be carried out over a period of 5 years, to support the long term goal of Marine Stewardship Council certification of Pacific Ocean yellowfin tuna in the handline and longline fisheries. To this end, all stakeholders have endorsed a an Action Plan which, when implemented, will satisfy the MSC standards, but will also embrace activities required to support WCPFC  management measures and are expected to underline the outcomes of the Vietnamese Tuna Management Plan. As part of this process, RIMF, supported by DECAFISH and the WPEA data collection programme, will set up a Retained Species Assessment Programme (RSAP), which will be responsible for determining risks, and developing management mitigation proposals, that will support the TMC in proposing a management strategy that will meet the MSC standard by year 5.

#### DESCRIPTION OF the ASSIGNMENT

##### Global objective

The expected position by Dec 2025 (i.e. entering into Full Assessment is that):

- The fishery does not pose a risk of serious or irreversible harm to the bait species, retained and ETP species, bycatch or habitats and does not hinder recovery for managing  species associated with the tuna ecosystem ensuring that the fishery does not pose a risk of serious or irreversible harm to retained species;

- There is a strategy in place for managing retained, bait species, bycatch, ETP species or habitats interactions in order to avoid the risk of serious irreversible harm from the fishery;

- Information on the nature and extent of retained species is adequate to determine the risk posed by the fishery and the effectiveness of management mitigation strategy.

##### Specific objectives

The purpose of the TOR is to set out the requirements for NIO to provide support services for fishery specific support activities at national and provincial level. These services, all of which will relate to:

- Analysing information collected by DECAFIREP on primary and secondary species, bait species, ETPs and on bycatch and ecosystem interactions;

- Exploring management mitigation strategies with stakeholders, including fisher associations, private sector companies and fisher communities;

- Promoting the concept of stakeholder led management actions; and awareness training;

- Advising Government of any required measures that are required in addition to CMM implementation requirements.

##### Requested Services

Working with fishing companies NIO will provide services to the TFMC. The following outputs must conform to the following principles:

- Ensuring that accurate and verifiable information is available on catches of all retained, bycatch (including bait fish) and ETP species;

- That the information available is sufficient to estimate the risks with respect to productivity and susceptibility limits, including mortalities and injuries to all bycatch species;

- That the distribution of habitat types is known over the range, with particular attention to the occurrence of vulnerable habitat types;

- That changes in habitat distribution over time are recorded;

The tasks to be implemented will include:

- Review bycatch mitigation measures appropriate for each fishery which might include:

  - Longline – use of circle hooks, TORI lines and lures, no catch retention of sharks, seasonal or area closures.

  - Hand-line – FAD management (if required)

- Undertake training in the Risk Based Framework to allow scientists to assess, with stakeholders, the risks posed to ALL retained, bycatch (billfish, sharks, other commercial and bycatch species), bait species and ETP species identified in the national regulations. This will form part of the training process outlined in Section 3.1.

- Undertake, fishery by fishery, bycatch mitigation stakeholder workshop, working from international best practice examples

- Prepare recommendations to the TFMC for a retained species management plan, if required;

- Prepare recommendations to the TFMC for a bait species management plan, if required

- Raise awareness on bycatch avoidance and ecosystem interactions, and developing a system that measures the effectiveness of the strategy.

- Support awareness of research needs, outcomes and application at provincial and national level to all stakeholders;

- Make an annual assessment to detect whether there are changes to risk levels for associated bycatch species

RIMF

Senior Researcher

- Qualifications and skills

- A post graduate degree in fisheries science or marine studies

- Experience in environmental risk assessment

- At least 10 years research experience

- Strong communication skills

- General professional experiences

- Knowledge of Vietnamese fisheries

- Demonstrated skills in report dissemination and report writing

- Clear knowledge of suitable bycatch mitigation strategies

- A working knowledge of English

- Junior researcher

- 1, Qualifications and skills

- A graduate qualification in marine sciences

- General professional experiences

- Strong communication skills to facilitate problem solving in data collection

- A working knowledge of English

#### DURATION

- The assignment will be for 5 years with a view to establishing long term linkages thereafter based on performance.

#### PLANNING

The assignment comprises a combination of scientific and technical input supported by a data collection, sampling and marine survey programmes.

#### BUDGET

Annual operational costs to be decided in consultation with VINATUNA and MARD. Broad budget outlines are provided in the supporting excel sheet (Tab Budget FIP tracking June workshop.xls)

#### EXPECTED MILESTONES AND REPORTING

The required outputs are set out in the table below:

| MILESTONES | Timeline | REPORTING Means of Verification |
| --- | --- | --- |
| Training in risk assessment and the application of EAFM | Completed | wwF Training certificates |
| Workshop to determine risks applying the risk based framework (SICA and PSA) | Completed | Risk assessment workshop report |
| Workshop to analyse risk mitigation strategies for sharks | 2017 | Management mitigation workshop report |
| Implement retained species mitigation measures for sharks | 2017 | Decrees |
| Evaluate the effectiveness of management mitigation measures for vulnerable retained and bait species | 2018 | Performance Review of measures undertaken |

## 4.4 DEVELOPMENT OF HARVEST STRATEGIES RULES AND TOOLS AND BYCATCH MITIGATION MEASURES

VINATUNA, supported by the WWF Asia Pacific Seafood Trade Network and national government agencies (MARD and DECAFIREP), industry bodies, VASEP, private sector exporters, are engaged a Fishery Improvement Project (FIP). This project will be carried out over a period of 5 years, to support the long term goal of Marine Stewardship Council certification of Pacific Ocean yellowfin tuna in the handline and longline fisheries. To this end, all stakeholders have endorsed a an Action Plan which, when implemented, will satisfy the MSC standards, but will also embrace activities required to support WCPFC  management measures and are expected to underline the outcomes of the Vietnamese Tuna Management Plan. As part of this process, the Government of Vietnam will provide input into the WCPFC General Sessions, but will also be responsible for ensuring that national and international (WCFC) measures are implemented into a national harvest strategy, with associated harvest rules and tools implemented.

#### DESCRIPTION OF THE ASSIGNMENT

##### Global objective

The expected position by Dec 2025 is that:

- There is a robust and precautionary harvest strategy in place in Vietnam which is responsive to the state of the stock, reflects the requirements of WCPFC Conventions and is designed to achieve stock management objectives set as target and limit reference points;

- There are well defined and effective harvest control rules in place that are consistent with International harvest strategies and ensure that the exploitation rate is reduced as the limit reference points are approached, and provide a management mechanism to allow recovery of depleted stocks;

- There is a strategy in place for managing secondary and bait species or habitatsinteractions in order to avoid the risk of serious irreversible harm from the fishery;

##### Specific objectives

The purpose of the TOR is to set out the requirements for MARD and D-Fish in relation to implementing a harvest strategy, in cooperation with the Tuna Management Council.

##### Requested Services

MARD and D-Fish will appoint two persons, a fisheries management specialist, and they will undertake the following tasks in response to international requirements to implement a harvest strategy at national level. The implemented actions will be provided by D-Fish and sub D-Fish/DARD.

Implementation and development of Proposed Strategy:

- Fisheries management strategy

- Formulate a stock assessment, for yelowfin and bigeye respectively

- Assign LRPs at 0.2 B0 MSY and a preliminary TRP of 0.4 MSY

- Develop fishery specific harvest controls for handline and longline, and apply at Provincial level

- Introduce the Decree/Circular implementing these controls

- Submit evidence that these measures have been applied to WCPFC

- Ecosystems and bycatch strategy

- Undertake a workhop to explore management mitigation actions for sharks (Box 1)

- Introduce the Decree/Circular banning finning at sea

- Implement effective management mitigation measures for sharks and turtles which are consistent with ecosystem risk assessment

- Performance evaluation

- Undertake a review of all management actions – harvest control tools and ecosystem management actions

Review of and adoption of proposed management tools:

- Coordinate a workshop comprising managers and stakeholders, to identify an acceptable system of management controls and to identify the appropriate rules to be applied to each fishery

- Determine the responsibility framework established within which harvest control rules would be set and delegating appropriate responsibilities to the Provinces

Among the best practice measures to be explored would include:

- Establishing a Vessel Day System (VDS) for longline vessels; or

- Evaluate the prospects for a species specific quota system to be applied across the various fleets operational in Vietnamese waters

These measures will require monitoring by D-Fish, and monitoring of the performance of sub D-Fish in implementing these rules and tools.

- National Fisheries Management Expert

- Qualifications and skills

- Post-doctoral degree in fisheries sciences, economics or community and social studies

- At least 10 years-experience in fisheries management planning and implementation within Vietnam, with a preference for experience gained in input and output controls.

- General professional experiences

- Knowledge of Vietnamese fisheries

- Working knowledge of English

Ecosystems and bycatch Management Expert

- Qualifications and skills

- Post-doctoral degree in fisheries sciences, economics or community and social studies

- At least 10 years-experience in fisheries management planning and implementation within Vietnam, with a preference for experience gained in input and output controls.

- General professional experiences

- Knowledge of Vietnamese fisheries

- Working knowledge of English

#### EXPECTED MILESTONES AND REPORTING

The required outputs are set out in the table below:

| MILESTONES | Timeline | REPORTING MEANS OF VERIFICATION |
| --- | --- | --- |
| Vietnam's compliant with CMM 2016-01, or any subsequent amendment | 2017 | FAD Management Plan and Regulations confirming limits set for YFT and BET |
| Workshop on exploring options for input (effort) and output (quotas) for longline and handline fisheries based on TRPs and LRPs and CMM 2012-01 (years 2001-2004 levels) | 2017 | Workshop report and recommendations |
| Responsibility framework established within which harvest control rules would be set and delegating appropriate responsibilities to the Provinces | 2017 | Organogram showing delegated responsibilities and reporting functions |
| Vietnamese management measures introduced for all tuna fisheries in Vietnam | 2017 | Regulations and Decrees |
| Undertake and assess evidence that the measures established are effective | 2018 | Performance review report (as per management plan requirement) |
| Implement shark mitigation measures | 2017 | Decree endorses CMM on sharks (and billfish) |
| Implement a decree banning shark finning at sea | 2017 | Decree |
| Ensure that all shark species are covered under observer reporting (3.1) | Ongoing | Observer reports and estimate of shark catches by species |
| Implement effective management mitigation measures for turtles which are consistent with national and international (WCPFC) obligations | Ongoing | Report demonstrating that requirements for protection and rebuilding are in place - non retention and dehooking; and evidence that the fishery is unlikely to hinder recovery. |
| Where risks are identified, instigate trials to reduce the interactions | Ongoing | Report on risks and sea trials |
| Fisher awareness | To be implemented | Workshop attendance records |
| Evaluate the effectiveness of management measures for shark species identified in the Risk Assessments | 2018 | Evaluation report of the effectiveness to the CMM, also included within Par 2 report to TCC |
| Timeline priority |  |  |

#### DURATION

- The assignment will be for 6 years ending at the end of 2018.

#### PLANNING

The work output comprises specialist management inputs from two assigned specialists under MARD, but linking to DECAFOREP and sub DECAFIREP.

#### BUDGET

Annual operational costs to be decided in consultation with VINATUNA and MARD. Proposed budget outlines are provided in the supporting excel sheet (Tab Budget FIP tracking June workshop.xls)

## 4.5.1 INSTITUTIONAL STRENGTHENING: GOVERNANCE, CONSULTATION AND DECISION MAKING

### The Ministry of Agriculture and Resource Development, Department of Capture Fisheries & Resource Exploitation and Protection and the Tuna Fisheries Management Council

#### BACKGROUND

VINATUNA, supported by the WWF Asia Pacific Seafood Trade Network and national government agencies (MARD and DECAFIREP), industry bodies, VASEP, private sector exporters, are engaged a Fishery Improvement Project (FIP). This project will be carried out over a period of 5 years, to support the long term goal of Marine Stewardship Council certification of Pacific Ocean yellowfin tuna in the handline and longline fisheries. To this end, all stakeholders have endorsed a an Action Plan which, when implemented, will satisfy the MSC standards, but will also embrace activities required to support WCPFC  management measures and are expected to underline the outcomes of the Vietnamese Tuna Management Plan. As part of this process, the FIP proposes to strengthen Vietnamese tuna fisheries management processes in accordance with international obligations and will identify institutional strengthening actions which are consistent with MSC principles 1 and 2.  This includes a clear understanding of roles and responsibilities by the policy (MARD), management organisations (DECAFIREP) and supporting Tuna Fisheries Management Council.

#### DESCRIPTION OF THE ASSIGNMENT

##### Global objective

The expected position by Dec 2025 is that:

- The management system includes consultation processes that regularly seek and accept relevant information, including local knowledge. The management system demonstrates consideration of information and explains how it is used or not used;

- The legal system in place is effective and consistent with local, national or international laws or standards that are aimed at achieving sustainable fisheries in accordance with MSC Principles 1 and 2

- The consultation process provides opportunity and encouragement for all interested affected parties to be involved, and facilitates their effective engagement;

- Clear long and short term objectives are in place that guide decision making are in place, and are explicit within a Fishery Specific Management Plan;

- The national decision making processes responds to all issues identified in relevant research, monitoring, evaluation and consultation, in a transparent , timely and adaptive manner and take account of the wider implications of decisions;

- The national Decision-making processes uses the precautionary approach and are based on best available information. Information on fishery performance and management action is available on request, and explanations are provided for any actions or lack of action associated with findings and relevant recommendations emerging from research, monitoring evaluation and review activity;

- Explanations are provided for any actions taken and recommendations emerging from research, monitoring and evaluation and review activity;

- The management agencies (MARD and DECAFIREP) have in place mechanisms to evaluate all parts of the management system and is subject to internal and external review processes.

### MARD

##### Specific objectives

The purpose of the TOR is to set out the requirements for MARD which undertakes responsibility for core governance issues – the implementation of law, creating an appropriate consultative process, the decision making processes, ensuring adherence to long term objectives and compliance with the WCPFC Convention.

##### Requested Services

As part of the requirement to strengthen governance functions there are some core activities that MARD needs to address, more specifically as an requirement as a Cooperating Commission Member (CCM) or WCPFC. If endorsed these core requirements will also be consistent with the outcomes required of the MSC, which recognizes the achievements made in good governance by countries.

Specific supporting activities have been identified as follows:

- Clarification of Vietnam's status within the convention, and extension of the convention area to the Vietnam

- Implementation of the new Fisheries Law containing the core elements which prioritise sustainable fisheries, and contain  provisions for automatic implementation of international conventions including the WCPFC CMMs

- Implementation of the Advisory Board through the NTMP process

- Revise the a tuna fisheries strategy so that long term and short term objectives demonstrate effective implementation of sustainable fisheries management systems

- Implementation of a compatible harvest strategy in Vietnam waters (and compliance with CMMs), which would include longline, purse seine and other gears (including handline and gillnet), and would be consistent with Vietnam’s obligations developed through any future changes to 2012-01

- Establishing national harvest control rules (input and output restrictions) across the range of tuna fisheries which allow for limits to be implemented as reference points are approached. The rules and tools will need to take account of best practice examples to illustrate their appropriateness (e.g. overall capacity limits, quotas and closed seasons)

- Setting a monitoring system in place (consistent with CMM 2010-03) which evaluates the effectiveness of the management measures

- Review negative and positive incentives against the background of stock status for yellowfin and bigeye, as well as the impact on bycatch

- Finalize draft NTMP and add inclusion of the handline fishery to the NTMP

- Clarify decision making structure which is defined with the NTMP

#### EXPECTED MILESTONES AND REPORTING

The required outputs are set out in the table below:

| MILESTONES | Timeline | REPORTING MEANS OF VERIFICATION |
| --- | --- | --- |
| MARD/RIMF participating in SC WGs and WCPFC general session discussions on reference points | Ongoing | WCPFC Report of the Annual Regular Session (9/10th Regular Session) (http://www..int/meetings) |
| Vietnam becomes a WCPFC CM (Contracting Member) | 2018 | VNM as an acknowledged CCM as per the General Assembly |
| National legal system, effective and organised and effective cooperation with other parties, where necessary, to deliver management outcomes consistent with MSC Principles 1 and 2 | 2017 | Fisheries Law |
| Tuna Fishery Management Council fully operational and all roles & responsibilities defined | Ongoing | TFMC roles and responsibilities enshrined in Law |
| Evidence would need to show that the Precautionary Approach to Fishery Management (PAFM) is explicitly understood and enacted at both national and provincial level | 2017 | National strategy document |
| Management Plan finalised, complies with MSC principles and contains a consultation process and includes a monitoring & performance component | 2017 | NTMP |
| Management Plan: External Review | 2017 | Independent expert |
| Evidence that the management plan is being applied and its effectiveness is assessed by a process of regular internal and external reviews | 2017 | Review of management plan OVIs |
| Introduce clear guidelines for taking management decisions, probably as a component of the management plan | 2017 | Minutes of decisions taken, including use of available information |
| Evidence is available that explanations to be provided for decisions taken, and should follow the basis of the management plan when introduced, which may include precautionary actions | 2017 | Minutes of decisions taken, including use of available information |

#### DURATION

- The assignment will be for 5 years ending at the end of 2017.

#### PLANNING

The work output comprises strengthening of law and compliance with management decision making consistent with WCPFC requirements, but also following principles advanced by the Marine Stewardship Council.

Annual operational costs to be decided in consultation with VINATUNA and MARD. Proposed budget outlines are provided in the supporting excel sheet (Tab Budget/FIP tracking June workshop.xls)

### D-Fish

##### Specific objectives (D_FISH)

The purpose of the TOR is to set out the requirements for D-FISH which undertakes responsibility for fishery management issues – the implementation of the Tuna Management Plan, following guidance in policy from MARD and the TFMC, Compliance and monitoring performance of these core functions.

- Participate in decision making process in establishing rules and tools

- Implement national harvest control rules (input and output restrictions) across the range of tuna fisheries

- Implement shark CMMs 2010-07 and CMM 2011-03/CITES App 2

- Implement effective management mitigation measures for turtles which are consistent with national and international (WCPFC) obligations.

#### EXPECTED MILESTONES AND REPORTING

The required outputs are set out in the table below:

| MILESTONES | Timeline | REPORTING MEANS OF VERIFICATION |
| --- | --- | --- |
| Introduction Vietnamese management measures for all tuna fisheries in Vietnam (with sub D_FISH) | 2018 | Regulations and Decrees |
| Undertake and assess evidence that the measures established are effective (with sub DECAFIREP, MARD and VINATUNA) | 2018 | Performance review report (as per management plan requirement) |
| Implement secondary species mitigation measures (other than those covered already by CMMs) where necessary (with sub DECAFIREP) | 2017 | Decrees |
| Evaluate the effectiveness of management mitigation measures for sharks | 2017 | Performance Review of measures undertaken |
| Implement a decree banning shark finning at sea | 2017 | Decree |
| Ensure that all shark species are covered under observer reporting above | 2016 | Observer reports and estimate of shark catches by species |
| Ongoing monitoring of turtle bycatch and life status in the handline and longline fisheries (Milestone 13 and 15) | Ongoing | Observer reports and estimate of turtles catches |
| Implement effective management mitigation measures for turtles which are consistent with national and international (WCPFC) obligations | Ongoing | Report demonstrating that requirements for protection and rebuilding are in place - non retention and dehooking; and evidence that the fishery is unlikely to hinder recovery. |
| Fisher awareness programme for shark and turtle interactions | Ongoing | Curriculum and fisher attendance records |
| Evaluate the effectiveness of management mitigation measures for sharks and turtles based on best practice | 2018 | Updated evaluation report on the measures applied and evidence that interactions are declining. |

#### DURATION

- The assignment will be for 6 years ending at the end of 2018.

#### PLANNING

The work output comprises specialist management inputs from two assigned specialists under MARD, but linking to DECAFOREP and sub DECAFIREP.

#### BUDGET

Annual operational costs to be decided in consultation with VINATUNA and MARD. Broad budget outlines are provided in the supporting excel sheet (Tab Budget/FIP tracking June workshop.xls)

### TUNA FISHERIES MANAGEMENT COUNCIL

##### Requested Services

As part of the requirement to strengthen consultation and decision making process, MARD are requested to create a Tuna Fishery Management Council, under the management and supervision of VINATUNA.

##### Specific objectives (TFMC)

The purpose of the TOR is to set out the requirements for the Tuna Fishery Management Council and lay out the basis for the Council’s formation and decision making processes in respect to the management of tuna fisheries.

##### Requested Services

The functioning of TFMC will be strengthened, and its role supported by national law.

MARD/DECAFIREP must seek to use the TFMC structure as a support tool for consultation and decision making processes, and to undertake specific support processes which strengthen national and provincial tuna fisheries management.

MARD should ensure that the membership of the TFMC is inclusive and provides for participation of an appropriate number of organisations engaged in, or with experience in fishery in relation to which the fishery managers are overseeing.’’ These should allow for input or membership from/of the national research organisations (RIMF and NIO), Provincial Government representatives, a MCS manager, VASEP, VINAFIS, and WWF. The TFMC and VINATUNA will play a central role in helping MARD meet its objectives by acting as key liaison bodies between MARD and those with an interest in a particular fishery. They will also provide direct advice to MARD on fisheries-management policies and compliance with the activities set out in the Tuna Management Plan, and assist in the development of cost-efficient management arrangements.

The role of the TFMC should be defined in National Law and its decisions promulgated into management regulations.  The TFMC’s duties include:

- Support the preparation of the Management Plan including setting of management indicators (catch and effort, stock status, and economic indicators);

- Propose a management strategy and harvest rules and tools  that ensure that the Plan can be implemented effectively;

- Promote the co-management of fisheries for artisanal tuna fisheries;

- Promote research, education, and training in relation to fisheries and the management of fisheries, to all stakeholder in district, province and national;

- Report on the outcomes of the plan, most specifically on how the management system responds to findings and relevant recommendations emerging from research.

- Monitoring and evaluation of the effectiveness of the management system;

- Determine the fee structure to pay for a research and development fund, the operating expenses for the Council, and an independent peer review;

- Evaluate the performance of the TMFC structure in line with the roles and responsibilities determined by MARD.

The core requirements of the TFMC would be:

- To ensure a coherent decision making process that results in measures and strategies to achieve fishery specific objectives, as laid down in the Tuna Fishery Management Plan (TFMP);

- That the decisions taken respond to all issues identified in relevant research, monitoring and evaluation and consultation in a transparent and timely manner, and take account of the wider implications of decisions;

- That the decision making process use the Precautionary Approach to Fisheries Management (PAFM) and the Ecosystem Approach to Fisheries Management (EAFM), based on best available information;

- That formal reporting systems are implemented to ensure stakeholder awareness of the decisions taken;

- Consultation processes that regularly seek to accept relevant information and encourages all interested and affected parties to participate.

##### VINATUNA support actions

VINATUNA organisational roles and responsibilities must include the following:

- Coordinating with MARD, DECAFIREP, VASEP, VINAFIS, WWF and the supporting researchers and fishery managers on inputs from supporting organisations, as required;

- Providing advice on statutory decisions (management measures) following the deliberation of the Council;

- Monitoring the implementation of the Harvest strategy, rules and tools including by Provincial and District levels;

- Organising training and awareness programmes for DECAFIREP fishery managers and fishers;

- Organising stakeholder workshops to optimise the receipt of relevant information, to promote the harvest strategy and explain the decisions taken by the MARD and supported by the TMFC.

The required outputs:

- Precautionary Approach to Fisheries Management and Ecosystem Approach to Fisheries Management incorporated into National and Provincial Law, and prescribed as a component of the TFMP

- Draft Tuna Management Plan endorsed, but updated annually;

#### BUDGET

Annual operational costs to be decided in consultation with MARD. Proposed budget outlines are provided in the supporting excel sheet (Tab Budget/FIP tracking June workshop.xls)

#### EXPECTED MILESTONES AND REPORTING

The required outputs are set out in the table below:

| MILESTONES | Timeline | REPORTING MEANS OF VERIFICATION |
| --- | --- | --- |
| Tuna Fishery Management Council fully operational and all roles & responsibilities defined | Ongoing | Decision making and consultation trees and Statutes of the Advisory Board and meeting minutes |

## 4.6 COMPLIANCE

### JOINT TUNA COMPLIANCE WORKING GROUP

#### BACKGROUND

VINATUNA, supported by the WWF Asia Pacific Seafood Trade Network and national government agencies (MARD and DECAFIREP), industry bodies, VASEP, private sector exporters, are engaged a Fishery Improvement Project (FIP). This project will be carried out over a period of 5 years, to support the long term goal of Marine Stewardship Council certification of Pacific Ocean yellowfin tuna in the handline and longline fisheries. To this end, all stakeholders have endorsed a an Action Plan which, when implemented, will satisfy the MSC standards, but will also embrace activities required to support WCPFC  management measures and are expected to underline the outcomes of the Vietnamese Tuna Management Plan. As part of this process, the FIP proposes to strengthen the fishery compliance system in order to ensure effective enforcement of the fishery management measures.  This includes an effective system of compliance resources deployed and sanctions, all of which when introduced will ensure systematic compliance by fishers.

#### DESCRIPTION OF THE ASSIGNMENT

##### Global objective

The expected position by Dec 2025 is that:

- A comprehensive monitoring, control and surveillance system has been implemented tin the fishery and has demonstrated a consistent ability to enforce the management measures set by DECAFIREP;

- Sanctions to deal with non-compliance exist, are consistently applied and demonstrably provide an effective deterrent;

- Evidence exists that fishers comply with the management system, including providing information of importance to the effective management of the fishery;

- There is no evidence of systematic non-compliance.

##### Specific objectives

The purpose of the TOR is to set out the requirements for the Joint Tuna Compliance Working Group and lay out the support requirements and activities required to implement an effective compliance and enforcement system.

##### Requested Services

The Joint Tuna Compliance Working Group (JTCWG) will be the implementing body to enforce the management measures set by DECAFIREP. An elected officer form the JTCWG will be a member of the TFMC.

The JTCWG’s duties include:

- Following decisions made by the DECAFIREP, and resulting Legal decisions put in place, the JTCWG should prepare, with the support of an international compliance consultant, a risk assessment, to determine appropriate deployment strategies. This will form part of the National Plan of Action against IUU;

- The systems of sanctions should be applied appropriate to the levels of risk identified;

- Organisations and individuals involved in the compliance process should be well understood with a clear hierarchy of decision making and active coordination functioning between the various groups – Department of Fishery surveillance, the Navy and Border Police;

- Evidence should be in place of deployment actions taken (collection centre checks, boardings at sea), and results (penalties and confiscations). A time series of these activities and results should illustrate a demonstrably effective deterrent;

- Awareness workshops should be promoted in cooperation with all stakeholder groups to explain the reasons for the measures and drawing on information received from fishers to support the effective implementation of the enforcement system.

- A continual internal review process of effectiveness of the Compliance system, through upgrading of the annual risk assessment exercise

- An external review process on the effectiveness of the compliance system

#### WORKING GROUP MEMBER’S PROFILE

The working group should comprise all those organisations actively engaged in enforcement activities, notably Department of Fishery Surveillance, the Navy and Border Police.

The outputs that must be achieved as follows:

- Evidence that awareness groups are taking place and that these act as a supporting deterrent as well as a source of valuable information to the enforcement organisations by year 2

- Evidence that a risk assessment system is being applied by year 3 and ongoing

- Evidence that inspections are taking place and compliance is increasing by year 3

- Evidence that sanctions are acting as an effective deterrent by year 3

#### DURATION

- Following the adoption of management measures by the TFMC

#### PLANNING

- To be decided by DECAFIREP.

#### BUDGET

Annual operational costs to be decided in consultation with MARD/DECAFIREP. Proposed budget outlines are provided in the supporting excel sheet (Tab Budget/FIP tracking June workshop.xls)

#### EXPECTED MILESTONES AND REPORTING

The required outputs are set out in the table below:

| MILESTONES | Timeline | REPORTING MEANS OF VERIFICATION |
| --- | --- | --- |
| Risk assessment of enforcement actions following the introduction of P1 and P2 associated management measures | 2017 | Risk assessment Report |
| Review of sanctions for non compliance | In progress | Sanction schedule |
| Effective evidence of systematic compliance and an effective system of sanctions | 2017 | Review of infringements |

## 4.7 PROJECT MANAGEMENT

#### BACKGROUND

VINATUNA, supported by the WWF Asia Pacific Seafood Trade Network and national government agencies (MARD and DECAFIREP), industry bodies, VASEP, private sector exporters, are engaged a Fishery Improvement Project (FIP). This project will be carried out over a period of 5 years, to support the long term goal of Marine Stewardship Council certification of Pacific Ocean yellowfin tuna in the handline and longline fisheries. To this end, all stakeholders have endorsed a an Action Plan which, when implemented, will satisfy the MSC standards, but will also embrace activities required to support WCPFC  management measures and are expected to underline the outcomes of the Vietnamese Tuna Management Plan. As part of this process, WWF will manage this project on behalf of the Asia Pacific Seafood Trade Network secure placement for a Regional Coordinator to supervise the implementation of the project and a National Project Manager, to monitor and support the application of the FIP. The Project will also require the support of an international consultant with specific strengths in Monitoring and Evaluation, facilitation of management processes as well as knowledge of MSC Fisheries Assessment Methodology.

### WWF REGIONAL COORDINATOR

#### DESCRIPTION OF THE ASSIGNMENT

##### Global objective

The expected position by Dec 2025 is that:

- The fishery is suitable for advancement to MSC Full assessment and has met with all the Assessment criteria that link to the outcomes and activities described in the FIP.

##### Specific objectives

The purpose of the TOR is to set out the requirements for the WWF Regional Coordinator who will be responsible for overall Project coordination, as well as liaising with stakeholders and funders (Industry Government and Donors).

##### Requested Services

The Coordinator will be responsible for the overall management of the Project and will act as the contact point for funding contributions, as well as liaison with the importers. The Project Coordinator will work with the National country manager and provide support as and when required.

The following duties are required:

- Coordinate the implementation of the FIP in partnership with the National Manager

- Access funding channels

- Develop, implement and track FIP Partner Agreements with private sector, including developing and monitoring communication protocols and managing of market recognition

- Managing the budget on behalf of WWF , and monitoring programme expenditure

- Liaise with stakeholders, especially the foreign partners and WWF Network

- Communicate FIP progress, developments, examples etc. to WWF and broader sustainable seafood community internationally, including managing communications around the FIP in the APSSTN website and other platforms and fora

##### Expert’s profile

WWF Regional Coordinator

- Qualifications and skills

- A higher degree in social sciences, fisheries science and/or business management

- Experience in Project management

- General professional experiences

- Extensive knowledge of Vietnamese fisheries and / or Vietnamese rural development

- Knowledge of the WWF network

- Working knowledge of English

#### DURATION

- Following the signature of the contract, the international consultant will be available for mobilisation within 10 working days. The exact date shall be agreed with WWF.

- The assignment will be for 5 years with a view to establishing long term linkages thereafter based on performance.

#### REPORTING

- With the assistance of the National Project manager, prepare a quarterly report for the WWF Asia Pacific Seafood Trade Network which will include summary FIP outcomes and Budget expenditure;

- With the assistance of the National project Manager, prepare a regular newsletter on FIP progress for circulation for all stakeholders

### WWF NATIONAL MANAGER

#### DESCRIPTION OF THE ASSIGNMENT

##### Global objective

The expected position by Dec 2025 is that:

- The fishery is suitable for advancement to MSC Full assessment and has met with all the Assessment criteria that link to the outcomes and activities described in the FIP.

##### Specific objectives

The purpose of the TOR is to set out the requirements for the National Project Manager to support the implementation and monitoring of the Vietnam Tuna Fisheries Improvement Project.

##### Requested Services

The Project Manager will be expected to undertake a series of activities during his/her tenure. The national officer will report directly to WWF and the M&E consultant, and will be responsible for coordinating the FIP budget and tracking quarterly progress of the FIP

##### Requested Services

The following duties are required:

- Monitoring the progress of each Activity as defined in the Programme LogFrame, and the above defined reports as provided in the above TORs

- Communicating with VINATUNA, MARD, DECAFIREP, and other stakeholders, as required

- Participating in workshops, and the activities of the TFMC

- Reporting and liaising with Regional Coordinator and the International M&E consultant

- Mentoring to various stakeholders as required

- Supporting the Project in a number of duties including preparing support input to reports for funders and the WWF Asia Pacific Seafood Trade Network.

##### Expert’s profile

WWF Project Manager

- Qualifications and skills

- A degree in environmental science

- Experience in Project management

- Knowledge of the Marine Stewardship Council Fisheries Assessment methodology

- General professional experiences

- Knowledge of Vietnamese fisheries and / or Vietnamese rural development

- Working knowledge of English and Vietnamese

#### DURATION

- Following the signature of the contract, the international consultant will be available for mobilisation within 10 working days. The exact date shall be agreed with WWF.

- The assignment will be for 5 years with a view to establishing long term linkages thereafter based on performance.

#### REPORTING

- Updating the WWF FIP Tracking document

- Collating FIP milestone outturns and proving these to the M&E consultant

- Preparing a quarterly report

- With the assistance of the National project Manager, preparing a regular newsletter on FIP progress for circulation for all stakeholders

Appendix 1:

PSA scores for targeted and retained species in longline fishery

PSA scores for targeted and retained species in handline fishery

There are no primary species as there are no supporting stock assessments for these species.

keithsymington@yahoo.ca

binh.vuongtrong@wwf.org.vn

The MSC FIP Benchmarking and Monitoring Tool (BMT) is used to assess the performance of each FIP over its project period. It may also be used by MSC to compare the progress of one FIP against the other.

There is no milestone for Performance evaluation, as performance outcomes are integrated into the Tuna Management Plan

M. Vincent, N, Ducharme-Barth, P. Hamer, J. Hampton, P. Williams, G. Pilling (2020), Stock assessment of yellowfin tuna in the western and central Pacific Ocean (31July) - Rev.03. WCPFC-SC16-2020/SA-WP-04 (Rev.3) . Available at https://meetings.wcpfc.int/node/11694

N. Ducharme-Barth, M. Vincent, J. Hampton, P. Hamer, P. Williams, G. Pilling (2020), Stock assessment of bigeye tuna in the western and central Pacific Ocean, WCPFC-SC16-2020/SA-WP-03 [REV3] . Available at https://meetings.wcpfc.int/node/11693

# WCPFC CMM 2021-01. Conservation and Management Measure for bigeye, yellowfin and skipjack tuna in the Western and Central Pacific Ocean, https://www.wcpfc.int/doc/cmm-2021-01/conservation-and-management-measure-bigeye-yellowfin-and-skipjack-tuna-western-and

Commercial fisheries are defined as national commercial fisheries as opposed to specific Provinces. As such a catch of 2,000 mt refers to the tuna catch by a single fishing method in Vietnam.

Vu Viet Ha, Tran Van Thanh, Dao Thi Lien and Vu Thi Hau, Research Institute for Marine Fisheries. Risk Assessment of Retained species caught by TUNA fishery IN VIETNAM, November, 2016

Assessment of the use and current status of circle hooks in vietnam tuna fisheries, WWF/VINATUNA 2021

WCFPC CMM 2008-01 requires observer 100% observer coverage for all purse seine vessels fishing in the EEEZ. Some countries apply 100% purse seine coverage to archipelagic waters, e.g. Papua New Guinea on the grounds that the WCPFC requires application of equivalent measures. WCPFC presently requires 5% observer coverage for Long Liners. IOTC requires 5% observer coverage for all vessels over 25 metres LOA.

MSC requires a level set at 0.5 BMSY. Any variation to this would require justification, but most explicitly must be shown to be sufficiently precautionary.

P4KSDI have had one PhD graduate trained in Hobart (CSIRO) – Lilis Saydeh. Proposed expert for this assignment, with the appropriate expertise,  could be Don Bromhead

P4KSI have had one PhD graduate trained in Hobart (CSIRO) – Lilis Saydeh. Proposed expert for this assignment, with the appropriate expertise,  would be Don Bromhead